Business Case – March 2026
Summary Sheet

Portfolio/ Business/Country Plan Summary: / The Africa Directorate business plan for 2025-26 emphasises the importance of “building long-term, mutually beneficial partnerships with African […] institutions, aligned with […] our Africa Approach.” It highlights using a “full range of tools” including diplomatic and development tools to support “a freer, safer, more secure, prosperous, healthier, and greener Africa – partnering with African states and others in addressing humanitarian crises, climate change, and biodiversity loss while advancing shared development goals in a rapidly changing world.” / The UK Office to the African Union [UKOAU] business plan for 2025/26 aims to building a “close UK-AU partnership that delivers on the UK’s objectives in Africa and the international system, in line with the Africa Approach […] demonstrates our support to the AU’s 2063 agenda, and helps to build a stronger, more effective African Union that provides continental leadership for resilient peace, climate change and economic and human development”. The CBP has three goals: (1) Strategic Partnership with the AU; (2) Development; and (3) Security and Governance. Goal 1 includes a commitment to “design a new AU Partnership Programme, as the FCDO’s flagship initiative for implementing the Foreign Secretary’s Africa Approach”. Goal 2 commits the UK to strengthening “the AU’s ability to delivery on shared priorities around governance and security, climate and nature, economic transformation, and health”. Goal 3 commits the UK to maintaining and strengthening “the longstanding UK-AU partnership on peace and security”. / We expect these themes and sentiments to be reflected in the new three-year business plan.
[note] Africa Directorate Business Plan for West, Sahel, Sudan and South Sudan – prior to merging into a single Africa Directorate in late 2025.

Title: / African Union Partnership (AUP) Programme
Programme summary (100 words maximum): / The AUP programme will support a partnership between the UK and AU to deliver results across four shared priority policy areas, in line with the UK Africa Approach: / Peace, security, and governance / Climate and nature / Economic growth / Migration / It will use a combination of diplomatic engagement, FCDO and HMG expertise, seconded technical experts, partnerships with specialist organisations, and direct financial support to drive forward progress on issues where there is shared UK-AU political interest in doing so. In the long-term, this partnership is intended to contribute to (1) a stronger relationship between the UK and the AU, (2) an AU that is more valued by member states, and (3) a more peaceful and prosperous Africa. / What is the rationale for UK Aid spending? (200 words maximum): / The AU is the principal multilateral body for Africa, a G20 member, and a key partner for the UK. Its priorities, as set out in its 50-year development plan – Agenda 2063 – closely align with our own, as set out in the Africa Approach. Working with the AU to tackle Africa’s challenges is in the UK’s strategic interest because a more stable, prosperous, and climate resilient Africa will reduce security threats to the UK, expand markets for UK businesses, and reduce the scale of irregular migration to Europe and the UK. In a time of geopolitical uncertainty, it is in the UK’s interest to invest in our partnership with the African Union. / The UK is well-placed to partner with the AU to make progress on our shared priorities. Our diplomatic reach, technical expertise – across peace, security, and governance; climate and nature; economic growth; and migration – and longstanding trusted partnership with the AU give us the ability to add genuine value to the AU’s own policy agenda.
Programme Value: £25 million		Country/ Region or Sector: / Africa Regional
Department/Country Office confirmation of review processes		Africa Programmes and Expertise (APEX), Africa Directorate
Contact name		Marco Simonetti
Threshold for final approval of Business Case: Africa Director
Date of Approval of Concept Note:	05/11/2025	Name and role of Approver / Baroness Chapman, Minister of State for International Development
Date of Approval of Business Case:	07/04/2026	Name and role of Approver / Kate Foster, Africa Director
Programme Code:	AMP Start Date: / 01/07/2026	AMP End Date: / 30/06/2029
Overall programme risk rating:	Moderate

Glossary

AfCFTA	African Continental Free Trade Area
AfDB	African Development Bank
AfSEM	Africa Single Electricity Market
AFSIT	Africa Facility to Support Inclusive Transitions
AGA	African Governance Architecture
APEX	Africa Programmes and Expertise Department
APSA	African Peace and Security Architecture
ARBE	Agriculture, Rural Development, Blue Economy, and Sustainable Environment department
AU	African Union
AUC	African Union Commission
AUCG	African Union Conflict and Governance programme
AU-GRAP	AU Green Recovery Action Plan
AUP	African Union Partnership programme
AUSP	African Union Support Programme
CEWS	Continental Early Warning System
DPAPS	Department for Political Affairs, Peace and Security
DRM	Domestic Resource Mobilisation
EAC	East African Community
EDIT	Directorate of Economic Development, Integration and Trade
EISA	Electoral Institute for Sustainable Democracy in Africa
ETTIM	Economic Development, Trade, Tourism, Industry, and Minerals department
FCAS	Fragile and Conflict Affected Settings
GCPA	Global Clean Power Alliance
GESI	Gender Equality and Social Inclusion
GGGI	Global Green Growth Institute
HLD	High Level Dialogue
HMG	His Majesty’s Government
ICF	International Climate Finance
JFA	Joint Financing Arrangement
LDC	Least Developed Country
MDD	Mediation and Dialogue Division
MOU	Memorandum of Understanding
MS	Member state
NDCs	Nationally Determined Contributions
ODA	Official Development Assistance
PFTD	Public Finance and Tax Department
PRO	Programme Responsible Owner
PrOF	Programme Operating Framework
PSC	Peace and Security Council
RECs	Regional Economic Communities
RMs	Regional Mechanisms for Conflict Prevention, Management and Resolution
SADC	Southern African Development Community
SEBE	Directorate of Sustainable Environment and Blue Economy
SRO	Senior Responsible Owner
TA	Technical Assistance
TPM	Third Party Monitoring
UCG	Unconstitutional Change of Government
UKOAU	UK Office to the African Union
UNDP	United Nations Development Programme
UPF	Unearmarked Pooled Funds
VFM	Value for Money

## Strategic Case

Why does the AU matter?
1. The AU is the principal multilateral body for Africa, founded to deepen political and economic integration and leverage cooperation on peace, security and development for the benefit of African citizens. As a continent-wide body with a mandate from its member states [MSs], the AU can intervene and act across Africa, either directly or through the Regional Economic Communities [RECs]. It is therefore a critical partner for the UK in addressing regional and cross-border challenges in Africa and championing African voices in global decision-making.
  [note] The RECs are regional blocs that promote economic integration, political cooperation, peace and security, and coordinated development among their member states. They serve as key building blocks of the AU, helping to harmonize policies, facilitate trade, and support continental initiatives such as the African Continental Free Trade Area and the African Peace and Security Architecture.
2. Working with the AU to tackle Africa’s challenges is key to supporting a more stable, prosperous, and climate resilient Africa that, in turn, will reduce security threats to the UK, expand markets for UK businesses, and reduce the scale of irregular migration to Europe. The AU also plays an important role in multilateral fora, as a G20 member and the multilateral body incorporating 54 UN-member states. In a time of increasing geopolitical competition, it is particularly important to continue to strengthen our partnership with this key institution.
How do the AU’s priorities align with our own?
1. The AU’s fifty-year development plan, Agenda 2063, sets out its blueprint for “transforming Africa into the global powerhouse of the future”. Key areas of focus – framed as aspirations – are growth, integration, good governance, and peace and security. These align well with our own priorities, as set out by Baroness Chapman at the recent launch of the UK’s Africa Approach. The new Africa Approach aspires to build respectful, long‑term partnerships in which the UK and African countries and institutions work with one another to drive mutual growth, shared prosperity, and real improvements in people’s lives.
  [note] Agenda 2063: The Africa We Want. | AU
  [note] Launch of the UK’s new Approach to Africa: Baroness Chapman’s speech - GOV.UK
2. The Africa Approach launch speech highlighted collaboration on peace and security as the “most important” thing the UK can do, as it serves as the “foundation of prosperity”. It commits the UK to work with the AU and other partners to support African efforts to “silence the guns” and promote post-conflict recovery. This aligns directly to Agenda 2063’s Aspiration 4 “A Peaceful and Secure Africa” which calls for a continent free from armed conflict. The Africa Approach also calls on the UK to “go much further to tackle violence against women and girls”, which complements the AU Convention on Ending Violence against Women and Girls. For the AU, the peace and security agenda is closely intertwined with that of good governance, democracy, respect for human rights, justice and the rule of law (Agenda 2063’s Aspiration 3) – a recognition that conflict arises where these are weak.
  [note] 44174-wd-EN_AU_Convention_on_Ending_Violence_Against_Women_and_Girls_CEVAWG_27.05.2025.pdf
3. The Africa Approach also underscores the UK’s desire to advance shared interests with the continent on climate and nature, including ensuring climate finance reaches those who need it most. This aligns with Agenda 2063’s environmental goals under Aspiration 1 and Aspiration 7, which call for “environmentally sustainable and climate-resilient economies” combined with “green growth and climate resilience” across the continent. AUC can play an important role in enhancing cross-continental impact, particularly in mobilising finance needed for MSs’ own plans and priorities.
4. The Africa Approach emphasises the need for the UK to shift from being a donor to an investor, placing mutual inclusive growth at the centre of its partnership with the continent. Agenda 2063’s Aspiration 1 outlines the need for economic transformation through diversification, industrialization, and value-added production, while its flagship projects – particularly the African Continental Free Trade Area, which is already a key area of UK support and engagement – are explicitly designed to accelerate growth, boost intra-regional trade, and foster job creation. The Africa Approach also resonates with Aspiration 7 on African-financed development.
5. The Africa Approach explicitly highlights migration as a priority area for the UK, particularly targeting root causes of irregular migration and strengthening border security to ensure that migration is fair and well-managed. Agenda 2063 frames the free movement of people within Africa as a key project. Aspiration 2 of Agenda 2063 envisions “An integrated continent, politically united and based on the ideals of Africa’s renaissance” where free movement of people contributes to trade and mobility within Africa.
  [note] Free Movement of all Persons and African Passport | AUDA-NEPAD
How can the AU advance these priorities?
1. The AU has a vital role to play in representing its member states on the global stage, ensuring that their collective interests are articulated and advanced within multilateral fora such as the G20 and United Nations. The AU also has the mandate to hold member states to account for the principles and commitments they have made under the AU’s legal instruments (treaties, protocols and decisions), including on good governance, respect for human rights, and the rule of law. While it faces persistent capacity constraints, African member states care about the AU, and African leaders and foreign ministers invest considerable time in its operation.
2. Africa faces an escalation of armed conflicts and democratic backsliding. In the Horn of Africa, the ongoing civil war in Sudan has created the world’s largest displacement crisis. Elections continue to be a flashpoint for violence. Since 2020 the rate of unconstitutional changes of governments [UCGs], particularly in the Sahel, has increased, reversing the decline of previous decades.
  [note] GPI-2025-web.pdf
  [note] Understanding Coup Trends in Africa – unpublished paper (2025)
3. The AU approach to peace, security and governance is enshrined in the African Peace and Security Architecture [APSA], as well as the African Governance Architecture [AGA] – with both frameworks housed in the merged Political Affairs, Peace and Security [PAPS] department. The AU monitors conflict risk through the Continental Early Warning System [CEWS] and uses diplomatic engagement, mediation missions and peace support interventions in emerging and entrenched conflicts across the continent. For example, the AU has convened a high-level team to mediate political dialogue between parties to the DRC conflict, including armed groups and regional stakeholders. The team, led by Togolese president Gngassingbé, consists of former presidents and will be deployed in 2026.
  [note] A process to review both APSA and AGA was announced in February 2025 to ensure they are able to meet the changing nature of peace and governance challenges. This presents an opportunity to address some of the challenges in delivery in this area.
4. The AU possesses crucial strengths in its legitimacy and diplomatic influence, however, in practice the AU’s response to conflict is often reactive and ad hoc, taking place once crises have already escalated. The space for the AU to respond to crises is increasingly constrained. While the AU derives legitimacy as an African-led decision-making body, member state sovereignty and interests increasingly determine when it can intervene. There is an increasing desire for regional responses to conflict and the AU, under the principle of subsidiarity, must respect the role of the Regional Economic Communities [RECs]. In spite of these challenges, the AU remains an important actor in achieving peace, security and better governance on the continent. Furthermore, as great power competition risks side-lining African priorities, the AU remains central to asserting African agency.
  [note] International Crisis Group (2025). Eight Priorities for the AU in 2025. https://www.crisisgroup.org/africa/african-union-regional-bodies/b205-eight-priorities-african-union-2025
  [note] Etyang, O., Abdulkadir, T., Masah, C. & Mapri, T. (2024). Evaluation of the AU Peace and Security Council: Lessons from 20 years of intervention and recommendations for the future. Accord. https://www.accord.org.za/publication/evaluation-of-the-african-union-peace-and-security-council-lessons-from-20-years-of-intervention-and-recommendations-for-the-future/
  [note] Research Analysts minute - AU-UN Relations on Peace and Security (Jan 2023)

Supporting the AU’s Peace and Security reforms / In February 2025, the AU commissioned a review of its Peace and Security Framework, comprising the African Governance Architecture [AGA] and African Peace and Security Architecture [APSA]. This review was commissioned in the context of a wider AU reform effort, which has been ongoing since 2016 and is currently led by Kenyan President William Ruto. The findings of this review were presented by President Ruto at the AU Summit in February 2026, with several recommendations made for strengthening AGA and APSA, including: / Do further work to integrate AGA and APSA into a single coherent framework / Review the working methods of the Peace and Security Council / Establish a fully-funded African Standby Force headquarters / Strengthen coordination on early warning / Expand the Peace Fund endowment and increase its autonomy / Increase ratification and implementation of relevant normative frameworks / Use greater sanctions in the event of unconstitutional changes of government and engage more to return member states to constitutionalism / Develop an African Foreign Policy framework aimed at enhancing Africa’s agency in international relations / Establish an effective structure to support the Panel of the Wise with the capacity to deploy and sustain political dialogue in crisis situations / AUP will support the UK’s efforts to work with the AU to advance the elements of this reform agenda that we judge are most likely to produce positive results for African citizens.

1. On economic growth, Africa’s trajectory has been shaped by resilience to shocks, structural transformation, and increased (albeit slow) regional integration. While growth in sub-Saharan Africa is expected to reach 4.2% by 2027, persistent challenges, such as elevated debt service ratios, fiscal constraints, climate shocks, and below-target per capita income levels, continue to temper the pace and equity of development. The AU joined the G20 as a permanent member during the 2023 summit, marking a significant step in amplifying Africa's voice in global economic discussions.
  [note] AETO_3.indd
2. The AU is actively taking a central role in managing the continent's growing debt crisis. There are 28 African countries at high risk of or in debt distress. These countries are facing increased debt service burdens, presenting liquidity risks and crowding out growth-enhancing and poverty-reducing spending (e.g., health, education, climate).​ The AU is beginning to play a more substantive role: its first debt conference (May 2025) resulted in the Lomé Declaration and, subsequently, the Common African Position on Debt. Given, (i) the scarcity of AU resources working on debt, (ii) the importance of the AU voice in representing debtors in the G20, and (iii) the UK’s aims to strengthening debtor voice, there is scope for increased collaboration on this issue. An inaugural AU-UK technical dialogue on sovereign debt sustainability (scheduled for Q1 2026) will provide further suggestions for collaboration.
  [note] Debt challenges were raised repeatedly by academia, civil society and by Global South leaders during the recent consultations on the UK’s new approach to Africa.
  [note] 44785-doc-EN_Draft_Zero_Declaration_AU_Conference_on_Debt_Final.pdf
3. On climate and nature, although African nations account for only around 2–4 % of global emissions, they endure faster warming, higher economic losses, extreme livelihood risks, and deeper vulnerabilities than most regions. At the same time, Least developed countries [LDCs] countries, particularly the most climate vulnerable, face barriers in accessing, and also absorbing, much-needed climate finance for adaptation and mitigation strategies. Fragile and conflict settings face particularly severe impacts as resource degradation, water scarcity and climate risks exacerbate conflicts (e.g. over natural resources) and access to funds is limited. The UK prioritises increasing access and delivery of quality climate finance from a range of sources. Working with AU mechanisms, like the Sustainable Environment and Blue Economy [SEBE] Directorate, can increase the AU’s ability to coordinate member states and RECs in accessing finance, as well as working on transboundary resources, particularly water. Beyond coordination, the AU can serve as a platform for sharing and scaling African examples of effective access models and linked reform of national systems.
  [note] State of the Climate in Africa 2023
  [note] UNDP - Climate Finance for Sustaining Peace: Making Climate Finance Work for Conflict-Affected and Fragile Contexts
4. The AU has also signed a Finance Mission Work Programme with the UK under the Global Clean Power Alliance [GCPA] to collaborate on mobilising private finance and building institutional capacity for Africa’s clean energy transition. The AUC is endeavouring to champion a continental masterplan for an African Single Electricity Market [AfSEM] to drive energy access and interconnectivity that is aligned with countries’ nationally determined contributions [NDCs].
  [note] AU Commission and Global Clean Power Alliance finance mission: action plan - GOV.UK
5. Intra-African migration dominates African mobility and rates are increasing. Much regular African migration is circular, often within countries, and depends on labour dynamics. While regular migration can support development outcomes, irregular channels present very high risks to migrants due to their control by organised criminal groups. What drives people to migrate irregularly is complex and personal but includes climate change, conflict and lack of economic opportunities. The AU’s approach to both regular and irregular migration is guided by its Migration Policy Framework for Africa and related protocols. It emphasises the protection of migrants’ rights, the promotion of safe, orderly, and regular migration, and the reduction of irregular flows through legal pathways and regional integration. The AU sees labour mobility and visa openness as a key aspect of its economic growth agenda, through harmonisation of migration policies alongside strengthened border management. The Africa Approach seeks to ensure that migration on the continent is fair and managed, and AUP will seek to engage with the AU to improve migration management that benefits member states and citizens, while contributing to the UK’s foreign policy objectives on irregular migration.
  [note] An analysis of trends and patterns of migration in Africa - New South Institute.
  [note] African Migration Trends to Watch in 2024
  [note] Addressing the “Root Causes” of Irregular Migration: Four Lessons for the AU-EU Summit
  [note] The Migration Policy Framework for Africa (MPFA) | AU
6. The interconnected nature of these challenges is evident in the way climate change, conflict, migration, and economic growth continually impact and influence one another. Environmental degradation and climate risks, such as droughts, floods and rising temperatures, not only threaten economies – especially in least developed countries –but also contribute to the escalation of resource-based conflicts, which in turn drive forced displacement and hinder development. These dynamics fuel both conflict-related and climate-related forced migration, with irregular migration presenting risks to migrants and policy challenges for countries like the UK. Labour migration remains a vital avenue for economic opportunity, and AU-level coordination is crucial for maximising its benefits, improving border governance and supporting the continent’s ability to respond to displacement. The AU’s mandate spans these interconnected issues, and in some areas, there is cross-departmental collaboration, for example, in the drafting of the Common African Position on Climate, Peace and Security.
  [note] WB “Migration - Africa’s Untapped Potential”
  [note] Cultivating common ground on climate, peace and security | PSC Report
7. The AU’s strengths present genuine opportunities to advance FCDO priorities across the continent, yet persistent structural constraints and political economy challenges remain. The UK needs to meet the AU where it is and be guided by what is feasible. This approach requires political acumen to identify where there is genuine will and scope within the AU to deliver results.
Embedding a Politically Informed Approach / The AUP programme will need to navigate a complex political economy within and around the AU. We recognise that delivering results will require us and our partners to think and work politically – meaning that we will need to build and maintain our understanding of the ideas, interests, and institutions influencing those with the ability to help us realise or frustrate our goals, and develop interventions that recognise, and where appropriate, seek to change those influences. The London-based programme team will work closely with colleagues from the UK Office to the AU to maintain a comprehensive understanding of the political economy of the AU and ensure this feeds into programming decisions. / We will also expect any external partners we work with to demonstrate their own knowledge of the AU’s political economy or outline a plan to develop that knowledge as part of their work. / Where appropriate, we may also commission analysis to help us understand the political economy of particular issues and enable us to identify the most promising entry points and approaches. This analysis may also identify where intervening is not appropriate for AUP.

Why is the UK well-placed to partner with the AU to make progress?
1. AUP is well-positioned to build on the successes of its predecessors (the UK’s AU Support Programme (2018-2022) [AUSP] and AU Conflict and Governance Programme (2022-2026) [AUCG]), as well as to complement other UK programmes working with the AU on trade, climate change, health, humanitarian and cyber.
2. During the implementation of AUCG, our approach became increasingly flexible, responsive and politically agile, with interventions closely aligned with the work of posts and thematic departments. This evolution is evident in AUCG’s more recent approach to rapidly responding to AU requests. For example, FCDO was asked to support the AU’s mediation efforts in Eastern DRC.
3. The new AUP programme will continue to scale and test this model of engagement whilst also working with reformers and looking for opportunities to strengthen long-term capability in areas of core interest where possible. The focus of the new AUP programme will extend beyond peace and security to support the strategic objectives of the UKOAU’s Country Business Plan. This new approach also acknowledges that these issues are inter-linked in both the UK’s thinking and the AU’s, e.g. on climate security.
Delivering a modern development partnership / AUP will be the UK’s main tool for building and sustaining a modern partnership with the AU. As a partnership programme, AUP will meet the AU where it is and be guided by what is feasible within the constraints that exist. Its focus will be on identifying tangible issues that both the UK and AU prioritise and working with the AU to make progress that benefits Africans and, in turn, the UK. While progress on these issues will be valuable in itself, it is central to AUP’s theory of change for that, in the long-term, delivering results will increase the perceived value of the AU amongst member states, leading to a more sustainable financing model and thereby reducing the AU’s reliance on external support. / Delivering results will require the UK to engage in a mix of capacity supporting (providing specialist technical inputs to support the AUC’s core capacity to make progress on priority issues), targeted capacity building (strengthening aspects of the AUC’s core by addressing skills gaps and supporting system reform), and, occasionally, capacity substituting (filling functions that the AUC should fill but is currently unable to due to financial or other constraints). Capacity substitution will only be used where it is critical to progress and where alternative options have been exhausted. / Our approach will reflect the four shifts that the Minister for Development has set out as central to the UK’s modern approach to development: / From donor to investor – we will partner with the AU to enable it and its member states to access new sources of innovative finance and private sector investment. For example, we will work with the Global Green Growth Institute [GGGI] to help the AU support member states to access international climate finance investments. / From service delivery to system support – we will work to strengthen the AU’s systems through influencing and targeted capacity building to address critical constraints that prevent progress on the issues we jointly care about. For example, in our elections work we will seek to work with the AU to strengthen approaches to risk assessment and prioritisation so that threats can be more effectively addressed. / From grants to expertise – we will use diplomatic engagement, FCDO and HMG expertise (including through a programme-funded advisor and the FCDO’s Communities of Expertise), seconded technical experts, and partnerships with specialist organisations to provide expert advice to the AUC across our shared priorities, only using direct financial support where necessary to unlock progress. / From international intervention to local leadership – we will work closely with colleagues in the UK Office to the AU to ensure that all our work is aligned with AU priorities and has genuine AU political support. We will focus our efforts on areas where the AU has committed to reform, including those relating to the AU’s peace and security agenda.
[note] International-development-ll.pdf

How will this programme help?
1. Building on the foundations and lessons from AUCG and responding to the direction of the Africa Approach and Agenda 2063, AUP will use a targeted blend of diplomatic engagement, FCDO and HMG expertise, seconded technical experts, partnerships with specialist organisations, and direct financial support to strengthen AU-led efforts to drive progress in our shared priority areas of: peace, security and governance, climate and nature, economic growth, and migration. In line with the Africa Approach’s focus on partnership, AUP will be based on an assessment of where there is genuine shared desire for progress. This will require the programme to be flexible, opportunistic and responsive to emergent needs and the dynamic political economy of the AU.
2. AUP will be ambitious by maintaining budget headroom to position the programme as a vehicle for other FCDO and xHMG departments to work with the AU. The programme will seek to create openings to leverage funding from elsewhere which can be channelled through this business case. This model has been tested within AUCG, which has received funding from the British Embassy in Ethiopia to support an AU monitoring mission in Tigray, from Public Finance and Tax Department [PFTD] to second a tax policy expert to the AU’s Directorate of Economic Development, Integration and Trade [EDIT], and from the ISF to second expertise on peace support operations to DPAPS.
3. AUP’s anticipated outcome level changes are focused around the four priority areas identified above. These outcomes detail the areas of change we expect the programme to contribute to over the three years.
            1. Peace, security, and governance: the AU is more actively monitoring conflict trends and democratic processes and rapidly deploying its resources to mitigate risks of conflict or mediate the cessation of violence.
            2. Climate and nature: the AU is supporting MSs (particularly FCAS) and RECs to develop strong investment-ready proposals to access climate finance, and more effectively promoting other environmental measures (such as regional interconnectivity of clean electricity).
            3. Economic growth: the AU is playing a more effective coordinating role on the continent on debt, tax, and other shared economic challenges.
            4. Migration: the AU is playing a more effective coordinating role on migration governance (e.g. through better migration data generation and sharing) to enable the safe and orderly mobility that drives development.
4. By making progress on these priority areas we expect the programme to contribute to wider efforts to:
            1. Further strengthen the relationship between the UK and the AU, allowing us to collaborate more effectively on global issues and strategic priorities.
            2. Further increase the perceived value of the AU amongst member states, thereby encouraging member states to increase their financial support to the AU.
            3. Create a more peaceful and prosperous Africa, thereby minimising threats to the UK and maximising opportunities for the UK.
How will this programme promote equality?
At a minimum, the design and implementation of AUP will be compliant with the International Development (Gender Equality) Act 2014 and the Public Sector Equality Duty (in the Equality Act, 2010). The programme will adhere to ‘do no harm’ principles and interventions will not worsen inequality and, where possible, will support the practical needs of marginalised groups. This will involve ensuring that all programme partners have (a) based their project design on sound gender and social inclusion [GESI] analysis (b) developed a credible plan to monitor and ensure that any adverse impacts of the programme can be both identified and addressed. AUP will also continue to build on AUCG by supporting initiatives specifically designed to promote gender equality, including the Network of African Women in Conflict Prevention and Mediation (FemWise), which is intended to increase women’s access to and participation in peace mediation and negotiation in Africa.
Climate and Environment
1. AUP is in line with UK Climate and Environment Commitments as set out in Programme Operating Framework [PrOF] rule no. 5, namely alignment with Paris Agreement commitments, environmental protection, and International Climate Finance. As the programme focuses primarily on policy and technical assistance, there are no specific climate risks. The addition of a climate and nature component will align with and complement broader HMG climate engagement with the AU, including on the AU-GRAP.
2. Paris Agreement alignment: As emission reductions are not a primary objective of the programme, shadow carbon pricing has not been carried out in accordance with PrOF Rule 5.
3. Environmental Protection: Under the climate and nature outcome area we expect the intervention will lead to positive environment and climate outcomes. PrOF rule no. 5 requires programmes to take into consideration environmental risks. Given the focus on policy and technical assistance, we assess the environmental risks to be minimal. All efforts will be made to minimise air travel and use of consumables by programme partners and staff. On the climate and nature outcome area, we will collaborate with the technical experts on climate within FCDO and within partners to ensure that AU initiatives supported by the programme ‘do no harm’.
4. International Climate Finance [ICF]: One of the main outcome areas is to support African member states and RECs to access international climate finance. This funding would qualify as ICF. The design of this component will identify the specific ICF key performance indicators this funding will report against.
  [note] https://www.gov.uk/government/publications/uk-international-climate-finance-results-2025/uk-international-climate-finance-results-2025#icf-key-performance-indicator-results
Compliance with Programme Operating Framework
1. Safeguarding: Through the AUCG programme, FCDO has been able to engage with the AUC on their ability and willingness to uphold adequate standards of safeguarding. All agreements and contracts will adhere to the UK’s safeguarding requirements and will only proceed following due diligence assessments. AUP will maintain a risk register throughout the programme cycle with explicit mitigation measures for the full range of safeguarding issues as related to FCDO’s focus on sexual exploitation, abuse and harassment, as well as other social or environmental risks, with clear oversight and responsibility. Actions identified at the design stage will be suitably codified in delivery documents (including contracts, MOUs etc.) and will be regularly monitored and updated.
2. Public Sector Equality Act: AUP will ensure that people with protected characteristics are considered during delivery, assessing both positive and negative impacts on them so that risks can be mitigated. Partners will be asked to consider this in proposals and throughout implementation.
3. Counter-terrorism: All programme funding is through instruments covered by the Programme Operating Framework. Partners and suppliers will undergo due diligence checks and mechanisms will be established to ensure proper use of funds. The risk of funds being diverted to support terrorism is low.
4. Partnership Approach: AUP is grounded in a partnership with the AU that seeks to be mutually beneficial. The programme will also work with other partners, both from the continent and from outside Africa. It will be important that these partners are trusted by the AU to support their work and activities. Therefore, the programme will benefit from their expertise and experience in collaborating with the AU.
## Appraisal Case

Options for allocation of resources
1. Working in partnership with the AU to strengthen its capabilities and impact across a range of shared AU-UK thematic priorities is complex and will demand a flexible and agile approach to programme implementation. Based on the experience of the AUCG programme and the expansion of thematic priorities based on the Africa Approach, the AUP programme considered a range of options to achieve the intended outcomes.
2. The development of the concept note identified four thematic priorities for the AUP programme based on the Africa Approach and the AU’s priorities. This is a change from the current AUCG programme which focused only on peace, security, and governance. This required AUP to consider different options on the balance of focus between these four thematic areas, particularly given the limited funding anticipated for the programme. Of the £25m programme value, £8.7m is expected to come from Africa Directorate’s ODA allocation, with the remaining £16.3m headroom enabling other parts of FCDO and xHMG departments to channel funding through the programme.
3. We have assessed three options for the allocation of anticipated ODA resources within the programme:
  [note] There was also the option to “do nothing”, i.e. no longer provide funding/support to the AU. This was discounted at the stage of developing the concept note. It would have meant losing the gains of previous UK programmes with the AU and undermined the relationship built up by the UKOAU.
            1. Allocate the confirmed resources equally across the four outcome areas – peace, security & governance, climate & nature, economic growth and migration – While this option would allow equal funding to be allocated to each thematic area, it would spread the resources available too thinly. This option would reduce the budget for peace, security & governance activities considerably compared to AUCG. AUCG had a budget of around £4m per year for peace and governance activities, whereas this option would entail an initial budget of about 25% of that. This would lead to current investments (into the Joint Financing Arrangement [JFA] for DPAPS and seconding technical expertise) and partnerships (with EISA, CMI and Berghof Foundation) being curtailed, which could undermine existing gains of AUCG with DPAPS and impact our relationship with the department. This approach also overlooks the fact that the UK’s collaboration with the AUC is at different stages – on peace, security & governance the UK has a long history of support and investment, whereas migration is a new area of collaboration that will require an approach that pilots initiatives to understand where the UK can add value.
            2. Maintain an exclusive focus on peace, security & governance with confirmed resources – This option would allow AUP to continue the interventions from AUCG on peace, security & governance at the same level of funding. AUP would be able to maintain the strong relationship with DPAPS and build on the investments of previous programmes. This approach also acknowledges the size and influence of DPAPS compared to other departments in the AUC. Other outcome areas would be funded as the programme secures other resources from across FCDO and xHMG. However, this approach could make it difficult for the UK to engage with departments outside DPAPS if it there is no confirmed funding and uncertainty over the appetite of other FCDO or HMG departments to buy-in to AUP. This approach would also not reflect changed approaches to partnership under the Africa Approach and the shifts in the UK development approach and FCDO priorities.
            3. Pursue a flexible, agile, and responsive approach across the four outcome areas – peace, security & governance, climate & nature, economic growth and migration – This option will allocate resources flexibly between the outcome areas depending on opportunities arising. This recognises the importance of the strategic priorities enshrined in the Africa Approach and Agenda 2063, allowing the programme to be flexible in leveraging new resources and responding to emerging opportunities for collaboration with the AU. In the first year of the programme, AUP will likely allocate most of the financial resources available to the outcome on peace, security and governance. This will enable the programme to build on the interventions from AUCG, particularly scaling work piloted on mediation support in the final year of that programme. The Year 1 budget will also allocate resources to new partnerships in the other outcome areas and explore opportunities to second technical expertise into departments outside DPAPS. This option has the benefit of testing different areas of collaboration that could leverage funding from other teams in FCDO and HMG – e.g. AUP could use the allocated resources to fund a secondment into ETTIMs to explore options for further FCDO funding on economic growth outcomes. We anticipate that the balance of resources between the outcomes in the budgets for Years 2 and 3 will be very different as new opportunities emerge with the AUC and with xFCDO and xHMG departments. The programme level steering committee (detailed in paragraph 93 in the management case) will be the main structure overseeing these decisions.
4. The business case recommends the third option – to take a flexible and adaptive approach to how the resources are allocated between outcome areas. The proposed breakdown of allocated funding is outlined in Table 4 in the financial case for Year 1 of programme.
Options for delivering support
Based on this decision, we have assessed a further set of options concerning how we deliver our support:
            1. Only provide technical expertise from FCDO and x-HMG – This option would focus AUP on leveraging FCDO and x-HMG expertise to respond to requests for collaboration from the AU. The UK’s modern approach to development promotes a shift from grants to expertise. AUP will have access to a wide of range of FCDO technical expertise that can be drawn on to support delivery. This could include programme-funded technical advisors, research analysts, FCDO staff working at posts across Africa, and technical support from the FCDO’s Communities of Expertise. The programme may also be able to draw on support from other HMG departments and agencies, particularly those with well-developed international capacity building capabilities. For example, on our elections work an FCDO technical advisor working on AUCG has developed an election risk assessment framework that could be used by the AU to support risk assessment and prioritisation; we are also in discussions with the UK Electoral Commission about the possibility of engaging with the AU. This option would be relatively low cost – potentially limited to a small number of programme-funded roles. However, given constraints to FCDO and HMG capacity, it would not provide the breadth or depth of support necessary to drive significant change or deliver meaningful results. Nor would it provide the flexibility required to respond effectively to opportunities as they emerge.
            2. Only provide seconded technical experts and partnerships with specialist organisations – This option would identify partners to work with the AU, providing different forms of support and accompaniment. AUCG has worked with organisations with strong technical expertise and a close working relationship with the AU to deliver specific initiatives to successfully achieve programme goals; for example, AUCG’s support to the Electoral Institute for Sustainable Democracy in Africa has provided support to the AUC on its election monitoring programme. AUCG has also facilitated secondees and technical experts into DPAPS, and other parts of the AUC, to address specific capacity gaps or to support AU interventions on the continent. This in-kind support facilitated by NORCAP provides experts at the request of the AUC and who, once in post, are accountable to AUC departments. This option would allow support to be targeted to shared UK-AU priorities, which reflects the UK’s commitment to move from donor to partner outlined in the Africa Approach. This option also enables AUP to provide flexible support to AUC departments that can be matched to their immediate needs. However, only pursuing this option would not make use of the expertise that FCDO and HMG could bring to bear and would risk important relationships with the AUC being held solely by our partners rather than by FCDO.
            3. Only provide direct financial support to the AU – This option would channel AUP’s resources directly to AUC departments. This could take place through one or through contributions to the Africa Peace Fund. Another option is to provide direct support to specific AU departments or specialised agencies through a bilateral MOU. The AUCG programme currently directs funding through the JFA with DPAPS and there is strategic consideration behind this: Commissioner Bankole and other AU seniors have previously lamented partners not providing direct funding to the AU, or being coordinated in their funding – therefore pooled partner funding represents a preferred option for AU financing, compared to bilateral agreements with AUC departments. By providing support to the JFAs, AUCG observed that the UK experienced increased diplomatic access with the AUC and a “seat at the table” on donor coordination. To achieve the outcomes on climate & nature, economic growth and migration, AUP could support the JFA providing core funding across the AUC. These options would provide a coherent and predictable funding approach to facilitate the functioning of the AUC and enable the AU to allocate funds to its own priorities. While providing provide direct financial support would prioritise AU ownership and would increase the space for the UK to engage diplomatically with the AU, only pursuing this option would reduce the FCDO’s space to align the funding to UK priority areas within the Africa Approach. It would minimise the control of the programme team in ensuring that AUP delivers tangible results. The AU’s budgeting cycles are rigid and long-term (often determined up to 2 years in advance) and this option would undermine the flexibility of the programme to respond to emerging opportunities or crises, and in turn the needs of the AUC to be able to respond to these.
              [note] We considered providing support to the Africa Peace Fund, which finances peace support missions and other operational activities related to peace and security. However, we decided that UK direct support to this fund would undermine the goal of the fund itself which seeks to raise resources from MSs and the private sector.
              [note] FCDO had previously provided funding to DPAPS under a bilateral agreement but joined the JFA in order to increase donor coordination and influence the arrangement itself.
            4. Provide support to the AU through a mixture of FCDO and HMG expertise, seconded technical experts, partnerships with specialist organisations, and direct financial support – This option would combine elements of the options above – leveraging FCDO and x-HMG expertise to connect the AU to the Africa network and technical experts; seconding technical expertise to AUC departments and specialised agencies to support delivery capacity; partnering with specialist organisations (through grants, contracts, or MOUs) to provide expert advice to the AUC that will help advance shared UK-AU goals; and providing direct financial support to the AUC across the outcome areas, through Joint Financing Arrangements and bilateral MOUs. This option combines the advantages of the options above and gives the programme a range of means to achieve change. It allows AUP to support AU longer term capability, alongside targeted interventions that can respond to emerging opportunities. This approach is well-suited to delivering on a range of outcomes with reduced funding. The early lessons from AUCG’s support to the AU’s involvement in the Eastern DRC peace process shows that the flexible and strategic combination of different interventions can leverage significant gains with a limited budget.
1. We recommend the fourth option: to use a flexible mixture of interventions to achieve the programme’s intended outcomes. This is based on the emerging lessons and experience of the AUCG programme. This option provides value for money through:
            1. Economy – The chosen option ensures resources are deployed only where they add clear value. It avoids overreliance on long, inflexible AU budgeting cycles, reducing the risk of funds being locked into nonpriority areas.
            2. Efficiency – The chosen option blends direct and indirect modalities to provide timely, flexible support that can adapt to emerging crises or opportunities – avoiding delays associated with solely funding AU core budgets. In-kind support can fill immediate capacity gaps efficiently, ensuring progress on agreed priorities.
            3. Effectiveness – The chosen option maintains a “seat at the table” through direct contributions to the JFA, strengthening UK diplomatic influence and alignment with AU priorities. It supports both long-term institutional sustainability (via direct funding) and short-term operational needs (via in-kind/indirect support).
            4. Equity – The chosen option centres African leadership through contributions to AU managed resources while ensuring the UK can responsively support initiatives that are under-resourced. It balances donor–partner dynamics by respecting AU priorities while still addressing areas critical to UK objectives and shared UK–AU interests.
Implementing the Preferred Options
Flexibility will be key to AUP implementation. The programme team (made up of both APEX and UKOAU staff) will use the criteria below to facilitate decisions over support to emerging opportunities, convening posts and thematic departments as necessary. This framework will be applied to assess requests for support from the AUC as well as interests of other FCDO/HMG departments in working with the AU. Oversight of this decision-making process will be provided by a Programme Steering Committee – this structure is outlined in the management case.
            1. Does the intervention contribute to the FCDO’s thematic and geographic priorities and follow the principles outlined in the Africa Approach?
            2. Does the intervention meet specific needs identified by the AU? I.e. requested by AUC and supporting Agenda 2063.
            3. Does the intervention respond to an opportunity or challenge where AUP is best placed to create impact?
            4. Is there political support within the AU, amongst relevant influential officials and MSs’ Representatives, for the changes expected to be supported by this intervention?
            5. Will the intervention strengthen capability rather than substitute for capacity that could be provided by the AU if it were sufficiently resourced?
Based on these criteria, AUP will be able to deploy a combination of options tailored to the specific opportunity or issue. For example, an intervention could engage an external partner to accompany the AUC on a particular policy, while also providing a secondee to ensure the relevant department has the short-term necessary expertise available, whilst building longer term capability through accompaniment and training. This could be supported by expertise from the relevant FCDO thematic department, provided through a Community of Expertise mechanism, as well as UK diplomatic engagement with senior AU figures on the importance of the policy. Fig. 1 below shows the process by which AUP will make decisions, design response and maintain feedback loops to ensure lessons are fed back into the programme.

Fig. 1

Theory of Change
1. The full Theory of Change is detailed below (Fig.2). The AUP ToC positions the programme as the flagship initiative for implementing the priorities and approaches set out in HMG’s recent ‘Africa Approach’ speech. The problem statement is framed by the challenges faced by the continent that are identified as shared priorities by the UK and the AU. The programme will seek to respond to these challenges through identifying ways to support and collaborate with the AU.
2. To support the AU to be better able to address these challenges, the AUP programme will deploy a combination of different interventions (diplomatic engagement, FCDO and HMG expertise, secondment of technical experts, partnerships with specialist organisations, and direct financial support) to respond to opportunities and requests from the AU. The outputs of AUP will depend on the nature of these different interventions. The aim will be to make progress on shared priorities while also, where possible, strengthening the AU’s capability to operate without external support in the future.
3. At the outcome level, AUP has identified the changes the programme expects to contribute to by the end of the three years. These relate directly to the four priority areas of intervention. We anticipate that outcomes of AUP will be seen through the accumulation of ‘success stories’ detailing instances of where and how strategically deployed UK support and collaboration has enabled the AU to deliver on its mandate – e.g. in deploying its resources to positive effect in a political or security crisis, or in convening MSs to deliver a positive policy change.
4. Given that some of the interventions will respond to new crises or test new ways of working with the AUC, it will be important to embed rapid learning and decision feedback loops at activity, output, and outcome levels to keep-AU focused interventions adaptive and aligned to impact. For example, the programme will assess whether secondments are providing the analysis and advice required by the AU to make progress on shared priorities, and adjust the approach accordingly.
5. The impact statement focuses on how, by delivering tangible progress in the four priority areas, the programme will contribute to a stronger relationship between the UK and the AU, an AU that is more valued by member states, and a more peaceful and prosperous Africa.
6. Across the ToC there are several assumptions, some of which link to our commercial case decision-making criteria below. Some of these assumptions will stay the same throughout the lifetime of the programme, while others will be affected by both AUP itself and factors beyond AUP. For example, we expect that achievement of positive outcomes (and outputs), will help ensure that the AUC continues to see the UK’s support as relevant and effective, and help the programme to navigate the political economy of the AU.
Fig. 2: Theory of Change

## Commercial Case

1. AUP will maintain a flexible and adaptable approach to working in partnership with the AUC. This will require the use of different delivery options to achieve the programme objectives. This flexible approach will be underpinned by the £16.3m budget headroom which other parts of FCDO and xHMG departments can use to buy into the programme and deliver shared objectives through the AU.
2. This approach will combine the following intervention options –
            1. Leveraging FCDO and x-HMG expertise to connect the AU to the Africa network and technical experts
            2. Seconding technical expertise to AUC departments and specialised agencies to support delivery capacity
            3. Partnering with specialist organisations (through grants, contracts, or MOUs) to provide expert advice to the AUC that will help advance shared UK-AU goals
            4. Providing direct financial support to the AUC across the outcome areas, through Joint Financing Arrangements and bilateral MOUs
These interventions will be supported by diplomatic engagement through the UKOAU in Addis Ababa.
1. In Year 1, AUP will continue to fund some interventions implemented under AUCG on peace, security and governance, and to pilot new interventions under the outcomes on climate and nature, economic growth, and migration. These pilots will be developed through a co-design process with the partner and the AU (and potentially other donors) during the first six months. Where appropriate, AUP will then sign funding agreements for a six-month pilot to be assessed on whether this work should/can be scaled up in Year 2. Any new partners will be subject to appropriate due diligence processes. Where these do not give us confidence that the partner is able to manage the funds and deliver agreed outcomes, then we will seek to identify new partnerships or deploy other interventions.
2. As opportunities arise, the programme may identify new partnerships to deliver activities with the AU, particularly as new work develops under outcomes on climate and nature, economic growth, and migration. The programme team will assess whether the request for support/engagement (from AUC and UK) meets the criteria for support outlined in paragraph 41 of the appraisal case. Part of this process will identify whether a funding agreement with a new partner is required (as opposed to working within an existing partnership, drawing on FCDO or xHMG expertise or providing funding directly to AUC).
Year 1 interventions
Leveraging FCDO and x-HMG expertise
AUP will draw on technical expertise from within FCDO and across HMG to support programme outcomes. AUP will initially fund a programme-funding advisor role (see management case for further detail and considerations) to manage relationships with the AUC on the agreed priority areas, identify opportunities for collaboration, provide targeted technical advice, develop plans for further engagement, and oversee technical interventions. The need for additional programme-funded advisory capacity will be assessed as the programme develops. This advisor will draw on support from FCDO’s Communities of Expertise, which are able to provide short-term technical advice across a range of thematic areas, as well as from FCDO’s Research Analysts where appropriate (e.g. on AU-led work to facilitate the DRC peace process). The programme-funded advisor will also engage with FCDO posts to ensure join up on country-specific issues, such as AUC support to election monitoring or work on climate financing. We will also explore the possibility of partnerships with HMG departments and agencies that are able to provide international capacity building capabilities and could work with the AUC to help drive progress in priority areas.
Seconding technical expertise to AUC departments and specialised agencies
Building on the experience of AUCG, the programme will maintain a partnership with NORCAP, a global provider of expertise to the humanitarian, development and peace-building sectors, operated by the Norwegian Refugee Council. Their support in recruitment and deploying secondees to the AUC will be delivered through an accountable grant and they will expand their focus to second experts more widely across the AUC – e.g. into departments and specialised agencies working on climate and nature, economic growth and migration, as well as peace, security and governance. During the implementation period, AUP will coordinate with other donors working with NORCAP (Denmark, Norway, Ireland) to identify the most effective coordination mechanism for seconding technical expertise.
Funding specialist organisations (through grants, contracts, or MOUs) to provide expert advice
1. In year 1, AUP will work with several specialist organisations to provide support to the AUP across the four outcome areas. These are expected to include:
            1. CMI - Martti Ahtisaari Peace Foundation to support the work of the Mediation and Dialogue Division [MDD] through training, accompaniment and logistical support. The partnership with CMI was developed as a pilot in the final 6 months of AUCG to test the space for supporting AUC mediation. While the focus of the pilot was initially on capacity building and logistical support, as a result of our engagement across FCDO and with MDD, the focus pivoted to provide accompaniment to the AU efforts in the Democratic Republic of Congo peace process – providing expert briefings to the mediators, supporting logistics for mediators’ meetings in Lomé and Addis Ababa. This has resulted in further requests for support to the AU’s mediation efforts on regional diplomacy, tying in with the work of the Africa Research Analysts and Central and Southern Africa Department to support the Doha and Washington processes. AUP will continue the partnership with CMI from the beginning of Year 1 building on the support to the DRC peace process and identifying opportunities to provide accompaniment and technical support to other AU mediation efforts.
            2. Berghof Foundation to support knowledge management within the MDD and build the capacity of the AU-established FemWise and WiseYouth mediation networks. This partnership was also developed as a pilot in the final 6 months of AUCG and has shown some promise. However, Berghof Foundation do not have an established relationship with the AU and this has proved a challenge to achieving the initial outputs, therefore the six-month pilot may not be taken forward.
              [note] FemWise and WiseYouth are the AU’s network of African women and youth in conflict prevention and mediation. They function as subsidiary mechanisms of the Panel of the Wise to strengthen women and youth roles in peacebuilding roles through advocacy, capacity‑building, and networking.
            3. A specialist organisation focusing on elections and democracy, to provide technical expertise around these themes to the AU. The AUCG programme has identified the need to focus more on elections where there is a higher risk of conflict, contestation or violence and FCDO has developed an Election Risk Assessment Framework to prioritise higher risk elections in 2026 (including Ethiopia, Somalia, South Sudan, CAR and Guinea Conakry).
            4. The African Facility for Inclusive Transitions [AFSIT] to support engagement with transition authorities in states that have experienced UCGs. AFSIT is a collaborative initiative by the AUC and UNDP to provide integrated programmatic support to African countries undergoing complex political transitions, including countries experiencing or at risk of UCG.
            5. The Global Green Growth Institute [GGGI] to support the AU’s work on climate finance. GGGI are a key FCDO partner on access to climate finance programming in Uganda, Zambia, Ethiopia and provide the secretariat for FCDO-funded East African Climate Finance Directors Meetings, a regional forum focused on access to finance. This pilot will build on a previous Canadian-funded project with GGGI to support the AU Green Recovery Action Plan [AU-GRAP] in working with seven member states and three RECs to build capacity to secure climate finance from investors. GGGI are the only organisation to have staff members embedded and collocated in the AU-GRAP team. Under AUP, the support to GGGI will continue to focus on enabling the AU to convene and support work on access to climate finance, with an increased focus on fragile and conflict-affected states who face greater barriers to accessing climate finance.
              [note] Closing the Gap: Trends in Adaptation Finance for Fragile and Conflict-affected Settings
2. AUP will work with FCDO and AUC departments to identify opportunities to work with external partners and pilot new initiatives that support economic growth. These will focus on specific policy problems outlined in the strategic case and will focus on areas where the AUC has comparative advantage over RECs and MSs through its convening power and collective voice. It will be important to ensure that these complement existing FCDO programmes on trade and food systems, while not duplicating the existing Africa Regional Trade Integration Programme.
Providing direct financial support to the AUC
1. We do not plan to provide direct financial support to the AUC in the first year of the programme; however, this may change if there is demand from other parts of FCDO to channel funds to AU departments through AUP.
2. Under the AUCG programme, the UK government joined a joint partner JFA MOU in 2024 with the governments of Denmark, Germany, Ireland, the Netherlands, Norway, Sweden and Canada to support the AU Strategic Plan 2024-2028. Within this arrangement, the UK provides Unearmarked Pooled Funds [UPF] to DPAPS. It is also possible to soft-earmark funding to specific departments or projects within this. The experience derived from AUCG (and other past FCDO funding to the Peace and Security JFA through ISF) gives us confidence that this would be an effective mechanism to channel flexible funding to DPAPS and we propose to retain the option of providing funding through this mechanism in future years.
3. There is a separate all-partner JFA MOU to provide UPF to a main fund for allocation anywhere within the AU programme budget. Under the expanded thematic scope of AUP, we will retain the option of providing funding to this UPF and “soft earmarking” the contributions to areas of shared UK-AUC interest (climate and nature, economic growth, and migration).
4. AUP will explore a pilot initiative with the African Migration Observatory [AMO]. AMO is a Specialized Technical Office of the AU established to improve the overall migration governance regime on the continent through better data and knowledge. We will explore whether to provide funding directly to AMO through a bilateral MOU, or if other options, such as securing technical support from a third party or leveraging xHMG expertise would be more appropriate to achieve AUP outcomes.
  [note] About | AMO
Allocation of funding
We do not have a target % of funding to allocate to interventions; rather, allocations will be determined using the criteria outlined and in line with the opportunities presented. We have determined an indicative breakdown of the Year 1 budget in the financial case with the following estimates for allocating funding (see Table 1 below). We do not anticipate providing funding directly to the AUC in Year 1 due to the levels of funding to the DPAPS JFA in the final year of AUCG (see paragraph 68).
Table 1 – Year 1 anticipated allocation of funding
FCDO and HMG expertise	3%
Seconded technical experts	35%
Partnerships with specialist organisations	62%
Direct Financial Support	0%

Value for Money
1. When considering value for money [VFM] within the programme, it is important to note that benefits are expected to follow from the empowerment of the AUC to deliver on its mandate – in the thematic areas of peace, security and governance, climate and nature, economic growth and migration. The ToC seeks to provide a ‘through line’ from investment to outcome, which will enable AUP to assess whether interventions will/have provided VFM.
2. There are some specific considerations for AUP VFM based on lessons from AUCG. Specifically, that the AUCG’s adaptive design and flexible funding mechanisms allowed for responsive programming aligned with AU priorities, while maintaining cost control and ensuring that resources are directed toward high-impact activities. The 2025 annual review noted that the programme risked becoming a “vehicle for funding disparate activities without coherent direction”. Therefore, it recommended that a future programme “should prioritise interventions that deliver measurable impact, reinforce the programme’s theory of change, and contribute to long-term institutional capacity within the AU, thereby ensuring that resources are used efficiently and effectively in pursuit of shared UK-AU priorities.” This lesson has been reflected in the design of the decision-making process outlined in the appraisal case and will be applied across the broader set of outcomes areas in AUP.
  [note] AUCG Annual Review 2024/2025
3. The VFM of AUP will be assessed based on the factors outlined in Table 2. We will look to ensure there are specific value for money metrics easily identifiable in the overarching logframe or results framework, which will provide a way to monitor value for money throughout the life of the programme. At an individual partner level, we will ensure all narrative reporting includes a value for money analysis and include broader qualitative metrics to enable the capturing of unintended effects and added value of their work.
Table 2 – VFM assessment
Economy	The unit costs of technical assistance, in particular consultancy costs and other high-value inputs (including using comparisons across partners). / The unit costs of training and AUC logistics (e.g. flights) / Whether particularly high AUC costs (such as DSAs) can be met from AU budgets, rather than programme funds.
Efficiency:	Flexibility in re-allocating funds where necessary (either because individual grants are not performing or because within those grants, the political and operational context necessitates a change in approach and/or activities). / Flexibility in re-allocating funds across the outcome areas to capitalise on success or respond to new opportunities. / The efficiency (and speed) of issuing grants to partners. / Progress in disbursing budgets, accurate forecasting and ongoing monitoring of financial variance – inc. managing any fluctuations in partner finance across the lifetime of the programme as smoothly as possibly / Ensuring no duplication in relation to other FCDO initiatives delivered with the AU, such as the upcoming Africa Regional Trade Integration Programme. / Ensuring partner staff costs are balanced to ensure efficient delivery.
Effectiveness	Having strong criteria for assessing opportunities / Using a more qualitative approach to MEL, examining both contribution and attribution to outcomes to better determine the reach of the programme. / Achieving individual logframe outcome indicators.
Equity	Using gender disaggregated data on participation in programme activities. / Mainstreaming equity in procurement processes.

## Financial Case

Programme budget and forecast

Table 3 below shows the indicative breakdown between Africa Directorate’s contribution to the programme budget and the remaining £16.3m budget headroom over the course of the lifetime of the programme. We expect use of the headroom to increase in Years 2 and 3 as pilot initiatives help to generate openings and opportunities for more substantial FCDO and HMG engagement.
Table 3
	2026/2027	2027/2028	2028/2029	Total
APEX ODA Allocation	£3.4m	£2.75m	£2.55m	£8.7m
Budget Headroom	£2.3m	£6.55m	£7.45m	£16.3m
Total	£5.7m	£9.3m	£10m	£25m

Note: AUP has received an ODA allocation of £8.7m from APEX, however 15% of the £3.4m allocated for year 1 is at ‘at risk’ and may be redirected to emerging priorities.
1. The indicative budget profile for Year 1 is shown Table 4 below and is affordable within the provisional 2026-2027 ODA allocations provided to APEX’s portfolio. Table 4 shows the predicted breakdown of activities contributing to each outcome in year one. This indicative allocation will be reviewed and confirmed through the finance budget allocations process.
2. We anticipate that the budget breakdown between outcome areas will be very different in Years 2 and 3. During Year 1, the AUP team will design and pilot initiatives in the areas of climate and nature, economic growth, and migration. The success (or otherwise) of the different pilots alongside feedback from the AUC will inform the budgets for Years 2 and 3.
3. In Year 1, we do not anticipate making contributions of funds to the JFA DPAPS. This is due the levels of funding provided to this mechanism during the final year of the AUCG programme. We intend to reassess this in the budgeting process for Year 2 based on the evolution of the programme. We also will maintain the option of using the JFA to channel headroom funding to DAPS, as we have done under AUCG with the UK support to the AU monitoring mission in Tigray.
Table 4 – Year 1 indicative budget from Africa Directorate ODA allocation
Outcome/ Intervention	FCDO and HMG expertise	Seconded technical experts	Partnerships with specialist organisations	Direct financial support	Totals
Peace, Security and Governance	£ 0	£ 550,000	£ 1,400,000	£ 0	£1,950,000
Climate and Nature	£ 100,000	£ 250,000	£ 500,000	£ 0	£ 850,000
Economic Growth	£ 0	£ 200,000	£ 100,000	£ 0	£ 300,000
Migration	£ 0	£ 200,000	£ 100,000	£ 0	£ 300,000
Totals	£ 100,000	£ 1,200,000	£ 2,100,000	£ 0	£3,400,000

The budgeting has drawn on the lessons from AUCG implementation. A key lesson from AUCG was the complexity of aligning workplans with the AUC and the likelihood of delays to AU-led activities, which led to underspending against budget projections and the necessity of a no-cost extension to the programme.
All APEX funding will be ODA-eligible. This funding will come from programme resources (RDEL). There is no capital funding (CDEL) in this programme.
Expenditure Monitoring, Reporting and Accounting
1. Annual activity workplans and budgets will be approved by the SRO through the programme’s governance structures. A quarterly reporting cycle will be adopted with partners through their respective MOUs or grant agreements, detailing process on programme implementation, expenditure and forecasting. These will be reviewed and approved by the programme team and used to assess the component’s contribution and progress in achieving individual component logframe milestones and targets, as well as the overarching programme objectives.
2. A critical challenge remains the ability to spend allocated budget within a complex political economy, like the AUC’s, where priorities are often in flux. Therefore, the programme team will work closely with partners to update financial forecasting on a regular basis and look to spot underspends early and reallocate across the programme. To strengthen forecast accuracy, AUP will apply risk-adjusted updates to partner forecasts based on the latest delivery data and workplans, with assumptions reconciled against partner reporting and updated as needed.
3. Arrangements for direct contributions to the AUC, e.g., through the JFA, will be different. On the JFA, the all-partner MOU commits DPAPS to providing quarterly financial statements, an annual narrative report no more than three months after the end of the calendar year, an independent audit of the fund completed no more than six months after the end of the calendar year, and regular review meetings with partners.
4. If the UK agrees a multi-donor framework with NORCAP to provide secondees to AUC, new reporting frameworks will need to be negotiated between the donor group. The UK will have a lead role in these negotiations to ensure they meet our Programme Operating Framework rules.
5. As above, robust monitoring of spend will be put in place to ensure that sector input codes are being adhered to, across conflict, governance and women and girls, climate change, migration, economic growth. This will be resource intensive and will require quality financial reporting from the implementing partners.
Flow of Funds
1. Downstream partners will be assessed through proposals and due diligence measures will provide assurance on financial management capabilities. If organisations currently funded under AUCG are successful we will ensure any lessons learned on financial management are acted on. We will look at any identified financial and fraud risks with these organisations and track progress on due diligence assessment recommendations.
2. Funds will be disbursed to accountable partners in Pound Sterling following receipt of financial reports. Funds will be disbursed to the JFA under the terms of the MOU.
Does the project involve financial aid to governments?
This programme will not provide any funding to country governments. All funding will be channelled to third party implementing partners through accountable grants, commercial contracts, or memorandums of understanding, or will be provided to the AUC using a memorandum of understanding.
What is the assessment of fiduciary risk, fraud and foreign exchange risk?
1. The overall financial and fraud programme risk is moderate. There are considerable delivery and absorption risks with the support with the allocated funding that is channelled through third-party implementing partners and not given directly to the AUC. Future direct support to AUC also present financial risks.
2. Moreover, the context in which suppliers will operate is complex, with difficulty assessing value for money, potential delays in reporting, the need to pivot funding to similar but different activities where necessary and, relatedly, the need to agree activities with the AUC in advance. We would mitigate this risk by including regular field visits to partners to assess their financial processes, bringing finance colleagues with us as needed to ensure we are using our financial expertise to assist our partners.
3. However, it should be noted that the programme will work with a limited number of partners, several of whom are partners from previous programmes, and have a strong track record. FCDO also has experience working with AUC mechanism like the JFAs. Therefore, it is assessed that the moderate risk rating for this programme is justified.
4. Noting the challenging fiduciary environment and challenging context for some of the work the AUP programme partners will operate in, we will conduct a fraud risk assessment once the programme is mobilised. This will involve reviewing partner risk registers, delivery chain mapping, looking at lessons from the previous AUCG programme, reviewing due diligence assessments for partners and meetings with selected programme partners to discuss fraud risk. We will have a clear statement of risk appetite and a process by which to escalate if this is breached.
Grants, contracts, and MOUs will be denominated in GBP so suppliers carry the risk of exchange rate fluctuations. FCDO will work with suppliers to manage long-term variations on the value of sterling, through for example, modifying some of the deliverables or seeking greater VFM savings.

## Management Case

Governance and programme management arrangements
1. The Africa Programmes and Expertise (APEX) Department will hold the budget for the programme and be accountable to the Africa Director for its delivery. This is subject to change as FCDO is going through restructuring as part of FCDO2030.
2. AUP will require the in-house capability to deliver a complex, flexible and opportunistic programme. The programme will seek to draw on expertise from within the FCDO, particularly from the Communities of Expertise and Research Analysts, as well as from colleagues at posts and staff in other government departments. However, delivering results will require a strong core team that can build relationships with the AUC, identify opportunities for collaboration, provide expert advice, and, where necessary, bring in and oversee additional support, whether that be FCDO/HMG expertise or expertise from external partners.
3. The programme will be delivered by a core team of staff located at FCDO HQ, alongside the UKOAU. This team will consist of a Grade 7 Senior Responsible Officer [SRO], who will have overall responsibility for programme delivery, alongside a HEO Programme Responsible Officer [PRO], who will ensure the quality of programme management for AUP. They will be supported by a programme-funded advisor who will provide thematic expertise to AUP across the programme’s focus areas (complementing the skills and experience of the SRO) and coordinate wider FCDO/xHMG expertise – the rationale for this is outlined in more detail below. The need for additional programme-funded advisory capacity will be assessed as the programme develops. The core team will also require the involvement of the Development Counsellor in UKOAU to support regular engagement with the AUC and other development partners working with the AU in Addis Ababa.
To ensure coordination between these teams, regular AUP programme team meetings will be convened to ensure that decisions are made in a timely fashion, delivery plans are adhered to, compliance is tracked, and challenges are discussed when they arise.
Programme-funded support
1. AUP is a complex programme that will bring together different approaches to achieve the anticipated outcomes. To deliver results, it will require close and responsive engagement with the AUC, and the ability to respond flexibly to new crises and opportunities across different geographies and thematic areas of intervention. Delivering the programme effectively will require the leveraging of networks across FCDO and wider HMG. We have considered how best to resource this work.
2. The options include:
1. Limited FCDO management team only – This approach does not include programme-funded roles and would involve a two-person team (SRO and PRO) within Africa Directorate delivering the programme. They will be able to draw on support from the wider FCDO (Communities of Practice, Research Analysts, and posts) but will have limited ability to sustain relationships with AUC counterparts, identify opportunities for engagement, provide technical advice, or enable the programme to capitalise on these opportunities. Based on lessons learnt from AUCG (which currently benefits from the support of two advisors, in addition to the SRO and PRO), this option would make it more difficult to deliver the programme effectively. A reduced delivery team would limit the capacity of the programme to capitalise on opportunities to engage with the AU on shared priorities and would restrict FCDO’s capacity to provide technical inputs to the design and leveraging of opportunities created through the programme.
2. External provider to help manage delivery – This option would contract an external provider to support the management of AUP. The external provider (e.g. a consultancy firm) would be engaged to develop relationships with different parts of the AUC and help to design and oversee interventions in shared UK-AU priority areas. An external provider is likely to find it harder than FCDO staff to establish credibility and trust with AUC counterparts and will not be as effective as engaging across the FCDO and HMG. Outsourcing important relationship management and technical oversight responsibilities would also risk important lessons, relationships, and knowledge being lost following programme closure. Using an external provider would be more expensive than using an internal alternative.
3. Programme-funded role – This option would provide a programme-funded role within the AUP team, alongside the SRO and PRO. They would manage technical relationship with parts of the AUC, work with AUC counterparts to identify opportunities for collaboration, provide technical advice to the AUC, and design interventions (linking to other forms of FCDO and HMG support where appropriate). The role is expected to cost ~£100k p/a – this is reflected in the financial case. We anticipate that AUP would recruit a programme-funded advisor role at inception to complement the technical expertise of the core team and enable the development of interventions in new thematic areas. The need for additional programme-funded advisory capacity will be assessed as the programme develops.
1. Overall, we have assessed that the third option represents better value for money than the possible alternatives. This delivers against FCDO’s new modern approach to development by increasing the use of technical expertise to achieve results with less ODA.
2. As the programme will be iterative in terms of its thematic focus, the exact requirements for thematic expertise are to be determined. However, we anticipate the role will focus on the intersections between the different priorities, such as climate-induced insecurity and fragility, conflict- and economic-driven migration, governance challenges driven by socio-economic grievances etc.
3. We have also assessed the option of basing the programme-funded role in Addis Ababa (located within the UKOAU) or in London (in APEX). While the option to base the role in Addis Ababa would increase the direct engagement with the AUC and Addis-based partners, the costs are much higher and not realistic within the scope of the anticipated ODA allocation. Therefore, the role would be based in the UK with sufficient programme-funded budget to travel regularly to Addis Ababa and elsewhere to support programme activities. AUP will work to streamline ways of working with the UKOAU in Addis Ababa and across the wider Africa network. There is the option to expand AUP capability later in the programme with a country-based staff role in the UKOAU in Addis Ababa and we will explore this at point of recruiting a second programme-funded role.
Programme Steering Committee
To ensure effective coordination, AUP will convene a programme-level steering committee on a quarterly basis, bringing together the core APEX team with the UK Ambassador to the AU and wider UKOAU staff, chaired by the SRO. This committee will play a vital role in overseeing programme progress, identifying learning, and reviewing challenges and risks to AUP. The steering committee will ensure that the strategic focus of the programme is maintained in the context of flexible delivery, particularly in considering trade-offs between investing in different AUP outcome areas. To remain agile in responding to the wider Africa context and making connections to the FCDO’s broader partnerships on the continent, representatives of geographic departments within Africa Directorate will also be invited to the programme steering committee. If necessary, the steering committee will be convened on an ad hoc basis to decide on whether to pursue an emerging opportunity with the AU.
Coordination with stakeholders, donors and partners
1. The programme will need to be flexible to manage the budget headroom, requests for support from the AUC and availability of programme funds from xHMG. Interventions may be of very different scales and complexity depending on the number of stakeholders from AUC, FCDO, HMG and external partners. For some interventions, it may be necessary to convene an output-level steering group to ensure that efforts are well-coordinated. The AUP management team will determine whether this is necessary on a case-by-case basis. For some steering groups AUP will chair and engage the UKOAU along with other FCDO departments involved or providing resources. In some cases, it may be more appropriate for another FCDO department to chair the steering group, for example, if the AUC’s role is part of a larger initiative.
2. Coordination with other donors is critical to the success of the programme. The AU Development Counsellor plays an active role in various donor coordination mechanisms for donors supporting the AU – including the JFA Donor Group and NORCAP Donor Group. Consultations with other donors were undertaken as part of the design process for this business case, to identify synergies and avoid duplication. The expectation is that for the DPAPS JFA, development partners will continue to meet, both with and without the AUC, to discuss progress and monitor risk.
  [note] This was highlighted in the AUCG Annual Review 2024/2025.
3. A key lesson from the AUCG programme is that partners can operate in siloes and there is not enough coordination – between partners and secondees, between donors. This will become more important with the expanded thematic scope, and the programme will identify opportunities to bring partners together – e.g. in the AUCG programme there is a joint workplan for partners working with the MDD. AUP will also coordinate with other UK programmes working with the AU on trade, cyber and health through the UKOAU. Furthermore, the programme will bring together partners to identify how their engagements with the AUC intersect. For example, AUP could bring together partners working on election monitoring with partners working on preventing UCGs to share experiences. This will help to ensure implementation is not siloed.
4. AUP will seek opportunities to collaborate with other development partners to work on shared priorities with the AU, e.g. identifying areas where funds can be pooled to contribute to AUP outcomes.
Monitoring, Evaluation and Learning
Monitoring and learning objectives for AUP will be to:
  1. track whether programme activities and outputs are being delivered as intended;
  2. assess whether these activities and outputs are contributing to tangible changes in shared UK-AU priority areas,
  3. monitor and analyse how the programme is being delivered, and;
  4. support programme learning and adaptation.
1. The overall monitoring strategy is to build on and strengthen existing partner monitoring and results systems. FCDO MEL advisory support may be used to map monitoring systems and capabilities for each partner and make recommendations for improving them. AUP and partners may also have access to MEL technical assistance through FCDO-funded independent monitoring contracts and will draw on these where possible. Duplication of donor reporting will be avoided and coordination and information sharing supported.
2. An overarching programme logframe, aligned with the ToC, will be used to track results against outputs, outcomes and impact. This will be developed within the first six months of implementation, alongside a programme monitoring and learning plan. The logframe will consolidate individual partner results frameworks. With a wide range of implementation approaches and partners, these may be logframes or alternatives.
3. Given the programme’s focus on institutional capacity, policy influence and political engagement, monitoring and results will prioritise qualitative and contribution-based approaches, complemented by quantitative indicators principally at output level and for tracking VfM.
4. Regular narrative and results reporting from partners will be supplemented with scheduled partner visits and spot checks by the FCDO AUP programme team (or in the case of initiatives funded outside of APEX budgets, by the relevant spending unit team. Monitoring visits will verify reported results, assess implementation quality, and review financial controls and safeguarding practices. Integration of gender and social inclusion will also be monitored.
5. Evidence from monitoring will be used to adapt the programme, principally through learning and reflection workshops. Given the need for the programme to be responsive and agile in leveraging opportunities to achieve the outcomes, AUP will closely monitor how the programme is being delivered – i.e. assessing whether different combinations of interventions show potential to deliver results. This learning loop will guide the adaptation of the programme. Synthesis of monitoring insights into learning notes or short briefs for the management team will further support programme adjustments. Particular attention will be paid to innovative mechanisms and initiatives and new thematic areas such as migration, assessing the extent to which these have potential for continuation and scale-up. There is a particular lack of robust evidence on the extent of uptake and use of technical expertise provided by secondees. This will be captured through working with NORCAP (or other secondee management organisations) to obtain mid- and end of assignment reflections from secondees and receiving departments.
6. There are no plans for a programme-level evaluation but AUP may be included in a future portfolio evaluation.
7. As above, spend against input sector codes (conflict, governance, climate change, economic development and migration) will be monitored closely to ensure internal spending compliance.
Assessment of Risk
1. The overall risk for the programme is assessed as moderate. The AUC, while showing clear ability to deliver against its priorities, continues to experience challenging operational issues, in terms of its technical and professional capacity and the overall political space it has in which to act: the AU is only as powerful as its Member States allow it to be. Therefore, a significant risk for this programme is that impact will not be sustained beyond the project lifetime. AUP’s flexible approach to working with the complex political economy and ongoing reforms process of the AU will help mitigate this risk. AUP acknowledges that the reforms process is beyond the programme’s sphere of control, but we will monitor developments (such as particular AUC directives) and work with partners and AUC staff to identify opportunities to push towards the programme outcomes in such an evolving context.
2. Robust due diligence procedures, recommendation tracking, and close management of implementing partners, as well as programme flexibility, will be used to mitigate risks associated with the operating environment. Recommendations from due diligence assessments, annual reviews and relevant recommendations in the AUCG PCR will be monitored in the annual review and followed up on in 6-monthly programme portfolio discussions.
3. The programme team will develop and hold a central risk register containing risks, appetites and mitigations which will be reviewed and challenged monthly by the programme team and SRO. The SRO will escalate any risks that are likely to exceed programme or APEX level appetite to seniors, including the Head of Group, Head of Department, Directors and Post as relevant.
4. FCDO will fully brief partners on safeguarding standards and ensure they apply robust safeguards and reporting measures throughout their processes. Safeguarding spot checks will form part of all field visits with partners. Poor safeguards within the AUC could lead to negative social or environmental impacts in programmes supported by FCDO-funded technical assistance. Regular meetings with AUC officials and NORCAP secondees mitigate this risk to an acceptable level. The AUCG programme was successful in advocating for robust clauses on safeguarding to be included in the multi-partner MOU with the AUC for the DPAPS JFA. Should any proposed DDA for making direct financial contributions to the AUC (e.g. JFA MAIN) not fall within risk appetite, then we will not fund it.
5. Below is a summary of the key programme risks and proposed mitigating actions.
Table 5 – risk register

	Gross Risk				Residual Risk
Risk/Risk Category	Likelihood	Impact	Rating	Mitigating action	Likelihood	Impact	Rating
Policy & Programme Delivery Risk
The wider thematic scope of the programme leads to coordination challenges within FCDO and stretches UKOAU resources too thinly.	Highly likely	Moderate	Major	Programme funded positions within the programme team can manage coordination xFCDO and provide support to the UKOAU team to engage.	Likely	Moderate	Moderate
AUP is not able to diversify beyond focusing on peace and governance and does not reflect wider mutual priorities of UK and AU	Likely	Moderate	Moderate	AUP will pilot initiatives across the outcome areas in year 1 and assess where there are opportunities for further development in Years 2 and 3. / AUP will draw on the UKOAU to develop/build on relationships across the AUC. / The AUP Steering Committee will be able to challenge the programme on thematic focus in its decision making.	Possible	Moderate	Moderate
Limited or no funding becomes available to fill the budget headroom, which means funds are spread too thinly to deliver significant impact and AUP disappoints expectations of the AUC around levels of UK support	Likely	Major	Major	Programme team to create awareness xHMG on AUP and advocate for potential buy-in. / Manage AUC expectations through clear communication on funding availability and transparency around AUP decision making. Theory of change is designed to be realistic about programme impacts relative to scale of funding	Possible	Moderate	Moderate
Implementing partners do not have the capacity for effective activity monitoring leading to lack of proper reporting of outputs/outcomes	Likely	Moderate	Moderate	FCDO requires quarterly monitoring of partner budgets and regular partner meetings. We work with partners on generating comms products and have clear agreed logframe indicators. We scrutinise budgets to look at the internal capacity for M&E.	Possible	Minor	Minor
Technical assistance provided through FCDO-funded secondments can be seen as capacity substitution rather than building the capacity of the AUC. Technical expertise and knowledge may not be absorbed into the AUC itself, limiting sustainability after the secondment ends.	Highly likely	Major	Major	Assess secondments on whether they could be supported more appropriately by AUC budgets / Strengthen outcome-level reporting by NORCAP. / Engage more directly with secondees and the AUC officials they are supporting to assess successes, challenges and role in future strategy. / Clear ToRs for the secondees detailing clear inputs/outputs and expected results and clear reporting requirements.	Likely	Major	Major
Poor financial controls by third party organisations leading to fraudulent claims through consultant costs billed incorrectly or inflated costs, meaning FCDO is paying for incorrect invoiced amounts.	Likely	Major	Major	FCDO checks partner financial controls and conducts DDAs on all third-party delivery suppliers. All recommendations for any changes to their policies logged and tracked on the delivery plan. / MOUs/accountable grants structured so that liability for loss of funds sits with supplier, not FCDO. / Conducts regular fraud discussions with partners, field visits to check financial systems/conduct spot checks on assets. Interrogate partner financial reporting and benchmark consultant costs to ensure VFM.	Possible	Moderate	Moderate
Strategy & Context Risk
The changing political will of Member States (through, for example, changes of government, domestic priorities and shifting regional alliances) means the AUC lacks clarity on a long-term programme of work and is overly reactive.	Highly Likely	Major	Major	Development Counsellor based in Addis continually monitors the AUC’s technical and political capacity to affect change, combining insights from implementing partners and the work of the UKOAU / UKOAU Ambassador supports this through high level connections with commissioners and wider network, to ensure early notification of changing political will and priorities. / Flexible approach ready to pivot when there are opportunities to respond to.	Likely	Major	Major
Lack of AUC funding for new staff leads to AUC's existing staff to be stretched. Existing staff are unable to dedicate the time to engage with those deployed under this programme. This could affect the effective absorption of TA supplied by the programme.	Likely	Major	Major	FCDO tolerates this risk and will monitor through SRO/Development Counsellor assessment of AU’s technical/political capacity to affect change to ensure programme outputs remain appropriate. / Discussions with AUC on funding staff through JFA as recruitment freeze is lifted.	Likely	Major	Major
Safeguarding Risk
There is a lack of evidence provided on the AUC implementing their agreed safeguarding policies. This could hide a mismanagement of SEAH cases within AUC departments. FCDO has a zero tolerance approach to SEAH and so needs to ensure it is managed by partners.	Likely	Major	Major	Programme team undertake mandatory safeguarding training/include safeguarding spot checks in all field visits with partners. / Continue to advocate for safeguarding language in multi-donor agreements / Capture how AUC depts manage and escalate safeguarding risks; this is a priority of the Development Counsellor in JFA discussions. / FCDO transfers risk to third parties providing TA – inc. thorough DDA to ensure safeguards are in place; clear risk mitigations (safeguarding SOPs, confidential reporting systems) in TA risk registers.	Possible	Major	Moderate
Reputational Risk
Most of the programme funding is channelled through third party implementing partners and not given directly to the AUC – risks being seen as working in parallel to AUC systems and processes and supporting organisations that the AU want to work with, rather than supporting the AU directly.	Likely	Moderate	Moderate	SRO and Development Counsellor hold regular discussions with the AUC to identify priority areas for support/engagement. / Development Counsellor will engage in AU budget consultation meetings to ensure complementarity with AU plans. / Direct contributions to the JFAs enable AUC to allocate funding to areas of need.	Possible	Moderate	Moderate