BUSINESS CASE ADDENDUM

PROGRAMME TITLE	UK Regional Support to the most vulnerable Palestinians from Gaza and the West Bank (UKRSP)
Directorate/ Post	MENAD Directorate – British Embassy Amman	Contact name	Sophie Oliveau-Morel
Original programme budget	£5m	Country or region targeted	Palestine
Cost extension value (if applicable)	£15m (£5.2m secured from the crisis reserve bid but not yet allocated, £3.5m resourced at risk and allocated leaving the remaining £11.3m with no funding source yet).	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	HMA Amman, Philip Hall
New increased or reduced programme budget (if applicable)	£20m	Original programme start and end dates	23/07/2025-23/07/2028
Latest AR programme score	N/A	New programme end date (if applicable)	N/A
		Programme ID	400733

Detailed information
Programme summary	The “UK Regional Support to the most vulnerable Palestinians from Gaza and the West Bank” programme is designed to flexibly respond to urgent humanitarian needs arising. The programme aims to save lives, reduce suffering and improve resilience during the current crisis and prevent a further deterioration of the humanitarian situation until a more durable political solution is reached. While reaffirming HMG’s ongoing support to Palestinians and to neighbouring host countries, and in conjunction with the Palestine bilateral programme (which focuses specifically on Palestinians in Palestine), it will provide humanitarian assistance to Palestinians in Gaza and the West Bank, as well as support for those displaced to neighbouring countries. / This programme has been directly responding to ministerial priorities. So far, through this programme, £500k has already been spent participating in the Jordanian-led air drops to Gaza through the MoU signed with the Jordanian Hashemite Charity Organisation. This was approved by 2PUS on 28th July agreeing to having UK-funded aid placed onto Jordanian aircrafts and airdropped into Gaza. £1m was approved by the Middle East and North Africa Director on 23rd June to support Egypt’s health care system in providing healthcare services for the medical evacuees through the WHO. £2m has been earmarked for medical evacuations from Gaza to the UK via Jordan with some of those funds having already been spent.
Changes	This UKRSP BC was approved by BE Amman HMA on 23rd July 2025. On 25th July 2025, the Prime Minister announced that the UK would medically evacuate Gazan children for treatment in the UK. This support came as the appalling humanitarian situation continued to leave many in urgent need of medical care. Most hospitals in Gaza are no longer functioning, essential medicines and supplies are running out and the operating environment is insecure. / This is the second amendment to the programme. This time we are seeking an additional £15m to the programme as the situation on the ground rapidly continues to change and develop opportunities to support Palestinians through regional initiatives increase. Baroness Chapman agreed to re-allocate £5.2m from the Crisis Reserve Fund to this programme on the 27th August 2025, meaning that the Business Case requires a minimum headroom of just over £10m. We are asking to raise the headroom to £20m (this is also in line with amounts set out in the current delegated authority guidance) so that we have the possibility (but not the obligation) to be involved in regional initiatives in the future should further funding become available. / The first amendment to the programme was as a direct response to the approval received from 2PUS to fund medical evacuations for a first stage for up to 50 patients and their families/support from Gaza to the UK via Jordan. There we explicitly expanded the scope of the BC, to ensure that the BC covers medical evacuations, and all expenses related to that, through and to Jordan, Egypt and further afield. This change ensured that the approved medical evacuations to the UK would be covered under the scope of the programme. / This change is not material, will not cause the programme to deviate in any way from the original BC and will not require adjustments to the theory of change.
Implementation	The implementation of the programme will remain the same. Posts in the region will continue to explore options for implementing partners. Additional services and associated costs may be delivered through the team in BE Amman engaging commercial partners, e.g. Royal Jordanian for chartered flights.
Budget	The original budget was £5m. Around £3.7m has already either been spent or earmarked, however, an additional £5m has been announced. In order to increase the headroom over the life cycle of the programme we are looking to raise the initial amount by £15m to a revised total of £20m in case Ministers express a desire to get involve in more initiatives. / As ODA allocations for 26-27,27-28 and 28-29 are not yet confirmed and this was not included in MENA’s ODA return, we will, once allocations are confirmed, identify funding choices of £11.3m within MENA, offering other activities/projects that could be cut and present these choices to Ministers.
Impact	Impact of cost/time extensions on VfM (check relevant box): / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the cost/time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Risk	The overall risk of the programme has been set and will remain as Severe. / Potential risks that could arise without an increase to the budget is the UK not being able to meet ministerial asks and the UK not being seen as a major player in the humanitarian work. / There are risks to not spending the allocated budget due to a change in the situation on the ground impacting accessibility. / Any new risks that arise directly from activities which are being carried out from this programme will be included in the programme’s risk register. This will include the possibility of not being allocated additional funds as well as the continually changing circumstances in the region.
Results/Monitoring and Evaluation	It is not yet clear what regional initiatives the UK may fund going forward as this is dependent on further funding being identified. A pipeline for the funding from the crisis reserve is in place. Results and output indicators to cover existing activities are in place and are being developed for activities to be funded under the crisis reserve. Any further activities identified under any uplift will be included in the log frame and measured and monitored accordingly. / This change is not material, will not cause the programme to deviate in any way from the original BC and will not require adjustments to the theory of change.