Business Case

Summary Sheet

Country Business Plan Summary: / The SDF3 Business Case directly supports the 25/26 Somalia Country Business Plan by delivering progress on climate-resilient economic development and governance reform in Somaliland which are two areas identified as strategically important for UK interests. SDF3 offers a strategic transition which maintains UK influence in critical development areas (economy, climate) while engaging with emerging priorities. Specifically, it aligns with CBP goals on climate and nature, migration, and humanitarian and development by fulfilling existing commitments under SDF2, while piloting reforms that will inform future programming. It maintains UK influence, including with the Somaliland government and key international partners, supports localisation, and tests the feasibility of a Presidential Delivery Unit, so contributing to long-term resilience and inclusive growth in line with the CBP’s shift away from direct service delivery. While the risk rating is high given the context, we judge this is manageable given an established delivery mechanism and partners.

Title: / Somaliland Development Fund 3 (SDF3)
Programme summary (100 words maximum): / The Somaliland Development Fund (SDF3) (<£5M in 25/26) will build on interventions initiated under SDF2, ensuring continuity and delivery of planned outcomes while maintaining UK visibility and strategic influence. The programme retains flexibility to operate in strategic sectors such as climate-smart agriculture, the blue economy, and renewable energy – all areas critical to Somaliland’s long-term resilience and inclusive growth. / SDF3 will also test small-scale governance reform pilots, embedding technical adviser (s) within targeted Somaliland institutions to trial innovative approaches to green economic policymaking. By working directly with communities, the programme will also strengthen citizen-state accountability. This dual approach will help build climate resilience and improve livelihoods across both rural and urban areas, while informing the design of the future Somaliland portfolio.
What is the rationale for UK Aid spending? (200 words maximum): / This programme will directly deliver against HMG and the Foreign Secretary’s priorities on growth through increasing incomes and job creation; climate through supporting green sectors and climate policy reform; and development partnerships by working in tandem with the government. These in turn will help reduce conflict and other drivers of illegal migration. / Somaliland stands at a critical juncture. The political settlement is fragile and mistrust in authorities is rising. Poverty, inequality and unemployment remain high, and the economy, focused on livestock and remittances, remains weak[1] climate events are increasing￼, particularly [2]girls.￼ Somaliland’s resources to build climate-resilient services and infrastructure, and spearhead growth through sound economic policies, are scarce. / Following democratic elections in November 2024, there is a window of opportunity for the UK to drive a more effective social contract and improve sustainability through green growth initiatives with the Somaliland authorities. / As the only permanent Western mission in Hargeisa and the co-lead on donor coordination, the UK is uniquely placed to deliver this programme under overall Danish leadership, having exceptional relationships with the authorities, a thorough understanding of the complex context and trust with key stakeholders in civil society, private sector and the international community.
Programme Value: Up to £5m		Country/ Region or Sector: / Somalia – specifically Somaliland
Country Office confirmation of review processes		Charles King (HMA Mogadishu), 31/07/2025
Contact name		Tatiana Fernandes (Development Counsellor British Office Hargeisa)
Threshold for final approval of Business Case: Ambassador – Charles King
Date of Approval of Concept Note:	21/07/2025	Name and role of Approver / Christopher Pycroft, Development Director
Date of Approval of Business Case:	dd/mm/yyyy / 01/09/2025	Name and role of Approver / HMA
Programme Code:	AMP Start Date: / 01/08/2025	AMP End Date: / 31/03/2026
Overall programme risk rating:	Major
[1] World Meteorological Organization, see map projecting change in weather patterns in Africa demonstrating significantly higher/ lower precipitation across Somaliland’s West and East.
[2] Ranked 178 out of 185 countries & territories on the impacts of climate change ND-GAIN Index (2024).

Strategic Case

Why UK intervention is needed
1. Somaliland, a former British protectorate, is a self-governing but unrecognised territory, declaring independence from Somalia after the 1991 civil war. Since then, Somaliland has functioned with de facto independence and is governed by a democratically elected government. Despite this, politics remains identity based, and Somaliland has low institutional capacity and limited state budget.
2. There is limited access to finance from multilateral development banks (MDBs), other donors and international climate finance organisations that directly address Somaliland’s economic growth and climate resilience needs in a bespoke and targeted manner – in part due to Somaliland’s unresolved status. Not addressing the lack of services and infrastructure increases the likelihood of communities remaining in a recurrent cycle of poverty. Poverty is further exacerbated by increasing risks of climate shocks and a lack of government ability to respond effectively.
3. The Somaliland Development Fund (SDF) has been operating since 2012. Originally led by the UK and supported by three Nordic donors (Denmark, Norway, Netherlands), the SDF was set up as a post-conflict, economic recovery programme building government capacity and infrastructure. Under SDF2 from 2018-25 (£62m, £25m of which is UK funding), the programme connected 286,000 urban citizens to potable water; rehabilitated 132km of roads reducing travel time between two major trade hubs by 40%; and irrigated 400ha of land tripling fodder production for food security. It is highly valued by the Somaliland authorities as one of its few genuine development partnerships that supports state delivery and accountability.
4. This business case is for a single-year transition to the new portfolio approach, building on the agreed concept note which continues to align with Government of Somaliland (GoSL) strategic objectives and directly contributes to the Foreign Secretary’s priorities on growth, climate, and migration. The components of this programme will directly shape the future Somaliland portfolio which will aim to build on Somaliland’s long-term resilience and development, while maintaining the UK’s status as a trusted development partner and influential political actor.
5. For 2025/26, the UK will maintain a modest contribution to the third phase, multi-donor Somaliland Development Fund, now led by Denmark. This will allow the UK to maintain influence over critical infrastructure development decisions taken by the Joint Steering Committee, chaired by the Ministry of Planning and National Development, Ministry of Finance and development partners (currently Denmark, Norway, Netherlands – with scope for more donors to join). This ensures that the UK can maintain oversight over the SDF’s investments and steer greater ownership and accountability to the government. The future Somaliland Portfolio will build on this. A small envelope will be earmarked under the SDF to support the development of a Presidential Delivery Unit which will seek to catalyse investment and development objectives. This component will act as a proof of concept for policy reform required to unlock the full potential of development investments, while gathering evidence to help inform governance recommendations needed to underpin the future portfolio. Denmark will manage both components, with the UK expected to lead design of the reform components via FCDO technical advice.
How the programme fits with Foreign Secretary priorities and country plan
1. This programme supports Somalia Network’s Country Business Plan for 2025/2026. Somaliland’s institutions lack systemic resilience. Somaliland cannot absorb shocks, adapt and transform. Strategic interests on security, migration and climate are undermined if this core fragility is not addressed through development. This programme directly delivers under country plan goals 2 (Climate & Nature), and 4 (Humanitarian and Development). Impacts will indirectly benefit country plan goal 3 (Migration).
2. This programme supports the Foreign Secretary’s priorities on growth through climate-resilient infrastructure and job creation in sectors like agriculture, energy and fisheries. It addresses migration by improving livelihoods and services for vulnerable groups, including internally displaced peoples reducing drivers of migration. The programme advances climate and nature goals by investing in renewable energy, sustainable water management, and locally owned climate policy reform. It strengthens development through partnership with Somaliland authorities, enhancing accountability and long-term resilience.

Intended impact and outcome for beneficiaries
1. The programme’s impact statement is: The Somaliland authorities are providing an enabling environment which delivers growth that is: environmentally sustainable; inclusive; resilient to economic, conflict, climate and environmental shocks; and informed by the priorities all their citizens.
2. The outcome statement is three-fold:
1. First, evidence of projects delivering climate resilient and inclusive growth: Investments are made which address binding constraints to economic development e.g. reduce cost of energy, improve water access and deliver resilient jobs/ livelihoods in productive sectors, and these have a positive impact on vulnerable populations, including women and other marginalised groups, by increasing incomes and access to services.
2. Second, Somaliland authorities’ decision-making processes improve: More transparent, accountable and evidence-based decisions are made on policy and institutional and regulatory reform, which considers issues of inclusion, climate, resilience, conflict, and environment.
3. Third, Transformational Change – as Somaliland authorities see benefits (growth, investment, support from citizens, future opportunities for revenue etc.) and understand what and how they should prioritise to continue seeing these benefits, they are more inclined to deliver improved policy. Somaliland authorities also increase and improve the use of own resources to pursue sustainable, inclusive and resilient growth. This leads to systems wide change in the behaviour of government more broadly, which perpetuates more growth.

What the programme will deliver
1. UK funding will be delivered through two components:
  1. Investments for green infrastructure and food systems (<£3m) – informed by political economy and conflict analysis.
  2. Technical Advisory Facility (<£1m). Testing proof of concept for future Somaliland portfolio.

Component 1: Contribution to the refreshed, multi-donor Somaliland Development Fund 3 (GBP 3M, CDEL), now led by Denmark. The programme takes the best aspects of the past phases – supporting government’s ability to deliver basic services – and adds a more strategic, evidence-based lens, and prioritises climate resilience. We will programme for £3m. 100% of this will contribute to International Climate Fund (ICF). Exact interventions will be scoped in partnership with the Somaliland authorities and other development partners. The following activities have been pre-identified as within scope of the Danish-led Fund. Activities which cannot be completed this year will likely be re-evaluated and re-scoped under the future Somaliland portfolio:
1. Climate-smart agriculture and food security: Build four water dams (~200,000m3 water/ year) providing water for 150,000 livestock, increasing prosperity and drought resilience. Conserving 10,000 ha land through irrigation for grain production, supporting food security.
2. Blue economy: Improve fish stock management and sustainable supply chains, benefitting ~200,000 people in Somaliland’s coastal communities.
3. Sustainable water management: Increase access to potable water for ~750,000 citizens, including Internally Displaced Persons.
4. Renewable energy: Lower price of energy, reduce reliance on fuel and increase production and jobs through new solar grids and battery storage.

Component 2: Technical Advisory Facility (GBP 1M, RDEL) will be led by the Danish in collaboration with the Somaliland authorities. This will support related economic reform and coordination with the donors and investment community (including UK diaspora). This aims to address shortcomings identified during SDF2, ensuring SDF3 interventions have a more long-term, transformative impact across Somaliland rather than in their isolated areas. We will programme £1m for conducting activities including a workshop in which all the key stakeholders will participate to test for the modality, design and functionality of the technical facility stationed at the presidency office. Exact workstreams will be scoped at inception stage but will likely include:
Technical assistance workshop for Delivery Unit design: contracting external delivery unit expertise to support critical design, governance modalities, and early prioritisation of key workstreams while seeking early-buy in from across Somaliland Ministries.
Climate and environment policy to influence future investments: The future Somaliland portfolio will seek to explore a variety of reforms required to catalyse transformational change, however given the limited time to test the concept, the focus this year will be on one or two key economic or climatic reforms identified under SDF1 and SDF2 required to drive and sustain existing investments. This work will set a strategy that guides investors (government, donors or private sector) on responding to Somaliland’s climate and environment risks – testing the functionality of an embedded, issue-specific technical advisor to quickly drive structural reforms.

What are others doing?
1. Denmark, Norway and the Netherlands are active donors or ‘friends’ of the SDF, working in close coordination with the Ministry of Planning and National Development and Minister of Finance on selected projects.
2. Sweden is providing support through the Berbera Corridor, supplementing work completed under SDF1 and SDF2.
3. The new (2025) UK-funded Green Urban Growth (GUG) programme, renamed Sinaan, is working in two cities in Somaliland – Toj Wajaale and Burao – with some targeted work proposed in Hargeisa. GUG will be working directly with local government, building on SDF2 investments e.g. on water in Hargeisa and initial infrastructure work in Burao, contributing to wider economic development and climate goals. Sinaan will reinforce the climate aims of SDF, developing investment pipelines for cities in Somaliland that can leverage SDF investments, potentially also picking up projects identified by the SDF and supporting mobilisation of finance for these from the private sector and impact investors. There will be close coordination and evidence transfer between Sinaan and SDF3. Sinaan’s SRO is also part of the SDF3 core advisory team, and vice versa.
4. The World Bank (WB) has a number of interventions across infrastructure sectors in Somaliland. The two key sectors they are working in are urban infrastructure and energy. Through the World Bank’s Somalia Urban Resilience Programme II (SURP), a new agreement has been signed to extend the programme to Hargeisa with initial flood risk assessment work already underway for the city. There will be close working between the Sinaan programme and the WB’s new interventions in Hargeisa and given the focus of SURP on infrastructure a strong link to SDF 3.
5. Energy sector reforms are currently being supported through the World Bank’s Energy Sector Recovery programme, these reforms focus on improving the overall functioning of the energy market in Somaliland working in a select set of cities – including Hargeisa and Berbera – to consolidate energy sector providers into single energy suppliers.
Transition to future portfolio
1. The UK is recalibrating its approach in Somaliland to draw the state away from aid dependency and strengthen resilience. SDF3 offers a strategic transition which maintains UK influence in critical development areas (economy, climate) while aligning with emerging priorities. UK contribution to the Danish-led SDF bridges past investments with future ambitions, fulfilling concepts designed under SDF2 while laying the groundwork for the future portfolio particularly on economic governance reform. This investment enables the UK to remain engaged in key sectors such as climate-smart agriculture, water access, renewable energy, and the blue economy without reverting to large-scale service delivery.
2. Crucially, SDF3 will act as a testbed for governance innovation, by embedding technical advisers within Somaliland MDAs to pilot reforms that promote inclusive and accountable systems. These reforms will focus primarily on critical issues which are hindering the full potential of SDF1 and SDF2 investments (led by the UK). This pilot will generate practical insights into how governance can be strengthened in ways that avoid reinforcing elite structures, an issue highlighted in the SDF2 Programme Closure Report.
3. SDF3 and the well-established Joint Steering Committee offers a low-risk environment to explore how a potential Presidential Delivery Unit could drive cross-government coordination, improve service delivery, and embed climate and economic priorities into decision-making.
4. By operating in high-potential regions and leveraging partnerships with local actors, SDF3 supports the UK’s shift toward a more transformative, system-oriented portfolio which helps support Somaliland’s development trajectory away from international development assistance.

Appraisal Case

Theory of Change
1. The hypothesis underpinning the SDF 3 Theory of Change is that IF the capacity of the Somaliland authority to develop policy, absorb evidence and deliver investments is strengthened AND the Somaliland authorities see benefits and absorb evidence of SDF supported investments and approaches (inclusive and sustainable growth, investment, support from citizens, future opportunities for revenue etc.) and understand what and how they should prioritise the use of their scarce resources to continue seeing these benefits, THEN they are more able and inclined to deliver improved policy. This will lead to systems wide change in the behaviour of the state more broadly (as long as awareness can be raised across Somaliland authorities around the successes and benefits of these approaches), which perpetuate more growth.[3]
  [3] As per the ICF methodology note previously cited, SDF might look for evidence that there is political will and local ownership, capacity and capability within government, increased innovation, evidence of effectiveness shared, replicability and sustainability, to ensure transformational change is achieved.
2. The expected impact is that the Somaliland authorities are providing an enabling environment which delivers growth that is: environmentally sustainable; inclusive; resilient to economic, conflict, climate and environmental shocks; and informed by the priorities of its people.
3. The expected outcome is evidence is produced of projects delivering resilient and inclusive growth that is coupled with improved and more transparent government decision making processes behind investments. This means that investments are made which address binding constraints e.g. around the cost of energy, improving water access, building climate-resilient agricultural practices, which deliver resilient jobs and livelihoods in productive sectors, and increased incomes for vulnerable populations including women and rural communities. Simultaneously, the state makes more transparent, accountable decisions on policy, reform and use of its own resources which consider inclusion, climate, environment, resilience and conflict thereby deepening trust in state decision making and strengthening the social contract.
4. The expected output is delivery of inclusive green infrastructure projects (output 1) in renewable energy and sustainable water management (output 1); support to food systems both for climate-resilient agriculture and the blue economy (output 2); and technical advisers embedded with government ministries facilitating economic and policy reform (output 3).
5. This is achieved through preferred UK inputs: At least 75% ICF CDEL to infrastructure development and food security, 25% RDEL for technical advisers, and in-kind programme support offered on a part-time basis to Denmark to support effective management of the SDF3 according to FCDO due diligence principles.

Figure 1: Theory of Change

Assessment of feasible options
1. To deliver the Theory of Change, we have considered three viable options and the counterfactual. These complement the higher-level options, including commercial delivery options set out in the Concept Note, rather than repeat them as we now have more clarity about needs and context post-elections.
2. Options that we consider in the development of the Business Case are:
1. Do nothing.
2. Provide funding to the SDF3 led by Denmark, which is a continuation of the SDF2 with a stronger climate focus plus embedding a test adviser/s through an Advisory Facility to improve governance and GESI aspects.

By appraising these options, we have considered:
1. Feasibility of delivering the Theory of Change.
2. Evidence of UK development Best Buys; and the
3. Somaliland context including complexity of how transformational change is achieved, learning from previous SDF1 and 2 and other programmes including through the third-party monitoring partner, and viability of delivery partners.
4. Impact of ODA reductions for FY2025/26 and future years.

Option a - do nothing
1. Do nothing and reallocate funds to other programmes or return funds to the centre. This would mean the UK loses the unique opportunity to influence the Somaliland authorities on governance and economic growth priorities directly after the elections and beyond, disempowering a new set of Somaliland authorities. With the UK being by far the second largest donor to the SDF3, Denmark have also signalled that the programme wouldn’t go ahead if we didn’t invest – meaning vulnerable Somalilanders, especially women and girls and rural communities, would lose out on major green infrastructure developments and food security support.
2. Doing nothing would also mean FCDO could not capitalise on the years of lessons learnt and our relationships in Somaliland that SDF1 and 2 have created, not allowing us to be more strategic and intentional in our future investments. Lastly, it would mean we were unable to implement the Foreign Secretary’s priorities on growth, climate and partnerships in Somaliland – and would leave a gap in our Country Business Plan support under our campaign goals on economic growth and governance.
Option b - provide funding to the SDF3 led by Denmark, which is a continuation of SDF2 with a stronger climate focus plus embedding a test adviser/s through an Advisory Facility to improve governance and GESI aspects
Provide funding to the SDF3 led by Denmark, which is a continuation of the SDF2 with a stronger climate focus. The SDF3 objectives are threefold:
1. Increased climate resilience in integrated water resources management and food systems. This refers to Somaliland’s ability to recover from or mitigate vulnerability to climate-related shocks, such as droughts.
2. Increased resilience among women, young people, internally displaced peoples and rural communities through new economic and employment opportunities.
3. Increased opportunities for private investment into green, climate-smart solutions (i.e., technologies, business and production models) through linkages to SDF projects or SDF-supported policy changes.

The Danish-led SDF3 will deliver the programme including the advisory facility through a Fund Manager/ Secretariat, working closely with relevant government departments and communities in which projects take place. Communities are brought in from the start and engaged through various forums throughout project design, to ensure sufficient community buy-in, smooth delivery, and to pre-empt conflict.
Value for Money for preferred option
1. We will continue to apply the same principles of Value for Money (VfM) as defined and developed by Mott throughout SDF2. In addition, we will explicitly draw from the VfM reporting captured under Denmark’s leadership, recognising that the Danes will be the lead implementors and are expected to have their own MEL/VfM contract in place. VfM performance will also be assessed through the Joint Steering Committee (JSC) and the “Friends of SDF” Forum, ensuring robust oversight and continuous improvement. Mott who is leading on SDF3
2. Achieving strong Value for Money (VfM) in SDF3 depends on the effectiveness of the processes and measures established to deliver results and report against VfM framework that states the metrics. To support this, the SDF programme has developed and monitors a comprehensive set of mechanisms that ensure compliance with implementation guidelines, procurement procedures, budgeting, and financial reporting. To enable robust VfM performance assessment, the following guiding principles will be applied:
- Development of VfM toolkits and enablers to support continuous improvement.
- Alignment of projects with NDP2 and the SDF3 Business Case, ensuring that implementation processes incorporate VfM considerations.
- Strong financial and procurement systems that enhance the programme’s ability to manage budgets, forecast expenditures, and improve procurement performance.
- Qualitative analysis for areas where results are difficult to quantify, enabling informed judgments about value.
- Holistic VfM appraisal that considers all aspects of programme delivery.
- Benchmarking of unit costs to closely monitor inputs, outputs, and outcomes.
- Effective use of data to support evidence-based reporting.
Commercial Case
What are the proposed delivery routes and funding instruments for this intervention?
The programme will be delivered through a combination of funding instruments and partners. This Commercial Case addresses how this programme will be delivered in practice. The Appraisal Case above sets out how the two components will deliver the Theory of Change:
  1. Component 1: Delivery of Projects in Green Infrastructure & Food Systems – implementation by Denmark through a Delegated Cooperation Arrangement.
  2. Component 2: Technical Advisory Facility – implementation by Denmark through a Delegated Cooperation Arrangement. There will be flexibility of shifting any underspend money to the infrastructure component. The programme’s funding instruments, rationale and indicative budgets are shown in Table 1 below:
Table 1: Programme funding instruments and rationale
Activity	Components	Type of funding Instrument	Rationale	Value
Green infrastructure and food systems	C1.1 Infrastructure delivery (CDEL)	DCA with the Lead Development Partner (Denmark)	A technically experienced and flexible partner, less transaction costs and better VfM, and UK maintains development leadership.	£3m
Technical Advisory Facility	C2 Advisory Facility and operational support to the fund manager (RDEL)		Provides high quality expertise, encourages flexibility and responsiveness to changing contexts, less prone to be hostage to clan dynamics than NGO.	£1m
				£4

For both components, FCDO will buy into the Phase 3 of the SDF delivered by Denmark. The delivery of those components will draw on lessons from SDF1 and 2, especially on the management and governance mechanisms; FCDO will engage very closely with Denmark on this. Just like in its predecessor programmes, the delivery mechanism for Component 1 and 2 will be via a contract with an expert Fund Manager who will be expected to provide efficient, timely, and transparent management of the components. The fund manager’s responsibilities will include performing a wide range of tasks related to the start-up, implementation, monitoring and evaluation, reporting, and overall administration. Denmark selected the Fund Manager through a joint procurement Official Journal of European Union (OJEU) procurement, with FCDO as a voting member. This process considered the fund manager’s capability and key cost drivers such as security, staff costs and travel.
Contracting and Partner Performance Management
1. Delegated Cooperation Arrangement with Denmark: FCDO has strong assurances that Denmark is able to deliver the SDF3 programme. Denmark is the only other donor partner with a dedicated office in Somaliland and have a suite of successful development programmes they have delivered bilaterally or through multi-donor funds in Somaliland. Beyond the SDF, this includes support to civil society, women and girls, and responsible investment. Denmark also has strong relationships with the Somaliland government. FCDO therefore assess that Denmark is well-placed to build on their strong track record in the region by delivering the SDF3 component.
2. The Delegated Cooperation Arrangement will be developed in parallel to this Business Case and signed off in September 2025 to allow the programme to start inception in October 2025. At a minimum, the agreement will cover the following delivery expectations: Quarterly forecasting; Quarterly Progress Reporting and KPIs; programme monitoring and verification reports; quarterly risk reviews and risk register updates; annual audit reports; results framework and review frequency; asset management provisions; modalities around annual reviews and handling of recommendations; and terms of project closure/ early exit. It will also incorporate some aspects of the governance structure outlined in the management case.
3. On funding modalities, the FCDO programme team will process fund requests by Denmark and will transfer funds directly to Denmark via regular payment in arrears. We envisage to do this quarterly or biannually to minimise resource burden for the FCDO. The fund request from the lead donor will be based upon the budget forecast shared with FCDO quarterly. We expect that the UK will pay based on the GBP forecast and actuals realised in GBP. Any resulting exchange rate issues will be absorbed by Denmark. However, exact handling will be set out in the DCA in coordination with Denmark.
4. The FCDO programme team will agree a performance framework against which the partner will self-assess during the programme year in quarterly intervals and during annual reviews, followed by a joint programme learning event to agree improvements as needed. Quarterly review conversations will include contract performance reporting, and regular ad hoc delivery conversations will take place with the lead donor to allow early identification and decision making on issues and risks given the dynamic delivery environment. The FCDO programme team will oversee any agreements with technical support and advice from a Commercial Lead and Contracts Officer, with additional guidance from the Central Commercial Department as needed.

## D. Financial Case

1. The proposed FCDO budget of £4m with the ability to scale up to a maximum of £5m if budgets allowed for one transitional year, will be spent within the economic development portfolio allocation in the approved Somalia Network’s Country Business Plan.
2. Appropriate review points have built into the programme design to assess relevance, fitness for purpose, and obtain HMT approvals for delivery within the FY25/26 Spending Review. The programme will apply lessons from the 2023 BEM internal audit review and ensure accurate classification and reporting on single CDEL (ICF) and RDEL delivery.
3. The budget will be allocated to the two proposed components which will be both delivered by Denmark through a Delegated Cooperation Arrangement (DCA)as follows:
1. Component 1 - Infrastructure for green growth component: It will be CDEL, of which 100% will be International Climate Funding (ICF). The programme will use part of Denmark’s (total 25m) and other donors’ funds (including FCDO) as RDEL to provide technical assistance to the government and secretariat support.
2. Component 2 - Advisory facility component: This will be delivered through a contribution to the Denmark alongside component 1. It will be 100% RDEL, providing policy advice and support to the government. We will programme £1m from our budget for setting up the unit for piloting a test for the functionality of the technical facility. Exact workstreams will be scoped at inception stage. Funds disbursal, reporting and controls on expenditure
1. The SRO will ensure that funds are disbursed in accordance with the signed agreements, adequate risk mitigation; and satisfactory financial management, including forecasting and accounting for variances. The Funds for the DCA and commercial contract will be disbursed quarterly (DCA) or monthly (contract) upon demonstration of realised activities, in accordance with the budgets, forecasts, progress and financial reports ensuring payments are not in advance of need. The FCDO programme team will conduct programme performance review meetings across the programme components to discuss implementation progress, challenges and delivery risks.
2. The PRO will apply standard financial monitoring, reporting, and accounting arrangements to ensure funds are not disbursed in advance of need; and that in liaison with the FCDO finance team ensure that each tranche is properly accounted for before new disbursements are approved.  FCDO will discuss and agree in advance with implementing partners any funding changes that impact delivery of the programme. Robust financial management, accurate forecasting and delivering results on time will be part of the key performance indicators for all implementing partners, with actions implemented robustly and at pace. Audit reports will act as additional levels of assurance, strengthening financial management controls through external processes.
Forecasts
During inception phase more detailed design work for each intervention will take place that will enable more accurate estimates to be made for the costs of delivering activities. Forecasts will be shared quarterly (DCA) or monthly (contract) with FCDO by the implementing partner. The programme team will reconcile these forecasts against (i) relevant data on the financial management system; (ii) annual work plans and budgets; (iii) previous reports; and (iv) annual and quarterly spending trends. Partners will be expected to apply resource accounting in budgeting and aim for less than 5% variances in their monthly forecasting and 1% variance for annual forecasts and budgets. This is however not cast on stone as risks and issues will sometimes crop up that can adversely impact the achievement of these delivery targets. Proactive communication will however be expected from implementing partner for effective management of risks and contributing to timely decision making. The format and content of financial reports will be discussed and agreed with the implementing partner during kick off and will follow the standards spelt out in the FCDO Programme Operating Framework (PrOF).
Financial risk and fraud
1. The programme will be delivered through a development partner and a commercial contractor. The main financial risks include funding not presenting good value for money, fraud, and loss/lack of record for assets. The residual fraud risk rating is Moderate. This is lower than BEM portfolio rating at Major, based on the safeguards mentioned in the paras below, and the better ability of physical access in Somaliland, enhancing ability to verify and monitor at short notice. SRO and PRO have their office minutes away from the implementing partner and SMP3 monitoring partner, thus also improving oversight and the ability to provide ad hoc spot checks, which is not possibly in programmes implemented in South Central Somalia.
2. Funds disbursed to Denmark will be paid based on activities delivered, which will discourage misallocation and will monitor spend.
3. To mitigate fraud risk, Denmark (DCA) will use independent third-party monitoring agents to verify activities on the ground and flag any risks. FCDO will hold biannual partner meetings to emphasize fraud management requirements, including regular messaging from senior FCDO leaders. The programme team will ensure regular reporting on activity progress and expenditure. FCDO will also carry out annual reviews to assess progress towards outcomes, value for money and risks. A detailed session will be held with implementing partner teams at inception to discuss FCDO PrOF rules and delivery requirements.
4. Overall, the SDF3 SRO and PRO will ensure that financial management, transparency and accountability systems of implementing partner meet HMG requirements, and that their risk mitigation measures, including to guard against Fraud and Sexual Exploitations and Harassment, are sufficiently robust.
5. Recommendations from existing partner due diligence assessments will be scrutinised and actioned robustly. A DCA does not include a due diligence assessment (DDA) of Denmark, although Denmark will conduct a DDA of the successful bidder as part of their OJEU tendering process. The programme team will take the necessary steps to ensure the programme adherence throughout the delivery chain to the zero-tolerance policy on fraud and the UK Counter Fraud/Bribery and Counter Terrorism legislation, and that all incidences of suspected/or alleged fraud are reported immediately to the Fraud Investigation team in the Internal Audit and Investigation Directorate.
Audits
Partners will be required to provide annual independent assurances to FCDO, that FCDO funds have been used for the intended purpose through audits or audited financial statements.  Implementers with downstream partners will be expected to apply the same level of rigour in managing their partners and ensure compliance with FCDO financial and programme delivery standards. Implementing partners will be responsible for ensuring the implementation of lessons and recommendations from such audits to continuously improve safeguards.
Assets
Partners will be required to maintain an updated register of all FCDO funded assets and furnish FCDO with a copy of the updated register at least once per year, and at points of asset changes. Asset disposal will be done in accordance with the FCDO PrOF while maximising value for money and ensuring clear communication on usage, storage, and disposal of the assets is maintained throughout the delivery period by the partner. Cars will include trackers, to ensure they will only be used for their intended project purpose.

Management Case
Management Roles and Responsibilities
This programme will be led by the Danish with the support from the programme team in British Office Hargeisa. The SRO and PRO programme team will support the successful management and implementation of the SDF3 programme in partnership with other SDF3 development partners. The FCDO team will ensure that the implementation of both components align and comply with the FCDO PrOF requirements. The team will have support by other cross-cutting advisers, especially on climate, social development and governance – these are existing advisers within the Somalia network. This will also ensure close alignment with other FCDO programmes in Somaliland, specifically Green Urban Growth (GUG)/ Sinaan programme. The team will also work closely with the commercial and finance specialists to ensure enough flexibility is built into the Delegated Cooperation Arrangement with the Danish considering the lessons on delivery in fragile, complex, highly political contexts, and UK funding constraints.

Governance Arrangements
Programme leadership tier: Joint Steering Committees, chaired by the Minister of Planning, National Development Partners, and co-chaired by Denmark. This body will meet quarterly or more often if needed to discuss and decide a way forward both on SDF3 and technical advisory issues. The SDF3 Fund Manager will act as the JSC Secretariat. Government of Somaliland ministries implementing both components of the programme will attend the JSC as observers when needed. The JSC will steer the direction of the programme. The decision-making structure in this forum will be made by consensus.
1. A Memorandum of Understanding between the GoSL and the SDF3 donors will act as the Component 1 governance agreement. Separately, Denmark, as the lead donor in SDF3 and the technical facility for this one-year transition, will enter into Delegated Cooperation Arrangement (DCA) with FCDO. The DCA will establish a clear framework of partnership between Denmark and the FCDO. Denmark is procuring a Fund Manager who will deliver this component.
2. As the administrator of Components 1 and 2, the Fund Manager has responsibility for overall stewardship of the donor funds received. This includes managing, controlling and reporting on funds received and projects funded, and supervising the use of funds disbursed. Day-to-day management of those Components rely on the Fund Manager’s apparatus and its operational policies and procedures.
3. The Fund Manager will also be responsible for appraisal, implementation, review, and monitoring and reporting on all performance aspects of the Components financed activities. The Fund Manager will also assume, on behalf of the donors, fiduciary responsibility (including active reporting on exchange rate movements) for the funds spent by the component. The Fund Manager will operate under the strategic direction and supervision of the SDF3 Joint Steering Committee as represented in the diagram below:
Table 5: SDF3 governance structure

Mobilisation and start up
Mobilisation of both components will take place in parallel, starting in September/October 2025
1. Component 1: It is intended that the DCA with Denmark will be signed no later than 30 September 2025 to allow for the UK to be one of the founding donors. Denmark completed a competitive process for fund manager procurement. Mott MacDonald were selected to lead implementation until 2028.
2. Component 2: This component will also be implemented by the Danish who are leading on the SDF3 programme. A pilot technical advisor test and a workshop for the design and modality of the delivery unit and its practicality will be conducted during this transitional programme. Lessons learned from the programme will be incorporated into the portfolio programme scheduled to commence next financial year.
Reprioritisation, exit strategy and extensions
The DCA with the Danish will clearly state that FCDO contribution will be valid for this financial year ending 31 March 2026. Contribution to the programme in outer years will depend on the design of the new Somaliland portfolio programme and the availability of funds.

Risk management and risk register
1. The overall net risk rating for the SDF3 programme is assessed as Major, which is within the risk appetite for BEM. As reflected in the BEM risk appetite statement, a high-risk appetite is necessary to achieve planned development, policy, and regional security returns in Somaliland. The Somaliland operating environment is unpredictable, internal and regional political tensions e.g. uncertainty following recent national elections, escalation of conflict and insecurity particularly in the East of Somaliland, and low government capacity, that may disrupt programme implementation in some geographies. Additionally, misappropriation of funds and safeguarding risks could minimise the programme impact.
2. Risks will be proactively managed throughout SDF3’s inception and delivery in line with FCDO risk management practices. This includes ensuring linkages to other FCDO programming through internal discussions at the risk programme forums, working group, portfolio board, and country strategy board. FCDO will maintain a programme risk register for SDF3, which will be regularly reviewed and updated by the programme team. Delivery partners will also be expected to maintain their respective risk registers which will feed into the FCDO SDF3 and BEM risk registers. FCDO will ensure that all partners proactively track, monitor, mitigate and report risks by including relevant clauses within agreements and ensuring risks are regularly discussed with partners in meetings and reports.
3. The SROs will escalate risks which exceed their risk appetite through SDF 3 governance structures to FCDO development directors, HoMs or directors, and directors will do so likewise to directors general. Alongside this, risks will be escalated directly to Ministers if appropriate, particularly significant risks to delivery or reputational risks.
4. The SDF3 programme team will also ensure that appropriate linkages are maintained across the BEM portfolio, especially in managing political, security, climate, fraud, and safeguarding risks.
5. The Table sets out the key risks to the success of the programme and mitigating measures. FCDO will regularly review programme risks, including identifying emerging risks and actions to mitigate:
Table 6: Main programme risks
	Title	Summary of Risk	Gross Risk	Mitigating Actions	Residual Risk
	Strategy & Context: Risk Appetite – Receptive (BEM RA is at Eager)
	Political uncertainty and interests	Heightened political uncertainty following national election outcomes, government capacity and localised conflict hinder programme delivery and undermine international support for development objectives.	Severe	FCDO to adopt a flexible approach to planning and implementation, allowing project activities to be postponed or funds shifted from one project to another. / FCDO to maintain high-level dialogue, and relationships with the government to remain aligned on priorities and to influence the government on programme interventions. / Conflict and political economy analyses are more explicitly included in programme design and implementation. More proactive and intentional participation of conflict and governance advisers in programme implementation. / Partnership Principles and aligned engagement scenarios in place and regularly updated in cross-Network effort.	Major
	Conflict in Somaliland	Conflict in the East spills over into intra-clan conflict and/or regional conflict.	Major	Programme designed to be flexible both in terms of scale and delivery channel. Conflict and political economy analyses are more explicitly included in programme design and implementation. More proactive and intentional participation of conflict and governance advisers in programme implementation. / FCDO to intensify engagement with Somaliland political actors and influencers. Drive alignment with international partners including through the various coordination forums to support dialogue between warring parties. / FCDO to liaise with development and implementing partners to monitor risks actively to the programme and identify mitigation in the event of increased insecurity.	Major
	Somaliland authority buy-in to diversification	Reduced state political commitment to diversify the economy, support inclusive and resilient economic growth, or deterioration in HMG relationships with the Somaliland authorities.	Major	Working closely with key SDF3 stakeholders gives early warning on change of policy, allowing SDF3 to influence, and to seek HMG and other development partners’ influencing support when necessary. / If these efforts fail and political support is critical, support would be scaled back or stopped.	Moderate
	Policy and Programme Delivery – Risk Appetite – Receptive (in line with BEM risk appetite)
	Component governance	The components are not working well together.	Major	Strong governance mechanisms as developed at mobilisation stage. These include at a minimum a quarterly Joint Steering Committees at Ministerial level, with both components and donors. Operational Committee will meet monthly. / Governance mechanisms include knowledge sharing between the two components as set out under the preferred option in the Appraisal Case.	Moderate
	Spend pressures	Inability to spend budget due to late agreement of SDF3 funding.	Major	FCDO/SDF3 to monitor and engage with business planning process and update its budgets and forecast as possible. / Agreements and contracts include necessary caveats and break clauses. / Our strong coordination with other donors can seek to ask other donors to step in and bridge our funding, as evidenced during the FCDO budget cuts. / Strong engagement with FCDO Programme Team and Danish to ensure breadth of donor spend is concluded in time. Somalia Network to offer in-kind programme management support to facilitate understanding of FCDO financial processes.	Major
	Political will	Insufficient political will to make the transformational changes mentioned in the Theory of Change	Major	Using TWP approach to shift opportunistically where needed, working agile and flexibly. / British Office Hargeisa team working closely with the Somaliland authorities, being alert to changing contexts.	Moderate
	Outcomes missed	Programme fails to deliver intended outcomes due to rapidly changing contexts.	Major	Theory of change assumptions constantly tested; / Programme context and progress regularly reassessed to create opportunity for redirection of outcomes and results as needed; robust MERL approach that accommodates feedback loops developed.	Moderate
Public Service Delivery and Operations - Risk Appetite – Cautious (in line with BEM risk appetite)
	Security deterioration of project locations	Major attack on project locations could prevent implementing or monitoring partners and FCDO staff to slow down/halt project delivery.	Major	FCDO programme team in Hargeisa to monitor the security situation of the project sites and to get updates from the implementing partners during the monthly meetings or soon after an issue develops. / The supplier needs to have a security focal point that keeps an eye on the security situation of the project delivery locations. / Including contractors’ contracts clauses of suspending contracts in case of any serious risks arises from the project sites.	Moderate
	Fund Manager delivery Issues	Changes in Core Team Members, at short notice.	Moderate	Having a staff retention mechanism in place. / The supplier must establish a recruitment procedure that verifies staff performance prior to contracting and allow for rapid identification and mobilising of replacement staff. / Establishing a roster of experts that can replace core staff as needed. / Setting in place robust knowledge management system within SDF secretariat to manage store and share information generated.	Minor
	Financial and Fiduciary - Risk Appetite – Cautious (BEM is at Receptive)
	Fraud	FCDO funds and/or commodities are diverted or not used for intended purposes and therefore demonstrate poor VfM	Major	Fraud risk and due diligence assessments ahead of disbursement; delivery chain risk mapping completed and managed by supplier annual independent audits and regular spot checks to be commissioned by FCDO. / All suspected and actual cases of Fraud reported and managed in close coordination with FCDO’s Counter Fraud Unit / Regular fraud training for programme team and implementing partners throughout the delivery chain, and clear signposting of whistleblower mechanisms	Moderate
	Exchange rate fluctuations	Exchange rate distorts programme’s ability to deliver within 5% of variance	Moderate	Contracts and disbursements are made in GBP, which will then be transformed into Danish Krona (component 1) or USD (component 2). Being dependent on exchange rate fluctuation due to exchange rate issues will need to be taken into account and communicated to the implementing partners at the start. / FCDO contract provisions on exchange rate management will place the responsibility on the suppliers/lead implementers.	Minor
	Reputational: Risk Appetite – Cautious (in line with BEM)

	Perceptions of elite capture	Risk of SDF3's activities being captured by one or more political/ clan-based elite. Working with the usual suspects and/ or large enterprises might reinforce the embodiment of status quo in terms of existing power dynamics and/ or lack of competitiveness.	Major	Ensure the focus on working with and for the benefit of a broad base of stakeholders is maintained. / SDF3’s implementing partners, and their staff stay abreast of political and social dynamics through periodic PEA, bringing in the governance adviser from the start / Ensure a minimum and diverse representation of national staff among SDF3’s implementing partners. / Put in place a robust and transparent procurement system. / Adopt a methodology for project prioritisation that ensures equity. / Maintain strategic relationships with Government authorities.	Moderate
	Reputational spill-over	Reputational damage to FCDO due to other risks not being properly managed	Major	Periodic review of risk registers and mitigations put in place to address risks in response to changing situations.	Minor
	Safeguarding: Risk Appetite – Receptive (in line with BEM risk appetite)
	Unintended environmental, social, governance consequences	FCDO may be criticised for facilitating investments that may fail or that may have unintended negative consequences either from an environmental, social or corruption perspective.	Major	SDF3’s implementing partners required to adopt best practice in environmental and social impact assessment and comply with all applicable local and international laws. / SDF3’s implementing partners to develop robust safeguarding plan and beneficiary feedback mechanism. / Regular safeguarding training and safeguarding updates / BOH safeguarding champion is also PRO of the SDF3 programme. / Using DDA recommendations to strengthen controls and Third-Party Monitoring verification to ensure action has been taken.	Moderate
	SEAH	There will be increased risk of SEAH in light of engaging communities more deeply to enable inclusion of women and more marginalised/vulnerable groups	Major	SDF3’s implementing partners will be required to develop and enhance their Do No Harm policy with clear lines of reporting SEAH concerns should they arise. / Conduct SEAH workshop with implementing partners to aligned them to FCDO ways of working and zero tolerance policies. / Bring in SDA regularly to check best practices.	Moderate
	People: Risk Appetite – Cautious (aligned with BEM)
	Missing governance adviser	Programme team have limited capacity to deliver high value programmes. Currently no dedicated governance adviser within Somalia Network.	Moderate	Workforce planning will ensure a proper balance between advisory and programme management support. / Bringing in 10% governance support where possible and influencing Somalia Network to reopen the governance advisory position.	Minor

Safeguarding
1. The economic development sector, particularly related to infrastructure, carries social and environmental safeguarding risks including SEAH. These run from procurement through to implementation and closure. If the programme supports increased infrastructure investment without mitigating safeguarding risks, then there is a risk of the programme causing harm. These risks are mitigated at the macro-level through implementing better regulatory policy frameworks which will be enablers for the government to attract investment from less scrupulous sources. The programme will therefore work to ensure that the regulatory and policy framework, and associated government capability, is built to mitigate safeguarding risks and hold investors to account on minimum /agreed social and environmental impact standards in infrastructure. Political Economy Analysis will be helpful in identifying shared UK-GoSL priorities within this space, government champions and entry points for action. A baseline assessment is recommended to assess the current approach within the sector and identify areas of opportunity to strengthen. This would ideally be done in consultation with, or with direct participation from civil society/ affected populations.
2. FCDO assesses the safeguarding risk to be major with a plan to reduce the risk once mitigations are in place. Within the delivery chain there is a risk of SEAH within infrastructure projects (Component 1) or within government ministries where the TA is based - perpetrated by or towards the TA, or within the ministry setting (Component 1 & 2). This risk stems from limited protections against SEAH in the workplace, and within a culture where violence against women and girls is normalised. It is imperative that the programme follows FCDO’s zero tolerance to safeguarding instances and inaction, and there is a proportionate mitigation at all levels. Examples include:
  1. Clear code of conduct throughout the delivery chain including measures of preventing SEAH from happening.
  2. Robust pre-employment checks for anyone working on the programme.
  3. Safe and accessible reporting pathways for SEAH survivors and provisions for survivor centred response.

Safeguarding will be embedded within the programme’s modus operandi and both SDF3 and the Advisory Facility will have dedicated safeguarding expertise. Safeguarding will be streamlined throughout the delivery chain and FCDO expects all stakeholders to follow the same due care to minimise the opportunities for safeguarding instances to occur. These include testing the robustness of the process during the Due Diligence of the supplier, open and frank conversations on safeguarding, integrating safeguarding into governance arrangements, recruiting a supplier with access to special safeguarding expertise, having disaggregated data as part of the results framework and including contractual provisions and milestones on safeguarding in the supplier contract. The full suite of mitigations and tools will be assessed during mobilisation.
Monitoring, Evaluation and Learning
1. The programme SRO and PRO are responsible for developing a comprehensive MEL framework to maximise learning and flexibility to adapt throughout and especially between both components during the implementation of the transitional one year. It will work with and build on Denmark’s MEL system for the SDF3, ensuring learning from the SDF3 can inform the Advisory Component and vice versa. This will overall strengthen the UK’s learning and thought leadership on systems-based approaches to governance and green infrastructure development in FCAS. The approach to MEL will:
2. Develop a strategic monitoring, evaluation and learning framework. The programme team will work with SDF3 and Advisory Component implementing partners to finalise the results framework during inception, develop processes for monitoring and agree processes for changing and updating logframe outputs, indicators and targets, including for ICF indicators such as KPI 1 and 4. We aim to work with Denmark and the SDF3 supplier to develop a results framework that is aligned with UK priorities, to minimise duplication where possible. Attribution will be maintained to avoid double counting. This will be developed by the PRO in coordination with the MEL adviser at mobilisation stage, with SRO oversight. Progress against the logical framework indicators will be tracked and discussed at monthly meetings with the delivery partners.
3. Monitor and assure performance during implementation. The MEL framework will ensure accountability between implementers and the programme team, using third-party support where there are access constraints. Denmark will procure a third-party monitoring agency to monitor and verify the SDF3 component. The Advisory Facility component will be monitored and verified through SMP3 or its successor programmes. The framework will provide an additional oversight function, ensuring that cross cutting themes (gender, social inclusion and climate) are fully mainstreamed into the design and monitoring of specific interventions. The programme team will work closely with the implementers to ensure lessons are shared across green infrastructure programmes and with relevant development partners, to shape investments by others (e.g. the World Bank, AfDB, EU). If required, findings will also feed into the Business and Country Plan, particularly the goal on Somaliland when signed off.
4. The FCDO’s REACH team will be available to guide and assist the SDF3 development partners at every stage of implementation including quality assuring related ToRs, procurement of service provider/s and reviewing the outputs to ensure evaluations uphold highest quality standards.