Business Case – August 2025

Summary Sheet

Portfolio/ Business/Country Plan Summary: / Mauritius is a Commonwealth democracy with close historical and cultural ties to the UK. Our current priority is to support and lead implementation of the Agreement concerning the Chagos Archipelago, ahead of ratification and entry-into-force in 2026, given the strategic importance to the UK and to Indian Ocean security of the joint UK/US base at Diego Garcia. In parallel to treaty implementation, we are also implementing the new UK-Mauritius Strategic Partnership Framework (SPF), a bilateral cooperation agreement signed alongside the deal, which sets the long-term direction and structure of UK-Mauritius relations this century. As the SPF sets out, our interests here are wider than the Chagos agreement. Our Country Business Plan goals for 2025-26 are therefore: / Core Service Delivery: Grow and deploy our diplomatic relations and influence to deliver implementation of the Agreement concerning the Chagos Archipelago ahead of entry-into-force in April 2026; deliver a high-quality consular service; prepare to respond effectively to a crisis; and provide robust corporate services to create a strong foundation for delivery of our mission statement; / Boosting Bilateral Growth: Promote UK growth and prosperity by implementing an enhanced Strategic Trade Partnership (STP) with the Government of Mauritius; deliver the trade & growth pillar of the SPF; and maximise opportunities for British businesses and investors in the economic partnership under the Agreement concerning the Chagos Archipelago; / Tackling Climate Change: Support Mauritius to unlock climate finance at scale from the private sector and international green funds through embedded UK expertise, progress the implementation of the Climate and Nature pillar of the SPF and advance Mauritius’s priorities on climate change including through capacity building; / Enhancing UK Security: Implement, with FCDO headquarters, the defence and security pillars of the Agreement concerning the Chagos Archipelago to safeguard Diego Garcia operations; implement the Maritime Security & Irregular Migration pillar of the SPF; and coordinate with the Indian Ocean Network on shared security threats; / Combating Illicit Finance: Build resilience to illicit financial flows (IFF) in Mauritius, delivering the objectives of the FCDO’s campaign to combat IFF.

Title: / Strategic Partnership Framework Programme (SPF-P)
Programme summary (100 words maximum): / The Strategic Partnership Framework Programme, or SPF-P, will implement and deliver core activities of the UK-Mauritius Strategic Partnership Framework (SPF), a bilateral cooperation agreement signed by the Foreign Secretary and Foreign Minister Dhananjay Ramful (Republic of Mauritius) in conjunction with the Agreement concerning the Chagos Archipelago on 22 May 2025 (by PM Starmer and PM Ramgoolam). The programme will be the principal mechanism through which SPF pillars relating to Maritime Security and Irregular Migration, Climate and Environment, Growth, Trade and Investment, and Institutional Reform and Good Governance will be implemented, commencing a new era for bilateral development relationships.
What is the rationale for UK Aid spending? (200 words maximum): / The SPF was conceived and drafted in collaboration with the Government of Mauritius and signed in the margins of the Agreement concerning the Chagos Archipelago. It sets a clear, long-term, strategic direction for UK-Mauritius relations as we work more closely together to implement the Agreement. Successful implementation of the Agreement and the SPF will see a significant boost to Mauritius’s achievement of its economic and human development priorities; and are therefore the core focus of Post (British High Commission (BHC) Port Louis)’s delivery of the FCDO’s six priorities and each of the 2025-26 Country Business Plan’s over-arching Goals (1-5): Core Service Delivery, Boosting Bilateral Growth, Tackling Climate Change, Enhancing UK Security, and Combating Illicit Finance. The UK Government’s comparative advantage is our expertise and ability to deliver in the relatively small (but increasingly contested) Mauritian operating context against each of the SPF pillars. The strategic outcome of the SPF-P, and the UK’s fundamental interest, is the successful implementation of the SPF that realises the goals and direction of the UK-Mauritius relationship set by the Foreign Secretary and Foreign Minister Ramful in May 2025.
Programme Value: / £1.5m, 2025-26		Country/ Region or Sector: Mauritius/Western Indian Ocean
Department/Country Office confirmation of review processes		Yes
Contact name		Kate Thomson, Head of Political, Programmes and Comms, BHC Port Louis (Mauritius)
Threshold for final approval of Business Case: Head of Mission (Port Louis)
Date of Approval of Concept Note:	20/08/2025	Paul Brummell, High Commissioner and Head Indian Ocean Network
Date of Approval of Business Case:	22/09/2025	Paul Brummell, High Commissioner and Head Indian Ocean Network
Programme Code: 400792	AMP Start Date: 17/09/25	AMP End Date: 31/08/2026 (for completion of activities)
Overall programme risk rating:	Moderate

Strategic Case

Context (1) – Mauritius Development Challenges
Mauritius is an island state of 1.26 million people. The country’s economy has developed rapidly since independence in 1968 and is currently classified as an upper-middle-income economy. Mauritius became a high-income country in 2020, but the impact of the COVID-19 pandemic meant it slipped back to upper-middle income country (UMIC) status in 2021. Development and growth have been slow since that time due to the pandemic, compounded by other exogenous shocks, including global inflation, the war in Ukraine, and the increasingly severe impact of climate change. Mauritius’s status as a UMIC means it is eligible to receive Official Development Assistance (ODA). Its key challenges in 2025 remain inflation, high public spending and levels of public debt, an ageing population, and the negative impacts of climate change on its key industries. Mauritius is a multi-party democracy and member of the Commonwealth, with free, fair and regular elections which have seen the peaceful transfer of power approximately every five years since independence.

Context (2) – UK-Mauritius Strategic Partnership Framework
Against this backdrop, the UK and Mauritius signed a bilateral cooperation agreement – the Strategic Partnership Framework (SPF) – on 22 May 2025, alongside and complementary to the Agreement concerning the Chagos Archipelago. The SPF was signed by the Foreign Secretary and Mauritian Foreign Minister Dhananjay Ramful as an open-ended agreement to advance shared, agreed-upon economic and development goals across a number of thematic pillars: Maritime Security and Irregular Migration; Climate and Environment; Growth, Trade and Investment; and Good Governance and Institutional Reform. It sets a clear, long-term, strategic direction for UK-Mauritius relations as our countries work ever more closely to implement the Agreement concerning the Chagos Archipelago, a top FCDO priority. Successful implementation of the SPF and the Agreement are the main focus of Post (BHC Port Louis)’s Country Business Plan for 2025-26 (and likely beyond): Core Service Delivery, Boosting Bilateral Growth, Tackling Climate Change, Enhancing UK Security, and Combating Illicit Finance.

Delivery of these strategic priorities and the CBP will be operationalised by the Strategic Partnership Framework Programme (SPF-P). This business case recommends establishing the SPF-P for a transitional period of one financial year, 2025-26, and using the evidence of this transitional year (along with the evidence of the preceding ODA programme, on which more below) to establish a multi-year business case from 2026-27 to 2028-29. The broad strategic range and timeframe of the SPF means the Programme’s activities will need to flex across financial years, but it will remain fixed on 1) implementation of key elements of the Agreement concerning the Chagos Archipelago (particularly as it relates to environmental considerations) and 2) the delivery of shared objectives on migration, climate change, growth, combating illicit finance, and democratic governance. The main beneficiaries of the intervention will therefore be the UK and Mauritian Governments. Both the SPF and the SPF-P align with the FCDO’s internal categorisation of the development relationship with Mauritius as an “Investment and Expertise Development Partnership”.

Evidence Base – ODA Programmes in Mauritius
The main evidence base on which the SPF-P is based and from which it will draw in delivery was established by Post’s previous ODA programme, the Mauritius Multi-Sector Development Programme (MMDP, £1.3m, 2022-2025, AMP code 400050). Successive annual reviews found MMDP was an exemplar of how to use small, targeted amounts of ODA in small-scale capacity building and technical assistance projects to effect transformational policy change with a key UK strategic partner in the region. MMDP was approved to support implementation of the Mauritian Government’s Vision 2030 development policy, which ultimately became obsolete following the 2024 general election. Nonetheless, SPF-P’s strategic case relies on the broad economic and development challenges that Mauritius faces, the vast majority of which have been similarly identified by the current government (since its 2024 election victory). SPF-P also relies on the evidence and programmatic logic of MMDP as it sought to support tackling those challenges, as well as its approach to programme management, value for money, and governance, for its strategic foundation, over-arching objectives, and governance and results frameworks. The evidence and findings of MMDP, and therefore of delivering ODA programmes effectively in the Mauritius context, are set out in MMDP’s two Annual Reviews (2023, 2024) and its Programme Completion Review (2025), all published on Devtracker, which marked the programme at A in each of its three financial years. In design and as we move to delivery, the SPF-P will follow the lessons and recommendations from each of these reviews.

Combating the Financing of Terrorism (CFT) and Anti-Money Laundering (AML) Considerations
Countering illicit finance is one of the central pillars of the SPF and therefore SPF-P. The UK’s work to strengthen key Mauritian institutions and practice, including compliance with Financial Action Task Force (FATF) standards and our ongoing work to prepare Mauritius for its next Mutual Evaluation Review, will ensure the programme is resilient to risks of terrorist financing and money laundering. Due to the nature of the overall programme and the SPF-P’s optimum implementing partners, the overall risks of CFT/AML are considered to be generally low. CFT/AML risks were monitored by the MMDP programme board and by implementing partners, and no significant concerns were reported. Risks will be monitored closely by Post’s Countering Illicit Finance team, who will themselves lead project management of some elements of the SPF-P during the implementation phase.

Public Sector Equality Duty (PSED) & Gender equality, disability and social inclusion (GEDSI) Considerations
GEDSI objectives are particularly relevant to Mauritius, a country which has high levels of ethnic, cultural and social diversity. Principles of inclusion and equality are embedded in Mauritius’s constitution but remain a central topic of debate in public life and government policy, particularly as they relate to ethnic group equality and representation. Challenges related to inequality and marginalisation of ethnic minority groups, women, less economically advanced people, the LGBT+ community and people with disabilities persist, constraining broader development outcomes[1]. The government has shown cognisance of the existence of these inequalities and of the importance of addressing them (not least as a Commonwealth democracy). Policy and legal frameworks promoting gender equality are in place, yet women remain underrepresented in political leadership, there is widespread evidence of gender-based violence (GBV - particularly in domestic settings), and the burden of unpaid care work falls disproportionately on women. People with disabilities encounter systemic barriers to accessing essential public services, limiting their full participation in society. Legal protections exist for LGBT+ individuals, yet many report experiences of marginalisation and discrimination. Social and economic marginalisation particularly affects the Creole community and people of Chagossian heritage. These intersecting inequalities highlight the importance of ensuring inclusive approaches to Mauritius’s development and in the delivery of SPF-P. Implementing partners will need to be particularly alive to the risks that projects emphasise or exacerbate these divisions, and the BHC programme team will ensure these risks are monitored and managed through its governance arrangements.
[1] UNDP Human Development Report 2025 (Mauritius HDI score drops significantly when adjusted for inequality)

Climate and Environment Considerations
As with anti-money laundering, climate and environment objectives are central pillars of the SPF and therefore SPF-P. Climate change is one of the most significant challenges Mauritius faces as a Small Island Developing State (SIDS) and supporting the government to tackle this challenge at a national and international level is one of the SPF-P’s central strategic objectives. Because of the acute local nature of this risk, the SPF-P will maintain a discrete climate risk register to provide sufficient (yet proportionate) climate risk assurance. The SPF-P will include projects relating to infrastructure, including energy and transport, social development, and technical assistance. The programme and implementing partners will therefore need to be particularly alive to risks around fossil fuel investment. Climate risk assurance will also need to be a central consideration for implementing partners, who will be expected to report specifically on their management of climate related risk.

Partnership Principles Assessment (PPA)
The SPF-P is considered to be in the middle of the spectrum identified by the PrOF. While the programme will largely be focused on the provision of technical assistance and capacity building to the Government of Mauritius, Mauritius will also receive a proportion of grant financing through the Taskforce on Access to Climate Finance Programme. Programme leads are considering a PPA for Mauritius during the course of completing the Fiduciary Risk Assessment (FRA) for Mauritius, ongoing at the time of writing (September 2025). Funding will be channelled through implementing partners, with the Government of Mauritius often the principal beneficiary. A PPA should be conducted, but in line with MMDP (on the evidence base of which, as this Strategic Case sets out, the SPF-P is largely founded), it will be for the SRO and PRO, working with Taskforce leads, to determine what a proportionate PPA process looks like in the context of the SPF-P timeframe and level of spend.

Safeguarding
The SRO and PRO will ensure that proper safeguards, monitoring and reporting are in place for all implementing partners, with effective prevention and reporting systems. All implementing partners will be supported to understand and proactively manage their safeguarding responsibilities, and to understand how to report them promptly to the FCDO, using the safeguarding toolkit for external partners. Implementing partner capacity and capability on safeguarding will be assessed rigorously through the due diligence process, and all due diligence reports (following MMDP’s example) will be cleared at SRO level before projects are delivered.

Risk
More detail on risk profile, appetite, and management is outlined below. The SPF-P will again seek to follow MMDP’s example by ensuring robust risk management and monitoring processes are in place. The SRO will ensure that risk is a standing agenda item on the quarterly board agenda and will hold the PRO accountable for the effective management, monitoring and escalation of risks and issues. The SPF-P will need to take a proportionate approach to its risk appetite, given the nature of the activities and the relatively low-risk operating environment.

Appraisal Case

This Appraisal Case has been drafted in line with the steps outlined in the PrOF Business Case guide.

Planned SPF-P Interventions and Theory of Change
The SPF is a bilateral cooperation mechanism that supports Mauritius’s economic development. The SPF-P is fundamentally a vehicle through which the priority objectives and provisions of the SPF will be delivered, in line with the overarching goal of promoting Mauritius’s economic development. Because the agreement is open-ended and long-term, it has been necessary to agree on the prioritisation of the most pressing SPF objectives on the basis of their significance and relevance to the Mauritian Government’s development objectives. The SPF-P’s planned interventions in 2025-26 will be structured around delivering those priority objectives, agreed bilaterally with the Ministry of Foreign Affairs, Regional Integration and International Trade. The relevant priority objectives are outlined in the table below, alongside the interventions that will deliver them in 2025-26 (further detail on costings outlined in the Financial Case). These interventions have been chosen through high-level discussion with the Mauritian Minister of Foreign Affairs as representing the most important and pressing elements of the SPF to be delivered (or commenced) in the first year of the agreement’s life, with remaining and wider provisions prioritised for delivery from the second year of the agreement’s life (the programming delivery vehicle for which is due to be determined).

Intervention	Key Deliverables	Preferred Implementing Partner Type	SPF reference
STRATEGIC OBJECTIVE: Delivery of SPF Section 5.1: “Alongside policy reforms by Mauritius, and in collaboration with the private sector, deliver a £12 million Access to Climate Finance programme that could unlock up to $1 billion in climate finance (25% of the funding gap in Mauritius’s Nationally Determined Contribution 2.0) to mobilise funding for mitigation and adaptation projects. This has a significant grant finance component.”
#1 - UK-Mauritius Taskforce on Access to Climate Finance	£1m grant finance component to support the set up and operation of Mauritius’s Climate and Sustainability Fund, through the existing Taskforce on Access to Climate Finance programme – subject to conclusions and recommendations of the 2025 Fiduciary Risk Assessment (September 2025); / Quarterly public/private climate finance coordination forum launched with dedicated secretariat and outcomes agreed (October 2025); / UK/Mauritius MoU signed (October 2025), subject to recommendations of the Fiduciary Risk Assessment; / Technical Steering Committee oversees first draft of National Climate Risk Map (March 2026).	Internal – HMG grant finance to the Government of Mauritius, subject to conclusions and recommendations of Fiduciary Risk Assessment (FRA – September 2025)	5.1
STRATEGIC OBJECTIVE: Delivery of SPF Section 5.5: “Provide technical support for the management, monitoring and enforcement of the Chagos Archipelago Marine Protected Area (MPA) to be established by Mauritius, through conservation expertise on mapping, design, governance, compliance, enforcement, sustainability, and capacity-building.”
#2 – Technical Support to the Chagos Archipelago Marine Protected Area	Support lead Ministries within the Government of Mauritius to formally establish a Marine Protected Area in the Chagos Archipelago, mirroring provisions of the existing BIOT/UK MPA; / Enable visits to Mauritius by international conservation experts as required for MPA establishment; / Provide capacity building to lead Mauritian Ministries to ensure the ability to monitor, manage and enforce the MPA is built into the Mauritian system.	External – third party, third sector conservation experts (e.g. Zoological Society of London, and the Chagos Conservation Trust)	5.5
STRATEGIC OBJECTIVE: Delivery of SPF Section 5.3: “Technical support for the implementation of the BBNJ Agreement including in areas such as conservation and utilisation of marine resources, transfer of marine technology, and access to financing to support implementation of the Agreement.”
#3 – Technical Support for Implementation of the BBNJ treaty	Support to Mauritius to implement and bring into effect the international agreement on the Conservation and Sustainable Use of Marine Biological Diversity of Areas beyond National Jurisdiction; / Capacity building to lead Ministries in the Government of Mauritius on the conservation and utilisation of marine resources, to build understanding of the terms and limits of the BBNJ; / Build and strengthen Mauritius’s policy, operations, and legal protections around fisheries, in line with the BBNJ agreement; / Support development and strengthening of Mauritius’s enforcement capabilities in its Exclusive Economic Zone in the Chagos Archipelago.	External – third party organisation, the Commonwealth Secretariat (which provides funding and support to Commonwealth countries on BBNJ implementation)	5.3
STRATEGIC OBJECTIVE: DELIVERY OF SPF SECTION 4.7: “Explore development of a civil aviation security programme of training, expertise sharing, and capacity building.”
#4 – Civil Aviation Capacity Building	Initial visit to Mauritius by implementing partners to conduct scoping exercise to establish Mauritius’s key civil aviation risks and needs; / Support to Mauritius civil aviation authority and key ministries to build accurate picture of threat and risk levels; / Support to Mauritius to strengthen, as needed, security culture in domestic civil aviation; / Additional bespoke training on effective cargo chain management, vehicle management and searches, and other security architecture as needed.	Internal – delivered by HMG officials at the Department for Transport (DfT) and/or Civil Aviation Authority	4.7
Strategic Objective: Delivery of SPF Section 6.4: “Explore ways of working together to promote good debt management, debt transparency, and debt sustainability”.
#5 – Sustainable Debt Management and Reform	Provide technical assistance and policy advice to the Ministry of Finance and the Bank of Mauritius (central bank) to improve debt management and fiscal reforms announced in the 2025 budget; / Scoping exercise to be delivered through a visit to Mauritius by implementing partners in 2025; / Creation of bespoke training modules and capacity building in response to specific asks from the Ministry of Finance and the MFA, as needed.	Internal – FCDO’s Public Finance Resource Centre (PFRC)	6.4

As the SPF is in its first and transitional year, SPF-P interventions will need to retain a significant degree of flexibility. The evidence of delivering ODA programmes in the operating context in Mauritius shows the importance of building agility and flexibility into programme delivery, management, and governance to maximise impact and value for money (VFM). The interventions listed above may need to be amended in-year (e.g. on the basis of scale of spend or implementing partner) to better achieve the strategic objective outlined above of realising the SPF as an agreement, and the overarching strategic goal of promoting Mauritius’s development through delivery of the SPF. The SPF-P is intentionally designed such that different, flexible interventions can be introduced or developed by the BHC programme team, so long as they make a clear and obvious contribution to the overarching goal of implementing the SPF as a bilateral agreement, and therefore of promoting Mauritius’s economic development.

Noting both the specific interventions outlined above, and the programme’s inherent need for flexibility and agility, the diagram below outlines a high-level Theory of Change for the SPF-P as a holistic intervention:

INPUT: funding for targeted, small-scale technical assistance projects to deliver against agreed UK-Mauritius priorities for year one of the Strategic Partnership Framework (SPF)

OUTPUT: technical skills, knowledge, and expertise are embedded and expanded in key Mauritian ministries/agencies

OUTCOME: service delivery, effectiveness, and efficiency by key Mauritian ministries/agencies is enhanced as a result of technical skills, knowledge, and expertise

IMPACT: SPF year-one agreed priorities are effectively implemented and provide a firm evidence programme evidence base to promote faster delivery and higher ambition to meet SPF objectives from year two and beyond

ASSUMPTION: planned interventions target the right decision-makers and actors in relevant organisations

ASSUMPTION: service delivery and effectiveness is tangible and measurable in the operating context

ASSUMPTION: year-one priorities are sufficiently broad in thematic scope to provide an evidence base for other SPF provisions

Options for delivering the planned interventions
The options to deliver the planned intervention are:
1. do nothing – do not create a programme to support and enable implementation of the SPF-P;
2. BHC directly manages small-scale, targeted projects on SPF priorities agreed bilaterally with Foreign Minister Ramful and delivered by other HMG, third, or private sector experts, and underpinned by a mix of MOUs, accountable grant agreements or small-scale commercial contracts;
3. direct financial aid to the Government of Mauritius; or
4. funding multilateral organisations only, underpinned by MOUs or accountable grant agreements.

The SPF-P’s delivery model will largely be based on the theory and evidence of the BHC’s delivery of the MMDP in 2022-2025. MMDP’s business case adopted a similar model to Option 2 above, with FCDO staff (both at the BHC and in London) directly overseeing and managing all interventions and programme components. Based on the evidence and experience of the MMDP, Option 2 is considered to be most suitable for the majority of SPF-P interventions at the individual level for the following reasons:
- ability to manage a wide range of stakeholders: the BHC has the necessary relationships with government and the necessary profile across Mauritius’s third sector to ensure that high-quality implementing partners can be identified promptly;
- ability to start quickly: there is a strong Ministerial requirement for delivery to begin and pick up pace as soon as possible, and FCDO oversight is considered the best mechanism to achieve this in an operating context characterised by delay;
- viable resource costs: relying on BHC programme management and policy expertise will ensure SPF-P resource costs can be maintained at a low level, and stand the best chance of maximising VFM;
- flexibility and ability to oversee different types of interventions: the programme team have the required experience of delivering ODA programmes in Mauritius to ensure the SPF-P can meet its objectives in a timely manner, and with a focus on VFM;
- ability to provide in-person support and advice to Mauritius: the programme team are well-practised at working with the Government of Mauritius;
- broader political context: the BHC and headquarters team are concurrently responsible for a range of wider HMG priorities delivering in Mauritius, including (but not limited to) the implementation of the Chagos sovereignty agreement, and so have the necessary political understanding to implement the SPF-P effectively.

The principal Option 2 delivery model will be accompanied by Option 3, a direct financial aid component, which is considered to be the most suitable option for implementing a priority SPF deliverable in 2025-26: intervention #1 in the table above, supporting the establishment and operations of the Climate and Sustainability Fund (CSF), itself a core objective of the UK-Mauritius Taskforce on Access to Climate Finance. The Taskforce was established in 2021 after COP26, responding to concerns among countries most severely impacted by climate change (including Mauritius) that mechanisms to support access to financing for climate mitigation and adaptation were insufficient. (Mauritius is a pioneer country; further detail on the Taskforce programme and its objectives are available in the Taskforce Business Case on DevTracker).

While this intervention is necessarily dependent on Mauritius successfully passing a Fiduciary Risk Assessment (an ongoing process at the time of writing), this delivery model is considered appropriate because the Taskforce has the requisite expertise, relationships, and institutional knowledge to mobilise the CSF, and to rapidly steer and mobilise resources towards achievement of our shared climate priorities; and to do so in the timeframe for implementation of SPF priorities in 2025-26. Furthermore, Option 3 (which will boost the operation of the CSF at a crucial time for Mauritius’s climate ambitions and objectives) offers a good fit with the design of the CSF as a new, flexible, and innovative mechanism that can be moulded over the coming years to best fit Mauritius’s climate finance strategy.

Preferred option: Expected benefits and balance of costs & benefits
The principal strategic benefit of the intervention is that the SPF will be implemented and meets the development expectations and aims of both Mauritius and the UK, with a measurable improvement in the capacity, capabilities, expertise, and service provision of the Government of Mauritius in key areas of mutual interest. These improvements will result in a reduction in poverty levels because the SPF-P will help realise the government’s economic and development priorities, and result in an overall improvement in the government’s ability and capacity to deliver for the people of Mauritius. Because of the flexible and open-ended nature of the SPF, the specific community-level beneficiaries of the SPF-P’s intervention cannot be known at the time of drafting, and indeed are part of the justification for establishing 2025-26 as an initial, transitional year for the programme.

Preferred option: VFM Statement, Measurements, and Considerations
As outlined in the Strategic Case, the SPF-P will follow the evidence base, conclusions, and findings of the MMDP, given their similarity as small, technical assistance focused programmes. VFM should be measured and assessed according to the FCDO’s Five E's model (see below).

Cost drivers and benchmarking: as with MMDP, the principal cost drivers of the SPF-P are expected to be 1) management costs (of the implementing partners to design, monitor, and evaluate interventions) and 2) assignment costs (of physically delivering the technical support to the Government of Mauritius, including fee rates, expenses, travel, communications, and other costs).

Economy - fee rates should be in line with market benchmarks, and the SRO, PRO, and project managers for the SPF-P should be able to demonstrate that daily fee rates charged by implementing partners are benchmarked against the MMDP and other relevant regional FCDO programmes of comparable size. The programme team will also want to ensure that they are following FCDO guidance on “best buys” for small-scale technical assistance programmes. At least one of the planned interventions will have a multilateral organisation as implementing partner, and the programme team will ensure that administration/management fee charges are not above the global market rate and are kept to an absolute minimum as a proportion of costs.

Efficiency – the programme team will ensure that assessments of how well implementing partners are converting inputs into outputs and outcomes are conducted at the project level for each intervention. Implementing partners will be instructed to provide bespoke, project level theories of change, against which efficiency can be assessed by the programme team. The programme team should also ensure that FCDO cadre support (e.g. economists, monitoring, evaluation and learning - MEL - advisers) are invited to participate in VFM efficiency assessments. This will be a crucial part of the evidence base that the SPF-P will generate for a longer term, multi-year successor programme.

Effectiveness and Cost-Effectiveness – effectiveness should be assessed both internally by the programme team against both project level results frameworks and theories of change, and externally, in collaboration with the Ministry of Foreign Affairs. Internally, the programme team will ensure that implementing partners have couched their results frameworks in the context of the specific, relevant provisions of the SPF as a bilateral agreement. Externally, both parties to the agreement (the BHC and the MFA representing the UK and Mauritius) should be satisfied that project level outcomes and impact have effectively delivered against the strategic objectives outlined in the SPF preamble to each pillar, and therefore the foreign policy objectives of both parties.

Equity – the Strategic Case has identified a range of intersecting inequalities in the operating context whose existence highlights the importance of ensuring the SPF-P takes an inclusive approach to delivery. While implementing partners will need to be alive to the risks of exacerbating inequalities and demonstrate that they are working with the programme team to manage these effectively, it will also be important for partners to build clear expectations around the positive impact on equality that they reasonably expect their projects to have, given their thematic profile.

Appraisal of Other Options
Option 1 is not feasible because, in addition to the negative impact on Mauritius’s development priorities in key areas, the end of our development partnership would have significant negative implications for the Strategic Partnership Framework and the wider UK-Mauritius bilateral relationship. The SPF cannot be implemented without the SPF-P because delivery of the majority of its provisions require specialist, technical expertise that require a targeted ODA investment. The negative implications of not implementing the SPF would be severe and likely include: advising the Foreign Secretary to renege on an agreement that he has approved and signed with another Foreign Minister, and causing Mauritius to doubt the UK’s commitment to a new era of bilateral relations (which would very likely extend to doubts about the UK’s commitment to implementing the Agreement concerning the Chago Archipelago).

Option 4 is also not considered to be a viable option because multilateral organisations are not sufficiently resourced or expert in the required field in Mauritius. During the course of MMDP’s delivery, as Annual Reviews have concluded, the BHC found challenges in timely delivery when working with multilateral partners and encountered risks in relation to VFM which can be avoided by pursuing Option 2 instead.

Commercial Case

This Commercial Case has been drafted in line with the steps outlined in the PrOF Business Case guide.

There are four broad options for funding mechanisms to deliver the 2025-26 priority projects for the SPF, as outlined in the Appraisal Case above:
1. Direct procurement through a contracted supplier;
2. Delivery through a third party (multilateral organisation or civil society organisation);
3. Financial aid to the Mauritian Government;
4. Drawing on an FCDO headquarters-managed programme or centre of expertise.

The table below outlines the preferred options, delivery partner type, funding arrangement, and risk management considerations for each of the interventions listed in the Appraisal Case. The broad thematic sweep of the SPF-P means that it will be necessary for interventions to adopt a range of delivery options, funding arrangements, and delivery partners.

Intervention	Key Deliverables	Preferred Delivery Option	Preferred Funding Arrangement	Risk Management
#1 - UK-Mauritius Taskforce on Access to Climate Finance	£1m grant finance component to support the set up and operation of Mauritius’s Climate and Sustainability Fund, through the existing Taskforce on Access to Climate Finance programme – subject to conclusions and recommendations of the 2025 Fiduciary Risk Assessment (September 2025); / Quarterly public/private climate finance coordination forum launched with dedicated secretariat and outcomes agreed (October 2025); / UK/Mauritius MoU signed (October 2025), subject to recommendations of the Fiduciary Risk Assessment; / Technical Steering Committee oversees first draft of National Climate Risk Map (March 2026).	Financial Aid to the Government, delivered through the Taskforce on Access to Climate Finance Programme	Memorandum of Understanding with Government of Mauritius, underpinned by existing agreements with Government through Taskforce on Access to Climate Finance programme.	Grant finance component feasible on the basis of recommendations of the Fiduciary Risk Assessment of the Government of Mauritius, currently ongoing (Aug 2025). / Risk that grant will not be spent in full by the Government of Mauritius will be mitigated by involvement of UK embedded officials in lead Mauritian Ministry.
#2 – Technical Support to the Chagos Archipelago Marine Protected Area	Support lead Ministries within the Government of Mauritius to formally establish a Marine Protected Area in the Chagos Archipelago, mirroring provisions of the existing BIOT/UK MPA; / Enable visits to Mauritius by international conservation experts as required for MPA establishment; / Provide capacity building to lead Mauritian Ministries to ensure ability to monitor, manage and enforce the MPA are built into the Mauritian system.	Delivery through a third party (multilateral organisation or civil society organisation), likely through unsolicited proposal	Accountable Grant Agreement with a local or international NGO	This intervention will most likely rely on expert CSO/NGOs which already have experience of delivering in the subject area in the same operating context. / The chosen partner will be subject to a due diligence process, led by the BHC programme team.
#3 – Technical Support for Implementation of the BBNJ treaty	Support to Mauritius to implement and bring into effect the international agreement on the Conservation and Sustainable Use of Marine Biological Diversity of Areas beyond National Jurisdiction; / Capacity building to lead Ministries in the Government of Mauritius on the conservation and utilisation of marine resources, to build understanding of the terms and limits of the BBNJ; / Build and strengthen Mauritius’s policy, operations, and legal protections around fisheries, in line with the BBNJ agreement; / Support development and strengthening of Mauritius’s enforcement capabilities in its Exclusive Economic Zone in the Chagos Archipelago.	Delivery through a multilateral organisation	Memorandum of Understanding with a UN agency or multilateral	The intervention will most likely be delivered by the Commonwealth Secretariat, which has taken the lead internationally in supporting commonwealth countries to implement the BBNJ agreement, and have already expressed an interest in doing so in support of the SPF.
#4 – Civil Aviation Capacity Building	Initial visit to Mauritius by implementing partners to conduct scoping exercise to establish Mauritius’s key civil aviation risks and needs; / Support to Mauritius civil aviation authority and key ministries to build accurate picture of threat and risk levels; / Support to Mauritius to strengthen, as needed, security culture in domestic civil aviation; / Additional bespoke training on effective cargo chain management, vehicle management and searches, and other security architecture as needed.	Drawing on an HQ-managed programme or centre of expertise	Memorandum of Understanding with HQ centre of expertise	The intervention will most likely be delivered by project managers/technical experts in the UK Department for Transport. Risks are therefore mainly around the availability of resource to deliver the project within the stated financial year. A due diligence assessment will not be necessary.
#5 – Sustainable Debt Management and Reform	Provide technical assistance and policy advice to the Ministry of Finance and the Bank of Mauritius (central bank) to improve debt management and fiscal reforms announced in the 2025 budget; / Scoping exercise to be delivered through a visit to Mauritius by implementing partners in 2025; / Creation of bespoke training modules and capacity building in response to specific asks from the Ministry of Finance and the MFA, as needed.	Drawing on an HQ-managed programme or centre of expertise	Memorandum of Understanding with HQ centre of expertise	The intervention will most likely be delivered by project managers/technical experts in HMG’s Public Finance and Resource Centre (PFRC), led by FCDO, and risks are therefore mainly around the availability of resource to deliver the project within the stated financial year. A due diligence assessment will not be necessary.

The BHC programme team will be responsible for robust programme management, due diligence assessments for implementing partners, safeguarding, financial management, technical advisory, strategic and political communications and monitoring, evaluation and learning. Governance and management are dealt with in more detail in the Management Case below, but the BHC will appoint individual project managers from existing staff who will be responsible for overseeing and managing delivery with implementing partners at the level of individual interventions.

Not-for-profit suppliers, with which the MMDP enjoyed significant success in the local context, will be engaged through unsolicited proposals submitted by experts in the relevant field, and subsequently through Accountable Grant Agreements and/or MOUs (in keeping with the relevant PrOF rules and guides). Fee rates are expected to be in line with standard FCDO programming, and suppliers will be expected and asked to demonstrate that their daily rates, as well as their overall management and administrative charges, have been benchmarked against existing or precedent FCDO programmes and represent VFM in comparison. The SPF-P programme team will use the cost evidence base of MMDP’s constituent interventions as the main tool for cost benchmarking, because (as this document outlines) the programme was a similar size, and engaged in interventions of similar theme and objective (e.g. on climate-related projects such as water infrastructure development delivered by external consultants). The programme team will engage the support of FCDO commercial advisers and economists to affirm that costs and fee rates are proportionate to intervention objectives, and comparable to wider FCDO programming standards.

Both internal and external providers will be given clear instructions around financial reporting and risk management timelines and, as per MMDP, will be provided with templates for regular reporting. Performance of internal and external partners will be assessed through the light-touch Programme Completion Review (PCR) which (subject to approval of SPF-P’s duration) will be due in August 2026.
Financial Case

This Financial Case has been drafted in line with the steps outlined in the PrOF Business Case guide.

The table below sets out in detail the nature and value of expected costs for each of the interventions outlined above in the Appraisal Case. The SPF-P is 100% ODA-eligible and the interventions are affordable within the existing geographical ODA allocation; similarly, all interventions are categorised as RDEL. Intervention #1 is the only intervention that is classified as non-budget support financial aid.

	#1 - UK-Mauritius Taskforce on Access to Climate Finance	#2 – Technical Support to the Chagos Archipelago MPA	#3 – Technical Support for Implementation of the BBNJ treaty	#4 – Civil Aviation Capacity Building	#6 – Sustainable Debt Management and Reform
Flow of funds – (payment recipients; intermediate beneficiary)	Government of Mauritius	Third party NGO/CSO à Government of Mauritius	Third party multilateral organisation à Government of Mauritius	Internal HMG centre of excellence à Government of Mauritius	Public Finance Resource Centre à Government of Mauritius
Costs to be incurred by FCDO directly	£1.0 million – grant agreed bilaterally between the UK and Mauritius	£0.2 million – technical capacity building; estimate provided by possible implementing partner	£0.1 million - technical capacity building; estimate provided by possible implementing partner	£0.1 million - technical capacity building; estimate provided by possible implementing partner	£0.06 million - technical capacity building; estimate provided by possible implementing partner
Financial aid to governments	Yes – 100%	n/a	n/a	n/a	n/a
ICF eligibility	Yes	Yes	Yes	No	No
Disbursement mechanism and expected schedule	Non-budget financial aid / Disbursed by December 2025	Milestone payment made in arrears / Disbursed by November 2025	Payment made in advance (subject to multilateral requirements) / Disbursed by November 2025	Milestone payment made in arrears / Disbursed by November 2025	Milestone payment made in arrears / Disbursed by November 2025

Monitoring, Reporting and Accounting for Funds
Implementing partners will be asked to provide detailed reports on a quarterly basis to the BHC programme team, covering activities delivered in the preceding quarter; achievements against project level results frameworks; risks and issues; and detailed summaries of spend against activities, with comprehensive financial forecasting looking forward to the next quarter and the remainder of the financial year. Partners will be provided with templates for their reporting and guidance on how to provide the required level of detail to the BHC programme team, following the standards set by MMDP (and found by successive reviews to provide sufficient controls and risk mitigation).

As outlined above, Mauritius is (at the time of writing) undergoing a Fiduciary Risk Assessment, the objective of which is to understand the fiduciary risk environment for the financial aid component of the SPF-P’s year-one priorities. The FRA will assess public finance management systems, policies, and processes of key ministries responsible for delivery of the Taskforce (a priority for the climate pillar of the SPF). While the FRA was prompted by the selection of the financial aid delivery model for this component, the report and any recommendations for remedial action will doubtless be instructive to the programme team in monitoring and assessing value for money, best buys, and optimum delivery models, including for future years of SPF implementation.

Fraud Risk
Fraud risk is expected to be low, particularly in the SPF-P’s first year. Implementing partners are either trusted and pre-existing NGOs/CSOs, or high-profile multilateral organisations, or internal HMG centres of excellence/resources. Expectations of implementing partners around conduct and reporting on fraud risk will be made clear in the text of any/all agreements signed, and partners will be expected to report in detail on their fraud risk management and controls. In additional to reporting on fraud risk in quarterly written reports, partners will also be expected to report verbally to the programme team in formal monthly (and informal, more frequent) calls.

Trigger points for the return of funds will largely not be necessary because the vast majority of disbursements will be made in arrears, and only upon satisfactory completion of milestones by implementing partners. Should any milestones be missed, the programme team will be empowered to make decisions about subsequent disbursements to implementing partners.

Contributions by other international donors in the above areas of intervention are possible – in some cases desirable – but this will not be fully known until the inception phase commences.

Complementary Interventions/Activities – Other Programmes
SPF-P activities will be complemented by several other sources of programme funds, which will be responsible for implementing non-ODA eligible elements of the SPF, namely:

Development Infrastructure – technical assistance on offshore wind and rail infrastructure development	£0.48m	FCDO Green Cities/Infrastructure Programme (ODA)
Good Governance: / Support for establishment of an anti-corruption-focused National Crime Agency (NCA) in Mauritius; / Launch of an Economic Security Partnership (ESP) with deliverables; / Police Force capacity building.	£0.325m	Africa Directorate (AD) International Security Fund (ISF) allocation (non-ODA)
Defence – Developing a bilateral defence relationship and providing support to build Mauritian maritime security capability / accrediting a Non-Resident Adviser to facilitate defence engagement; / training by Royal College of Defence Studies; / training by UK Hydrographic Office; / capacity building in Exclusive Economic Zone management; / capacity building in Maritime Domaine Awareness.	0.255m	Ministry of Defence (MOD) allocation (non-ODA)

Management Case

This Management Case has been drafted in line with the steps outlined in the PrOF Business Case guide.

Management and Internal Governance
The SPF-P will again seek to use the management and governance structures adopted by the MMDP, which successive Annual Reviews and the Programme Completion Review found to be effective and proportionate. The SRO for the SPF-P will be the Head of Mission at the BHC – Paul Brummell, British High Commissioner and Head of the Indian Ocean Network. The PRO will be the First Secretary, Political, Programmes & Communications at the BHC, reporting directly to the SRO and accountable for the day-to-day management of the SPF-P. SRO and PRO responsibilities will be outlined in the authority letters that programme teams are required to issue by the PrOF. The PRO will oversee project managers who will have responsibility for day-to-day management and oversight of individual implementing partners. The approximate percentage full-time equivalent for key SPF-P management officials is outlined in the table below:

Position	Programme Role	%FTE estimate
Head of Mission	SRO	5%
First Secretary, Political, Programmes and Communications	PRO	30%
BHC UKBS/CBS	Project managers (x1 per intervention listed above)	10%

The SRO will chair a quarterly programme board, attended by the PRO and all project managers (BHC members of staff with responsibility for individual elements of the programme). The PRO, with London, will convene monthly meetings of a programme working group, the responsibilities of which will include preparing for the quarterly board. These management arrangements will allow FCDO teams to assess project performance, to respond to and manage risks, and to take decisions to escalate risks for action as and when necessary.

Logical Framework and Results Monitoring
The nature of the individual interventions comprising the SPF-P in 2025-26 mean that comprehensive logical frameworks will need to be compiled at the level of individual projects by implementing partners before delivery commences. Project level logframes will be blended into a programme level logframe to enable the SRO and PRO to track results at the level of strategic programme objectives, with a particular focus on the extent to which interventions are delivering against high-level pillars and sections of the SPF. This programme level logframe will be developed in due course as components move to the implementation phase.

Risk Monitoring and Management
The PRO will be responsible for opening and managing the programme’s risk register, in consultation with project leads and the SRO. Project leads will be given instructions on what this appetite means for decisions about project delivery, which should be made by the programme board as the body with overarching responsibility for programme delivery. Risk appetites in the seven key risk categories will be set as outlined in the table below, with the officer responsible for setting them:

Risk Category	Risk Appetite	Risk Rating	Owner	Summary of Key Risk (in given Category)	Mitigations
Strategy and Context	Receptive	Moderate	SRO	Government of Mauritius lacks capacity to meet required absorbative level of SPF-P spend and progress on SPF implementation is delayed or fails to be realised in UK priority areas.	SPF-P programme team and programme board to assess capabilities against deliverables in the project design and mobilisation phase; and programme team to ensure capacity building is a core objective of SPF-P interventions.
Policy and Programme Delivery	Receptive	Minor	SRO	FCDO lacks sufficient programme management resource and capacity to implement SPF-P fully and to meet PrOF requirements on reporting, monitoring and evaluation.	Programme board to ensure that each intervention has a named project lead/manager for the duration of each intervention and set out roles and responsibilities should be set out in writing from SRO/PRO to project leads.
Public Service Delivery and Operations	Cautious	N/A	SRO	N/A (comment: the SPF-P does not relate to delivery of consular services or the delivery of internal operations which relate to security, legal, technology, information, and property risks.)	N/A
People	Receptive	Minor	PRO	FCDO is not sufficiently resourced to respond flexibly to changing SPF priorities and lacks the technical capabilities (or the ability to source those capabilities from other HMG departments) to meet Mauritian expectations and objectives.	Programme board to ensure that each intervention has a named project lead/manager for the duration of each intervention; and designed interventions do not exceed programme team or wider HMG capacity to deliver and manage.
Safeguarding	Cautious	Moderate	PRO	Due diligence processes are not conducted with sufficient rigour to ensure that implementing partners have robust protections to guard against harm to beneficiaries in Mauritian communities or government.	Funding agreements clearly establish rules, requirements, and best practice for implementing partners on safeguarding; programme team will conduct robust due diligence processes to assess safeguarding practices of implementing partners and discuss remedial actions with them where necessary; and reporting templates have discrete sections on safeguarding and implementing partners are held to account robustly for spending decisions.
Financial and Fiduciary	Cautious	Moderate	SRO	Due diligence (prior to delivery phase) and results monitoring and evaluation (during and after delivery) are not sufficiently robust to ensure that implementing partners have not used funds for any purposes other than those outlined in agreements with FCDO and have not caused any unintended consequences impacting beneficiaries.	Programme board ensure thorough due diligence assessments and reports are delivered in line with the relevant PrOF guide; funding agreements clearly set out implementing partner requirements and expectations on financial reporting and use of funds; and project leads hold implementing partners to account through clear and regular reporting timetables and templates.

Management Evidence Base
These management arrangements have been considered in the context of the requirement to avoid unnecessary complexity. They are based on the management arrangements of MMDP, the precursor ODA programme, which largely functioned efficiently and successfully, as Annual Reviews and the PCR have shown. However, at the end of 2025-26, it is recommended that the FCDO programme team undertake a light-touch PCR which will make recommendations for the establishment of a further, multi-year ODA programme for SPF implementation (effectively functioning as a Mid-Point Review).