Business Case

Summary Sheet

Country Plan Summary: Through diplomatic, development, economic and business, policy and regulatory engagement we will deliver UK growth, climate, health, security, and consular priorities in South Africa. We will implement the new Growth Partnership delivering commercial wins for UK companies, both investors and exporters, and drive inclusive, sustainable growth that creates jobs and economic opportunities for both countries. We will also support SA in its ambitions for a Just Energy Transition, key to our global climate goals and unlocking growth opportunities.

Title: / South Africa: Economic Reform Accelerator
Programme summary: / The Economic Reform Accelerator will support the government of South Africa to deliver growth-enhancing economic reforms targeted at the binding constraints to growth. Through technical assistance and policy-focused research provided to senior policymakers in economic-cluster ministries the programme will address capacity bottlenecks in design and implementation of the government’s reform agenda.
What is the rationale for UK Aid spending?: / South Africa’s economy has grown at an average of 0.7% a year since 2015, far below population growth of roughly 1.5% per annum. As a result, per capita incomes have fallen over this period, while debt to GDP has rapidly increased, from 45% in 2015 to 80% in 2025. This has also led to worsening economic outcomes for the poorest in society, with the world’s highest levels of unemployment and inequality. / Key to addressing these challenges, which have left over 11 million people living under the international poverty line, will be delivering economic reforms to raise growth. The Government of National Unity (GNU) has committed to a pro-growth reform agenda to improve the business environment and raise investment. This includes the President’s flagship reform programme Operation Vulindlela, as well as other macroeconomic policy reforms to improve labour market regulation, fiscal management and industrial policy. / The Economic Reform Accelerator will work in partnership with officials leading on the reform agenda in South Africa, ensuring the work is demand-led and built around the country’s own priorities for unlocking economic growth. Ensuring these reforms are informed by a strong evidence base and learn from international best practice will not only unlock growth for South Africa, but will also increase export opportunities for UK firms in our largest trade partner in the continent and improve the business environment in a country where the UK is the largest foreign investor.
Programme Value: / £1.5m		Country/ Region or Sector: / South Africa
Department/Country Office confirmation of review processes		Reviewed by South Africa Portfolio Committee February 2026 prior to HoM approval
Contact name		James Beeson
Threshold for final approval of Business Case: / Head of Mission
Date of Approval of Concept Note:	dd/mm/yyyy	Name and role of Approver / Antony Phillipson, / High Commissioner
Date of Approval of Business Case:	dd/mm/yyyy	Name and role of Approver / Antony Phillipson, / High Commissioner
Programme Code:	AMP Start Date:	AMP End Date:
Overall programme risk rating:	Moderate

Strategic Case

The challenge
1. South Africa’s economy has grown at an average of just 0.7% a year since 2015. With population growth of around 1.5% this has led to declining per capita incomes, with real incomes in 2023 below those in 2007[1]. Prolonged economic stagnation has seen a decline in South Africa’s fiscal position leading to the country losing its investment grade credit rating in 2020. Public debt has risen from 31% of GDP in 2010 to 80% in 2025.
  [1] World Bank (2025). Driving Inclusive Growth in South Africa
2. Economic stagnation has worsened poverty outcomes and made it harder for the government to respond.[2] Unemployment and inequality levels are among the highest in the world and the IMF estimates[3] that 34% of the population live below the middle-income poverty line (over 21 million people) while the World Bank estimated in 2014 that over 11 million South Africans lived below the international poverty line – a number which has likely grown in the intervening decade.
  [2] World Bank (2025). Economic Update, Edition 15
  [3] IMF (December 2025). South Africa: Staff Concluding Statement of the 2025 Article IV Mission
3. South Africa’s business environment is constrained by a number of factors, including poor security, corruption and red tape that limits private sector dynamism and the entry of new firms, reducing competitiveness in product markets.[4] But at the heart of South Africa’s growth challenge lie two binding constraints: government capacity and spatial inequality.[5] Government capacity challenges stem from a mismatch between the service delivery requirements on the government, particularly at municipal level and through state-owned enterprises, and the capability of those institutions to deliver effectively. Meanwhile, the spatial inequality which is the legacy of the apartheid era leaves many of South Africa’s poorest households located far away from centres of economic activity, limiting their access to jobs and services.
  [4] Khan, A. (2023). Back to Office Report: South Africa, FCDO
  [5] Hausmann et al. (November 2023). Growth Through Inclusion in South Africa, CID Faculty Working Paper No. 434
4. Government capacity constrains public investment. Line ministries, municipalities and state-owned enterprises repeatedly underspend their capital allocations, reflecting the challenges they face in procurement and delivering vital infrastructure upgrades. Gross fixed capital allocation stands at roughly 15% of GDP; far below the government’s target of 30% by 2030 and below faster-growing emerging markets such as China (~40%), India (~30%), and Vietnam (~30%). A consequence of this is increasingly acute infrastructure bottlenecks, with energy, rail and port underperformance frequently cited as the biggest obstacles to doing business in South Africa.
5. Unless it addresses these challenges, South Africa will continue to see falling real incomes and growing numbers of people in absolute poverty. South Africa already has one of the largest social-grant systems among peers, costing nearly 3.7% of GDP and reaching almost 70% of households[6]. Increasing fiscal pressure from a lack of growth will make this harder to sustain, pushing many vulnerable households further into poverty.
  [6] IMF Article IV Staff Report, 2025
6. A lack of economic growth also makes it much harder for South Arica to tackle entrenched gender inequality. At 35%, the female unemployment rate is well above that of men (29%), limiting women’s economic empowerment and leaving them more exposed to any reduction in the government’s social safety net as fiscal pressures increase.
The opportunity
1. While South Africa’s challenges are formidable, the current development bargain in South Africa presents an opportunity. As the World Bank’s recent Growth for Inclusion report states, “The new political context emerging from the May 2024 elections provides a unique opportunity for South Africa. The alignment of economic and politi­cal incentives, in the sense that improving the econ­omy is essential for gaining political power, offers a platform to launch a decisive transformation pro­cess, even if there is not yet an agreement on which economic reforms to implement. Such alignment was key to the successful economic transfor­mation of China in the early 1980s, Vietnam in the late 1980s and 1990s, Poland in the 2010s, and India in the early 2020s. Those successes were anchored on “a development bargain, whereby the country’s elites shifted from protecting their own positions to gambling on a growth-based future.”[7]
  [7] World Bank (2025). Driving Inclusive Growth in South Africa
2. South Africa’s Government of National Unity (GNU) has a clear priority to restore economic growth through addressing infrastructure bottlenecks, raising investment and improving the business environment. This represents an acceleration of the growth-friendly agenda from the previous administration, under which the Economic Reconstruction and Recovery Plan made raising infrastructure investment and improving the business environment key priorities[8].
  [8] Government of South Africa (2020). Economic Reconstruction and Recovery Plan
3. Operation Vulindlela (OV), President Ramaphosa’s flagship economic reform agenda, has shown the commitment of the government to restoring growth. Now in its second phase, OV has used a cross-government approach to tackle systemic policy challenges with a focus on network industries and has been welcomed by business as demonstrating tangible success across its priority areas.
4. This work has created a track record of success on implementation, which has long been a challenge in South Africa. Recognising the political challenges of implementation of difficult reforms, it has used the power of the Presidency and National Treasury to drive through change at the highest levels, helping to overcome departmental-level challenges to implementation.
5. Recent optimism around South Africa’s economic outlook, including an upgrade by S&P in November 2025, have shown the reform agenda is beginning to pay off. This has reinforced the calculation that delivery of these reforms is closely aligned with retaining political power, incentivising a focus on service delivery and speeding up the pace of reform, strengthening the hand of the GNU.
6. Ensuring South Africa makes the most of this dynamic, to raise the underlying growth rate, will be crucial to tackling South Africa’s development challenges. Through reversing de-industrialisation and encouraging broad-based growth, South Africa will create the jobs needed to address its unemployment challenge. At the same time, higher growth rates will strengthen its fiscal position, reducing debt as a share of GDP and borrowing costs, giving it the fiscal space to maintain its extensive social safety net.
Partnership with the UK
1. The UK and South Africa work closely together under the UK-SA Growth Partnership, which was launched by the Foreign Secretary at the UK-SA Bilateral Forum in November 2024. Half of all the UK’s investment in Africa is in South Africa (£24bn), which is also its largest trading partner (£12bn annually); improvements in South Africa’s business climate and stronger economic growth will have direct benefits to the UK as well.
2. As part of this co-operation, the UK already works closely with South Africa on economic policy making. This includes close work between UK and South African policy officials as members of the G20, peer-to-peer collaboration between the Bank of England and South African Reserve Bank as well as between respective Treasuries, and a programme of technical assistance under the International Economic Partnership programme (which ends in the coming FY).
3. The Economic Reform Accelerator will build on this close relationship with senior government officials to ensure support is driven by South African policy makers to help them deliver their priorities for economic reform. This will ensure the support provided under the programme will be demand-led, focused on the most pressing policy priorities to maximise the impact of the programme.
4. The design of the programme captures lessons learned from the International Economic Partnership. Foremost amongst these is the close work with policy officials which has driven the most successful workstreams under the previous programme. Bringing in policy makers to the design of the intervention and providing them with ownership of the work done ensures the work is valued and used in policy making. It also ensures the speed and responsiveness of the previous programme is maintained, which encouraged policy makers to approach us for further support where there were internal capacity constraints.
5. Working with government to deliver these reforms will ensure our development partnership with South Africa is focused on delivering system reform and strengthening the capability of the government of South Africa to improve economic outcomes, rather than stepping in to provide service delivery. Faster economic growth that reduces poverty, including for women & girls, will be unlocked through:
  1. An improved evidence base for policy makers, providing them with the information they need to shape policy in line with South-African-focused research alongside international best practice;
  2. Faster implementation of policy implementation through supporting key senior officials in delivering their work, addressing bottlenecks in government policy delivery;
  3. Providing platforms, both public and private, for policy debate to help build policy consensus across government departments and with the wider public.
6. SA-TIED, focussed on strengthening the evidence base, will be carried out along eight workstreams:
  1. Strengthening National Treasury’s Secure Data Lab;
  2. Public revenue mobilisation;
  3. Poverty, inequality and labour market outcomes;
  4. Macro-fiscal analysis and policy modelling;
  5. Food energy and water;
  6. Reform implementation;
  7. Public expenditure.
7. Meanwhile the technical assistance will be demand-led, focused on the work of South Africa’s government to address the country’s structural challenges. This will include work that informs the development and implementation of Operation Vulindlela, work to strengthen infrastructure budgeting and procurement, labour market reforms and its engagement with international issues, for example trade policy.
8. Both areas of work build on lessons learned from a predecessor programme, the International Economic Partnership. The work done under this programme highlighted the strengths of providing flexible technical assistance to senior policy makers to help deliver policy change. The focus of the International Economic Partnership was in strengthening South Africa’s approach to its international policy agenda, particularly around its G20 Presidency. This new programme will have a stronger focus on domestic economic reform given the opportunity to support delivery of much-needed structural reforms.
9. This programme will be complementary to the UK’s broader economic development work in South Africa. The Economic Reform Accelerator will focus on the centrally-led reform agenda, raising the underlying growth rate and improving macroeconomic stability. Alongside this, our Urban Resilience programme works to tackle spatial inequality and economic exclusion, while our SME Invest work focuses on ensuring growth is jobs-rich and creates a dynamic small business sector. In this way, the UK will work to raise the growth rate and ensure a more equitable distribution of this growth.
10. By working in this way, this programme is closely aligned with the UK’s Modern Partnership approach. We will use both UK and international expertise to maximise the work done by South African policy officials and Ministers, ensuring this supports South Africa’s priorities and maintains South African leadership on policy decisions. Responsive, demand led support will ensure South Africa strengthens its own economic systems, and our close work with policy officials will allow us to tap into he appropriate expertise within the UK system where needed.
Impact and evidence base
1. There is an extensive evidence base to support the broad focus of South Africa’s reform agenda. The Harvard Growth Lab conducted a landmark review on the binding constraints to South Africa’s growth in collaboration with National Treasury (Hausman et al 2023) which fed into the priorities within Operation Vulindlela and the wider work done by the economic cluster of government departments.
2. Independent modelling by South Africa’s Bureau for Economic Research has found that full implementation of OV reforms could raise the long-run growth rate from 2.2% to 3%, as improved rail and port performance increases exports while energy reforms boost investment, with improving consumer confidence raising household consumption.[9]
  [9] Haverman, R. Bureau for Economic Research (2024). Turning the 3% growth fairy tale into reality
3. Supporting government-led, pro-growth national policy reform is assessed as a ‘great-buy’ in the FCDO’s review of ‘best-buys’ in economic development. FCDO analysis finds that the success of this type of intervention depends on “engaging with Government and getting to know how different departments function, building relationships with key players. Success depends on our influence and the quality of our local knowledge...as well as the quality of the advice/TA”. By working directly with the senior officials tasked with delivering the government’s reform agenda, the programme will maximise the impact of our technical assistance and ensure it is focused on live policy discussions.
4. This work will also build on the UK-SA International Economic Partnership, an existing programme of technical assistance to the government of South Africa focused predominantly on international economic policy making but also providing some support to domestic economic policy formation. The last two annual reviews of this programme (now in its final year) have found it to be a high performing programme (scoring A+ in 2024 and 2025) with strong traction in government departments, and the programme will build on these strong links with government policy makers which are so crucial to success.
5. The programme will learn lessons from this predecessor programme[10]. This will include clear scoping of work to prevent ‘mission-creep’, remaining focused on the main policy challenges facing South Africa. Crucial to delivering this will be governance structures to ensure effective oversight of programme direction and ensuring a clear division of responsibilities within the programme management.
  [10] FCDO (2025). International Economic Partnership Annual Review, DevTracker reference 300985.
Other donors
1. There are a number of other donors working to support South Africa’s economic policy making. Most support has a sector focus and is not covered here, but similar programmes to the Economic Reform Accelerator include:
2. The World Bank provides significant support to South Africa, including a $1.5bn development policy loan in 2025 to support infrastructure investment and a programme-for-results intervention supporting energy and municipal reform work. This is alongside some technical assistance provided by the bank, with experts working closely with parts of South Africa’s government, predominantly focussed on the energy and infrastructure sectors.
3. The OECD have a joint-work programme with South Africa, part of which is focussed on fostering inclusive growth and competitiveness. The work under this area includes policy briefs to provide recommendations for the government on economic policy, surveys to provide more granular data on challenges, and support to improve product-market competition.
4. The additionality of the proposed programme alongside these elements of work is its flexibility and speed of response, which stakeholders within the Government of South Africa have repeatedly highlighted as a strength of the International Economic Partnership.
Gender equality
1. The programme will actively promote gender equality. Drawing on expertise at post from the Social Development Advisor (SDA), the programme will continue workstreams established in the International Economic Partnership with the Planning Commission and learn lessons from challenges in mainstreaming gender in wider macroeconomic advice. Work to do this will include:
  1. Continuing collaboration with the National Planning Commission to ensure gender is mainstreamed into the work of the Medium-Term Development Plan, with a focus on identifying suitable indicators to capture the impact on gender. This work is also informing the National Development Plan 2030, providing support to the National Development Commissioners and DPME officials in mainstreaming gender in their work
  2. Strengthening the inclusion of gender impacts in macroeconomic policy formation, including within the technical assistance provided by the programme. This has had mixed results in the International Economic Partnership and lessons learned will be incorporated into the design of the new programme to capture this, involving the gender advisor proactively at an early stage to ensure these considerations are better reflected in the support provided.
2. Social development issues, including gender, disability and youth impacts, will also be considered during the design phase of interventions under the flexible technical assistance element. By including the SDA in the review of terms of reference for areas of work the programme will capture these considerations at the design phase and ensure these are mainstreamed in the work of the programme.
Safeguarding considerations
1. Effective mitigation of safeguarding risks – environmental, social and governance as well as sexual harassment and exploitation - will be managed throughout programme delivery. A thorough due diligence process on all implementing partners including their capability and commitment to safeguarding will be assessed as part of the mobilisation process. Safeguarding risks have been considered and included in the management case.
2. Partners are required to have systems for ensuring safeguarding, to eliminate or minimise the risk of actual, attempted or threatened exploitation, abuse and harassment (including sexual exploitation and abuse and sexual harassment (SEAH)). This includes rigorous systems and processes for ensuring the prevention of safeguarding incidents both within organisations and their downstream partners as well and a clear and robust incident response process.
Prevention of fraud and bribery and sanctions compliance
1. Suitable clauses will be including in all implementing partner contribution agreements to establish, maintain and enforce, policies and procedures that adequately ensure compliance with the relevant requirements and prevent the occurrence of fraud and bribery and compliance with the UK’s sanctions regime.
2. All implementers will be required to keep appropriate records of its compliance with its obligations for the prevention of prohibited acts and to make such records available to FCDO on request.
Climate and environment
1. The programme will focus on macroeconomic reforms and not have a specific focus on climate policy. However, in raising overall growth it will create the economic conditions to support the economic diversification and job creation needed to mitigate the phase-out of coal, gas and combustion engine industries.
2. Where workstreams do include a climate element, for example on some OV reforms and the climate workstream under SA-TIED, the BHC’s climate advisor will be included in the design of relevant terms of reference and activity happening under these interventions.
3. The programme will be fully aligned with the requirements of the Paris Agreement and the programme team will ensure all delivery partners follow the necessary environmental protection safeguards including impact and risk assessments.
Risk
1. The overall programme risk is judged to be moderate. This reflects the political risks in the outer years given the importance of the existing political commitment to delivering the reform agenda this programme will support. A full risk register is set out in the management case. The two major risks to delivery of the programme are:
  1. A loss of consensus around, and/or political will to deliver, the economic reforms this programme will support. The threat to the political bargain outlined in the ‘Opportunity’ section above would undermine the alignment of incentives crucial to delivery of this programme.
  2. A lack of engagement with the programme from policy makers who chose not to take up the offer of support would make it much harder to secure the senior-level buy-in to the programme which is necessary to ensure a genuine partnership approach and ensure the programme is demand-driven.
Appraisal Case

The Economic Reform Accelerator will work with South Africa’s government to support the delivery of its ambitious reform agenda to unlock economic growth. By providing senior officials the tools they need to deliver these reforms at the fastest possible speed this will make the most of the existing development bargain in South Africa, raising the underlying growth rate and improving the business environment.
Theory of change
The diagram below sets out the theory of change underpinning the programme:

More inclusive economic growth
Greater fiscal sustainability
Stronger evidence base for policy decisions

Policy briefs and research products
Outputs
Outcomes
Impact
Technical assistance to policy makers
Improved policy formation
Faster economic growth
Policy-led research
Faster reform implementation
Platforms for policy debate to shape decisions
Cross-government policy consensus

The causal pathway to unlocking higher growth flow rests on the need to turn academic research in broadly accepted areas of reform into policy specific advice which is then agreed across government and implemented effectively.
Assumptions underpinning theory of change
1. Input to output
  1. Academics are willing and able to work closely with South African government officials to produce policy-relevant research at a speed useful to government officials
  2. The delivery mechanism is able to recruit appropriate economic expertise with relevant international and South African-specific expertise
2. Output to outcome
  1. There is demand from government for more policy-tailored evidence to inform decision-making, and senior officials and ministers are guided by evidence in formulating policy
  2. Policy makers are open to working with UK-provided technical assistance as part of policy formulation
  3. Supporting senior officials in the design of policy will alleviate bottlenecks preventing policy implementation, increasing the capacity of initiatives such as OV to implement reform.
  4. Externally led round tables led by subject matter experts will help build cross-government policy consensus
  5. Implementation of policy is held back by bottlenecks within GoSA
3. Outcome to impact
  1. Government-led structural reform is needed to raise South Africa’s underlying growth rate.
  2. Raising economic growth remains the guiding principles of government policy
  3. Structural reform will ensure South Africa’s growth is more broad-based, sharing the returns to growth across a broader range of industries
  4. Structural reforms will increase fiscal sustainability, strengthening the ability of the GoSA to provide social support programmes for the most vulnerable in society.
Evidence underpinning the theory of change
Evidence supporting this theory of change is set out in the strategic case above, but the strength of evidence for the assumptions above are set out in the table below:
Assumption	Strength of evidence
There is a need for more policy-tailored evidence to inform decision making	Strong. National Treasury continue to drive the work of SA-TIED which focusses on producing evidence for policy-makers. Since the last phase of SA TIED, a second directorate within National Treasury have chosen to contribute funding to increase their influence over the focus of the work, and SARS have also agreed to co-fund, reflecting their value of the work done.
Policy makers are open to working with UK-provided technical assistance as part of policy formulation	Strong. Demand for support through IEP and other offers from the UK under our growth partnership have exceeded the availability of resource for support, highlighting a high level of appetite and confidence in partnering with the UK and involving UK expertise in policy making.
More accessible research, tailored to the needs of policy officials and emphasising practical advice will improve the use of evidence within government	Mixed. A review of SA-TIED phase II found that policy influence “tends to occur through dialogue and applied analysis rather than [academic] citations, highlighting the importance of structured engagement and translation products” which suggests the extra work done to make research more accessible is worthwhile, but this is only limited evidence.
Senior officials and ministers are guided by evidence in formulating policy	Strong. South Africa’s reform priorities already draw heavily on evidence to inform their areas of focus. Close work between National Treasury and the Harvard Growth Lab show a willingness to engage with the evidence, while experience through the International Economic Partnership has shown, for example, strong engagement with academics in the DPRU to inform labour market policy. Co-funding by the Government of South Africa for SA-TIED shows an institutional commitment to involving policy makers in evidence generation and use.
Externally-led round tables led by subject matter experts will help build cross government policy consensus	Limited. There is little beyond anecdotal evidence that using externally-led policy discussions will help develop a cross-government consensus on policy decisions.
Raising economic growth rates and improving the business environment remain the guiding principles of government policy	Strong. The government has made repeated public statements on its commitment to a pro-growth reform agenda. Analysis such as that by the World Bank cited above highlights the existence of the ‘development bargain’ to align political incentives with development needs.
Government-led reforms can address the binding constraints and raise South Africa’s underlying growth rate.	Strong. There is substantial evidence that the government has the levers to tackle the constraints to growth. Alongside reforms to the network industries highlighted in the strategic case, this is also the case for labour market[11], fiscal[12] and industrial policy[13].
Economic growth translates into poverty reduction	Strong. South Africa’s structural challenges have undermined its previously diversified economy. By addressing these, the programme will support broad-based, inclusive growth in South Africa which creates more jobs. Growth will also strengthen the country’s fiscal position, protecting the extensive social safety net that protects the most vulnerable in the country.
[11] Bhorat, H & Cheadle, H, (2009). "Labour Reform in South Africa: Measuring Regulation and a Synthesis of Policy Suggestions", University of Cape Town
[12] Khalid, Asma and Nguyen, Anh D. M. (2025). South Africa’s Fiscal Framework: Challenges and Options for Reform. IMF
[13] Bhorat, H., Cassim, A., Hirsch, A. (2014) Policy Co-ordination and Growth Traps in a Middle-income Country Setting: The Case of South Africa. WIDER

Options appraisal
1. The options for delivery are considered below. These are assessed against the following criteria:
  1. Value for money (VfM): the extent to which the intervention maximises the impact of the activity proportionate to the resource required.
  2. Modern Partnership: how much the option delivers a genuine partnership and in-country ownership which supports the delivery of South Africa’s reform priorities and ensures close involvement in policy making.
  3. Capacity, Capability & Delivery Risk: the extent to which the option provides the expertise and flexibility to respond to the requirements of the government of South Africa.
2. Option 1 – Do Nothing. The FCDO would not provide support to South Africa’s economic reform agenda. In this scenario, reforms would still go ahead but at a slower pace and with less input from subject matter experts. The evidence base for reforms would continue to grow but at a slower rate and with fewer products designed specifically for consumption by policy makers.
  1. Value for Money: Very poor.
     Generates no return on the identified reform opportunity. Fails to address binding constraints to growth, creating costs of inaction (slower reforms, missed investment, weaker fiscal outcomes). Misses the window of opportunity to deliver reforms and does not improve the business environment. Slower growth also undermines returns to other elements of the BHC’s economic development programming.
  2. Modern Partnership: Weak.
     Signals withdrawal at a moment when reform momentum and government demand is high. Risks eroding trust and credibility, reducing the UK’s ability to shape economic governance and weakening bilateral cooperation. Does not support co‑design or shared ownership.
  3. Capacity, Capability & Delivery Risk: N/A.
     While it avoids delivery risk, it creates significant strategic and political risk, as bottlenecks in reform capacity remain unaddressed. Missed opportunity to build institutional capability and to demonstrate UK responsiveness. Potential reputational risk if partners expect UK support.
3. Option 2 – Technical Assistance Only. The FCDO would provide technical assistance (TA) to policy makers, strengthening their capacity to deliver and implement policy.
  1. Value for Money: Good.
     TA‑only is relatively low‑cost and can deliver targeted advisory support efficiently. Offers good VfM where the binding constraint is implementation capability and where high‑quality expertise can shift policy outcomes. Crucial to VfM will be the quality of the relationship with senior decision makers in government.
  2. Modern Partnership: Good.
     Enables close working with government counterparts, supports co‑production of reforms, and builds trust through responsive problem‑solving. However, not including support to SA-TIED (which was funded under the International Economic partnership programme) may negatively impact the UK’s relationship with National Treasury.
  3. Capacity, Capability & Delivery Risk: Moderate.
     TA is relatively straightforward to deliver and commercially available. Delivery risk centres on: availability of suitably senior experts; engagement with policy officials and strength of experts’ relationships with government.
4. Option 3 – Technical Assistance + Policy‑Relevant Research. The FCDO would provide technical assistance alongside support to the generation of policy-focused research disseminated in products designed for policy officials.
  1. Value for Money: Good.
     Combining TA with applied research improves the evidence base and informs prioritisation. This results in more cost‑effective interventions over time, especially where reforms require diagnostics, modelling, or deeper analysis. Slightly higher cost than TA‑only, but typically better VfM in complex reform environments. Through co-funding research we can extend the reach of a pre-existing research agenda, delivering more activity at a quicker pace than without UK involvement. This approach will benefit from economies of scale while retaining oversight of research direction and priorities.
  2. Modern Partnership: Very good.
     This approach enables co‑creation of knowledge, supports partner‑led decision‑making, and deepens institutional partnerships. It helps embed reforms in systems rather than individuals, strengthens dialogue, and shows the UK’s commitment to National Treasury’s own research agenda. This aligns very well with modern partnership principles. Our close work with the government to understand their priorities here will also help us identify other avenues through which UK expertise could provide support.
  3. Capacity, Capability & Delivery Risk: Moderate
     Alongside the risks in option 2, this option carries further risks to delivery including: coordinating research with fast‑moving policy needs; ensuring government access and buy‑in to evidence; ensuring appropriate expertise of researchers.
5. Summary Comparison
Option	VfM	Modern Partnership	Delivery Risk
1. Do Nothing	Very poor	Weak	N/A
2. TA Only	Good	Good	Moderate
3. TA + Research	Good	Very good	Moderate

Option 3 is our preferred approach, offering a balance between providing technical assistance into policy makers to help them respond quickly to opportunities to deliver policy change, while also strengthening the policy-relevant research base from which officials can draw to inform decisions.
Delivery model
1. Technical assistance: there are three feasible delivery models for technical assistance: in-house FCDO expertise posted out to South Africa; directly recruited country-based staff seconded into ministries; or an externally procured consultancy.
  1. In-house expertise. This would provide a much clearer UK-link to the expertise, allowing UK civil servants to work closely with South African counterparts to deliver policy change. Delivery chains would be shorter, strengthening oversight and influence. However, to maximise impact FCDO experts would need to be based in South Africa, raising project costs and reducing flexibility to move support between policy agendas as priorities shift. Relationships would also take time to build, and seconded experts would have limited South Africa specific knowledge.
  2. Seconded country-based staff. Recruiting local South African economic expertise will help ensure the technical assistance understands the domestic context for economic policy making and would allow for a cheaper, more responsive long-term secondee into National Treasury policy teams. As above, this approach would limit flexibility between areas of support and to respond to changing priorities given the need to recruit and retain experts on longer contracts.
  3. External consultancy. This would give a much more flexible approach, bringing in relevant expertise to match priorities as they evolve and bringing in greater South Africa specific knowledge and stronger networks (if used as a criterion in procurement). This approach would also be easier to scale. However, oversight of support will be harder given the reliance on an external body, the UK links will be less clear, and there is the potential for scope creep as the implementing partner influences programme priorities. The resource required to procure an external delivery agency would likely be disproportionate for a one-year TA programme unless it could be procured through a framework agreement.
2. Breaking down the appraisal above to consider the different pros and cons of technical assistance, both in-house expertise and consultancy would give a lower value for money reflecting their higher costs, while using the consultancy approach would reduce delivery risk given the flexibility of using a consultancy model to respond in an agile way to government priorities and areas of engagement with the government of South Africa:
Option	VfM	Modern Partnership	Delivery Risk
2a. In-house TA	Moderate	Good	Moderate
2b. Locally recruited TA	Good	Good	Moderate
2c. Consultancy-delivered TA	Moderate	Good	Low

1. Given the respective advantages and disadvantages of the options above, our preferred option is to make a final decision on delivery mechanism in partnership with the government of South Africa, discussing the appropriate mechanisms based on their specific priorities once the programme moves into the delivery phase. This will allow us to ensure government buy-in for the chosen model, which will be crucial to traction and therefore ensuring value-for-money.
2. Research: There are two feasible options available; either delivering an FCDO-led, stand-alone research programme, or partnering with a pre-existing initiative.
  1. Creating our own research programme would give the BHC greater control over research priorities and direction. However, the relatively small level of funding available would mean a fairly limited scope of research, which may make it harder to secure close buy-in from the government of South Africa for policy makers to engage with the process and ensure research was being used. It would also risk being seen as duplicative or competing with the National Treasury’s preferred research programme (see b).
  2. Joining with an existing initiative would ensure our support for research achieved economies of scale and buy-in from the government of South Africa. The SA-TIED (Southern Africa: Towards Inclusive Economic Development) initiative is led by South Africa’s National Treasury and is a priority initiative for their senior leadership, ensuring the intervention is country-led and informed by policy priorities. National Treasury are doubling their funding to SA-TIED compared to the last phase, reflecting their strong commitment to this element of the programme, and have asked the UK to partner with them. The advantage to the SA-TIED programme of UK participation is that the UK can mobilise funding quickly relative to other funding partners, supporting a key priority of the programme which is to increase the pace of reform implementation.
3. Given the clear benefits of partnering with the government of South Africa, our preferred option is to participate in the SA-TIED initiative.
Value for money
1. There are a number of factors which drive value for money under the approach outlined below:
2. Economy – Minimising costs while maintaining quality
  1. Using a competitive tender to appoint a delivery partner where external consultancy is used for the technical assistance will ensure costs for this element of the programme reflect market rates and provide market discipline for implementing partner costs. Close work with the government of South Africa and the British High Commission may, for example, allow the programme to use venues provided by these institutions for free, further reducing costs.
  2. The SA-TIED element will be delivered by UNU-WIDER, a UN organisation which has pre-agreed cost ceilings and rates for expertise. As an internationally respected research institution it can draw on a wealth of development economist expertise, and share insights from similar programmes it is running in other countries. The participation on National Treasury also ensures space for the Secure Data Facility is provided free of charge, as well as officials’ time in research participation and free access to crucial data.
3. Efficiency – Converting inputs into outputs at the lowest feasible cost
  1. Partnering with SA-TIED to deliver research elements will leverage co-funding from the government of South Africa, the EU and potentially other partners to deliver economies of scale. This will spread the costs of commissioning and administrating research, ensuring these fixed costs are spread across a wide range of research work.
  2. Working closely with the government of South Africa will provide an ongoing check that the work being done by delivery partners to provide research and technical assistance is focussed on the right questions and being done in a way which is most accessible to policy officials. This will ensure that outputs produced by the programme are closely aligned to policy-makers’ needs, reducing unnecessary work.
4. Effectiveness – Delivering the intended outcomes and impact
  1. A genuine partnership approach with the government of South Africa, bringing officials into discussions on delivery mechanisms for respective elements of the programme, will ensure the support provided is most effective at delivering the support to policy makers.
  2. Maintaining a high quality of technical assistance and research, delivered by subject matter experts with a strong understanding of the South African context, is crucial to ensuring the work produced genuinely improves South Africa’s evidence base. Quality assurance by BHC advisors and South African officials will allow the programme to respond appropriately where work falls below the expected standard.
  3. Ensuring implementing partners for the technical assistance have strong networks into the government of South Africa, and is well placed to provide rapid, in-country support to officials will ensure that support is genuinely useful for, and responsive to, officials.
  4. A focus on country-led support with clear ownership by South African policy officials will ensure the outputs of the programme genuinely make a difference to the quality and speed of economic reform in South Africa.
  5. Conversations with government partners over their priorities will also, as discovered through the International Economic Partnership, identify other areas where the UK and South Africa can work together on economic policy, further strengthening our partnership approach and maximising VfM from the intervention.
  6. An agile and adaptive approach will ensure the support can respond to emerging opportunities to advance reforms and a changing political landscape.
5. Equity – A fair distribution of benefits from the programme.
  1. Ensuring that distributional impacts are considered as a part of evidence generation on policy advice will help strengthen these considerations in South Africa’s policy formation;
  2. A specific workstream on mainstreaming gender into the National Development Plan will strengthen gender considerations in economic planning and build capability and awareness within the Planning Commissioners of South Africa.
  3. SA-TIED will include targeted inclusion targets for the commissioning of research, encouraging co-authorship of work with marginalised groups.

Commercial Case

1. To maximise results and value for money, the programme will use a flexible and adaptive approach and robust programme, financial and risk management processes and systems. An adaptive programme should maintain the ability to change activity (beneficiaries/methodology, etc.) to adjust to different scenarios and reflect learning. This flexibility has been crucial to success of the International Economic Partnership.
2. The preferred delivery option is as follows:
  1. Research: Memorandum of Understanding with UNU-WIDER
  2. Technical Assistance: Combination or selection of a commercial contract with delivery partner and seconded expertise.
3. Each of these routes is considered in turn:
Memorandum of Understanding
1. The research element of the programme will be delivered through a Memorandum of Understanding (MoU) with UNU-WIDER to support the Southern Africa – Towards Inclusive Economic Development (SA-TIED) programme. This will support the launch of phase III of the SA-TIED initiative, which UNU-WIDER have been delivering the programme since its inception.
2. Performance management: A logframe will be agreed with UNU-WIDER, in collaboration with the other funding partners, led by National Treasury who will provide the majority of the funding (see financial case). KPIs will include delivery of research and policy briefs across the agreed workstreams, with regular reporting on a six-monthly basis provided by UNU-WIDER against these targets. Given the pooled fund approach to programme delivery, FCDO-specific results will not be separated from the overall programme impact and will need to be attributed on a pro-rata basis.
3. Management of the MoU will be done through the BHC South Africa programme team, supported by the Programme Assurance Team. Governance structures of the programme will include a steering group (National Treasury, SARS & UNU-WIDER) which will hold accountability for delivery of the programme, with the BHC sitting on the Advisory Group which will provide strategic direction to the programme, quality assurance on programme outputs (with a focus on policy-relevance) and support policy uptake by government.
4. Value for Money: In line with the VfM considerations outlined in the appraisal case, the MoU approach will ensure cost transparency as funding is drawn down ahead of spend, in line with guidance on UN MoUs. This allows for full cost transparency and provides an opportunity to challenge cost considerations. The close involvement of National Treasury and SARS – who will both be providing in-kind resources (data, office space, officials’ time) as well as direct funding, will ensure strong buy-in from the government – a critical element in realising efficiency and effectiveness considerations.
5. Risk: The UK has been a partner of SA-TIED since 2022, and the risks to this element of the programme are low, having worked with the delivery partner previously. However, risks to delivery remain and are outlined in the table below:
Risk	Gross Likelihood	Gross Impact	Mitigation	Residual Likelihood	Residual Impact
Funding constraints – Programme unable to secure minimum viable funding levels	Unlikely	Major	Engage with key funders, including National Treasury to secure programme funding.	Low	Major
Reduced demand for evidence-based input at policy level	Possible	Major	Strengthen policy engagement strategy, maintain high-level relationships, focus on policy areas where demand for evidence is high.	Low	Moderate
Scope creep – Programme/workstreams expand beyond agreed focus	Likely	Minor	Strong engagement with programme through both formal and informal channels to monitor workstreams and commissioned research.	Possible	Minor
Data-sharing agreements not finalised, limiting data availability	Unlikely	Moderate	Provide support to UNU-WIDER in engaging with relevant institutions to secure relevant data-sets.	Low	Moderate

Commercial contract
1. Experience from delivering technical assistance through the International Economic Partnership demonstrates the value of using a capable commercial supplier able to deploy specialist economists, policy advisers, and researchers at pace, while providing strong programme management structures. A competitive tender process will invite bids from interested suppliers; South Africa has a competitive economics consultancy industry with strong local expertise. The chosen supplier/s will need to understand the political economy in South Africa, have good links with government entities, and have the ability to deploy quickly in-country.
2. The Terms of Reference will be developed in partnership with National Treasury and other Government of South Africa stakeholders to ensure the work focuses on priority areas of policy reform and strengthens ownership by the government of South Africa. Evaluation of bids will focus on the extent to which the responses proposed represent a feasible strategy to provide flexible technical assistance to policy officials and demonstrate the appropriate mix of expertise and links into the government of South Africa.
3. We expect the contract to include an inception phase in which the supplier will test the proposed delivery plan. Agreement to continue to implementation will be dependent on HMG’s satisfaction with the delivery plan and budget set out after the inception phase.
4. Performance management: The supplier/s will develop key performance indicators, for testing during the inception phase and adapted as necessary in agreement with BHC South Africa and National Treasury for the implementation phase. BHC South Africa will authorise payments based on evidence that the delivery partner/s are achieving the planned outputs. BHC South Africa will review progress quarterly, alongside financial reports.
5. BHC South Africa will monitor the supplier’s performance against the terms of reference and key indicators for quality, timeliness and cost. This will be done through quarterly reports and steering committee meetings involving the supplier, BHC South Africa and representatives from the Government of South Africa. The contract will include break clauses in the event of substantive changes to programmes requirements or to address poor performance. The procurement process will ensure good value for money in terms of costs, quality and effectiveness.
6. Value for money: The main cost-drivers of this element of the programme will be the fee rates and travel expenditure of the experts providing the technical assistance. Using a competitive tender to procure the inputs for this element of the programme will ensure input costs reflect competitive market rates. From previous tenders we expect high levels of interest from the market for the programme, fostering competition. KPIs will be agreed through inception, in line with the theory of change and allowing BHC South Africa to monitor both the quantity and quality of delivery. Building in flexibility will allow the programme to adapt to changing reform priorities and policy challenges effectively.
7. Risk: While using an implementing partner to deliver technical assistance to policy officials in the government of South Africa is relatively low risk and uses a tried-and-tested model of delivery in South Africa, some risks to delivery remain:

Risk	Gross Likelihood	Gross Impact	Mitigation	Residual Likelihood	Residual Impact
Lack of engagement from government limits policy impact	Likely	Major	Early engagement with policy officials to strengthen engagement with the programme, strength of government networks a selection criterion for implementing partner	Unlikely	Major
Contracting limits flexibility and responsiveness to demand	Possible	Moderate	Include clear change control mechanisms and adaptive‑delivery provisions, reflecting ERA’s flexible approach.	Unlikely	Minor
Scope creep of support into broader range of policy areas	Likely	Moderate	Active oversight from BHC to monitor delivery by implementing partner and proactive engagement in workstream development.	Possible	Minor
Limited market appetite reduces competition	Possible	Moderate	Strong early market engagement, clear scope and realistic timeframes for delivery.	Unlikely	Minor
Over‑reliance on key personnel creates turnover vulnerability	Possible	Minor	Require suppliers to present succession plans and alternative resourcing options.	Unlikely	Minor

Seconded expertise
1. As and where conversations with the government of South Africa identify longer-term seconded experts as a more suitable delivery mechanism of support, where using a commercial arrangement would prove expensive. This would use BHC recruitment processes to hire relevant individuals who would then be seconded into National Treasury.
2. Performance management. Oversight of performance would be the responsibility of the relevant South African government department, with a clearly designated line manager and objectives against which performance would be measured. Regular keep in touch meetings with the BHC with both the secondee and their line manager would provide BHC oversight of the work.
3. Value for money. Directly hiring well qualified individuals is a more cost-effective route to providing longer-term expertise embedded in National Treasury, compared to paying hourly/daily rates through consultancies.
4. Risk. We have seconded individuals into National Treasury previously and have found this mechanism to be effective. The reliance on one individual to delivery is a risk, however, as if this individual underperforms or withdraws from the agreement, it will be harder to replace.

Financial Case

The funding for the programme will be split between technical assistance and support to SA-TIED. The majority of the funding will go towards technical assistance, reflecting the need for this to be a minimum viable size to be cost-effective given the costs of using a consultancy. The remaining allocation to SA-TIED is front loaded to enable to the programme to start as soon as possible, while other donors mobilise funding later in the programme.

Component (£m)	FY25/26	FY26/27	FY27/28	Total
SA-TIED	£0.5	£0.0	£0.0	£0.5
Flexible TA	£0.0	£0.0	£1.0	£1.0

1. Funding for 2028/29 has been reduced from that given in the previously approved concept note, reflecting confirmation of post’s ODA allocation for the Spending Review Period; all funding is within limits currently set. Spending under SA-TIED is C-DEL in line with PrOF guidance, and with agreement with the Research and Evidence Directorate. Technical assistance spending is R-DEL. No funds will be disbursed directly to the government of South Africa.
2. The funding profile reflects the opportunity to partner with UNU-WIDER to launch phase III of SA-TIED within the current financial year and provide the resources for the initial scale up while other donors come onboard, while the time needed for procurement of a commercial supplier for the TA means delivery will start during financial year 2027/28, following on from the International Economic Partnership which is expected to end in 2026/27.
SA-TIED
SA-TIED funding will be disbursed through an MoU between BHC South Africa and UNU-WIDER.
1. Early funding of the programme is necessary to ensure the programme has the resources to continue without a break from phase II. This will allow the programme to retain key staff and quickly launch new requests for proposals and continue to expand the work of the datalab. UK and National Treasury funding will be used initially, with other donors, particularly the EU, supporting the programme later in its life cycle. The funding will be managed through a pooled trust-fund structure, held by UNU-WIDER in Helsinki, against which funds will be drawn down for operational expenses.
2. Co-funding is expected from the EU, alongside National Treasury and the South African Revenue Service to the values below (converted from ZAR and USD):
Partner (all values converted into £)	Total funding	Share of total
British High Commission	£500,000	12%
European Union	£874,000	21%
South African Revenue Service	£112,000	3%
National Treasury	£2,674,000	64%
Total	£4,160,000	100%

1. UN programme governance processes will be in place for the management of all monies, which will include regular audit and review, alongside the BHC-led annual review process. A zero-tolerance approach is taken towards fraud and corruption.
2. The financial and fiduciary risk to this element of the programme is assessed as low. The programme already has a strong record of governance and oversight. The programme will not fund or create assets owned by the FCDO; the equipment in the datalab will be funded separately by the government of South Africa.
Flexible technical assistance
1. Payments to the contracted supplier will be made on a quarterly basis, with payments split between a pre-agreed, fixed quarterly programme management fee and a results-based payment linked to programme milestones. All payments will be made in arrears.
2. As part of the commercial arrangement with the supplier the following mechanisms will be put in place to ensure funds are used for their intended purpose:
  1. Due diligence assessments will be carried out on the implementing partner and any junior consortium partners prior to agreeing the contract.
  2. Financial, procurement, fraud and whistleblowing systems will be required and agreed with implementing partners during the inception phase.
  3. Funds will be disbursed on receipt of a valid invoice supported by a breakdown of expenditure in line with the work plan and overall budget set. In accordance with FCDO standard institutional agreements, each invoice will be supported by a breakdown of the costs being claimed against each budget line in the agreement, and the PRO will be responsible for due diligence of this activity.
  4. The implementing partner(s) will be required to report activity on a quarterly basis, setting out progress of implementation (including milestone delivery, context analysis and risks) and a financial progress report.
  5. Regular reviews of risks to the programme, including related to fraud and corruption; a zero tolerance approach to fraud and corruption.
  6. Audited financial accounts of the implementing partner will be required on an annual basis to demonstrate how funds are being used.
3. The technical assistance element of the programme will only be funded through the BHC, with no co-funding arrangements. There are no specific accounting considerations created by this element of the programme.
4. Financial and fiduciary risk to this element of the programme is assessed as low. Close work with the implementing partner, alongside the government of South Africa, will provide oversight of technical assistance and wider programme delivery, giving assurance that funds are not misspent.
Management Case

Overview of Delivery Responsibilities
1. The Economic Reform Accelerator programme will be delivered through two complementary components:
  1. SA‑TIED (MoU) – delivered by UNU‑WIDER under the leadership of the Government of South Africa’s National Treasury, supported by FCDO programme oversight.
  2. Flexible Technical Assistance (Commercial Contract) – delivered through a competitively procured supplier, drawing on the proven model of the International Economic Partnership (IEP), which demonstrated high‑performing, demand‑led support to senior SA policymakers
2. Each component has bespoke management arrangements appropriate to its delivery mechanism, with unified oversight through the central programme governance structure.
Central Governance and Oversight Structures
1. As set out in the Concept Note, the programme will be overseen by:
  1. Senior Responsible Owner (SRO): G6 Economic Counsellor– an accredited Senior Expert in Private Sector Development;
  2. Programme Responsible Officer (PRO): G7 First Secretary, Economic Affairs – an accredited Expert Economist;
  3. Programme Manager: Dedicated EO resource supporting delivery and contractor/grant management.
2. The SRO is accountable for delivery, risk management, ensuring VfM, and alignment with the Country Plan. The PRO and Programme Manager oversee daily management, contract/grant administration, assurance and reporting.
3. Monthly meetings of the SRO, PRO and programme manager will cover progress of both elements of the programme, as well as reviewing the risk register and budget management. This will also provide a regular check in of programme monitoring and evaluation.
4. The programme will be regularly evaluated through the FCDO’s Annual Review process which will assess the programme’s performance against outputs and the broader Theory of Change every year. This structure ensures that changes to delivery and recommendations can be provided and acted upon in a timely manner to ensure benefits are realised.
5. The technical assistance element of the programme will require greater direct management from the BHC given its structure of working closely with government officials to identify areas of work and ensure a flexible, responsive structure. It is envisaged that roughly 75% of management time would be spent monitoring this element, with 25% overseeing SA-TIED involvement, given the wider structures set out below.
6. As part of the management arrangements, regular conversations with key stakeholders across government will be required as part of our monitoring and evaluation. This qualitative feedback will be vital to ensuring the programme delivers against the theory of change, and provide evidence for the annual review of the programme.
7. Governance and management of each part of the programme are set out below, through which the monitoring and evaluation of the programme will be delivered.
SA-TIED
1. SA‑TIED’s governance structure is well‑established, with participation from the BHC, other donors, and UNU‑WIDER and the government of South Africa. This structure has been consistently used through previous phases of SA‑TIED. There are several tiers to this management structure:
  1. Advisory Group: Provides external oversight and challenge to the progress of the programme. It will meet every six months to review progress, making recommendations to improve policy relevance and impact. It will consist of UNU-WIDER, National Treasury, SARS, donors (including the BHC) and external policy experts.
  2. Steering Committee: Accountable for implementation of the programme. It will meet monthly and consist of UNU-WIDER, National Treasury and SARS. The Steering Group will monitor day-to-day operations of the programme, trouble-shooting institutional issues and ensuring effective working between UNU-WIDER staff and GoSA.
  3. Programme Lead: Provides day-to-day management of the programme, providing a central point of co-ordination between academic work and policy officials working with the programme, as well as management of the wider programme management team.
  4. Workstream leadership: Responsible for defining calls for research proposals and ensuring close work between academics and policy officials. Each workstream (seven) will have co-leadership; one policy official from a relevant department (often National Treasury) and a senior academic from the relevant field of study.

Advisory Group
Steering Committee
Workstream 1: Data Evidence
Workstream 2: Public revenue mobilisation
Workstream 3: Poverty, inequality & labour markets
Workstream 4: Macro-fiscal analysis
Workstream 5: Food, energy & water
Workstream 6: Reform implementation
Workstream 7: Public Expenditure
Policy official and academic co-leads for each workstream
Programme Lead

Flexible Technical Assistance Component
1. This element mirrors the successful International Economic Partnership management model, which delivers rapid, high‑quality technical support while maintaining strong oversight and VfM. Management structure should balance the need to keep the programme flexible and responsive to the needs of policy makers, while providing robust challenge to emerging areas to avoid scope-creep.
2. FCDO will manage the technical assistance supplier through a structured performance and contract management framework consisting of:
  1. Monthly Delivery Meetings: Chaired by the PRO, bringing together the BHC programme Manager and delivery partners, these sessions will:
    1. Review progress against tasks
    2. Identify emerging opportunities for activity
    3. Adjust priorities to maintain responsiveness
    4. Assess programme risk
    5. Cover fraud, safeguarding and other regular reviews
  2. Quarterly Reporting: required for programme oversight and payment, these will:
    1. Review performance against KPIs
    2. Validate delivery milestones and VfM
    3. Review financial forecasts and adjust workplans
    4. Assess risks and mitigation actions
  3. Steering Committee: Held every six months, chaired by the programme SRO and attended by the PRO and programme manager from the BHC, delivery partner and government stakeholders, the steering committee will:
    1. Provide oversight of programme progress against delivery plan
    2. Provide strategic advice and guidance to areas of focus
    3. Ensure strong collaboration with the government of South Africa
  4. Quality Assurance: ensuring outputs are of sufficient quality, mechanisms will include:
    1. Peer review of analytical products
    2. Review of policy briefs and outputs by relevant policy leads
    3. Internal BHC review and sign‑off
    4. GESI and climate integration checks
    5. QA with BHC’s Social Development Advisor through regular engagement
3. The work delivered through the technical assistance programme will be proactively shared with key stakeholders across the BHC, with quarterly updates linking to the outputs of the programme.
Safeguarding
While the programme is judged to have low safeguarding risks. Under both elements of the programme individuals will be asked to work in environments outside the BHC’s control. While most of these places will be offices and relatively low-risk environments, the risk is low but some risk remains. The programme will have a zero-tolerance approach to SEAH, and the BHC expects all stakeholders to follow the same due care to minimise the opportunities for SEAH instances to occur. These include testing the robustness of processes during the Due Diligence of the supplier, open and frank conversations on safeguarding, integrating safeguarding into governance arrangements, using indicators as part of the results framework, and including contractual provisions and milestones on safeguarding in the supplier contract. The full suite of mitigations and tools will be assessed during mobilisation.
Risk Management
The table below shows the programme’s risk appetite alongside the British High Commission and FCDO risk appetite levels.
Risk	Programme Appetite	BHC / Appetite	FCDO / Appetite
Strategy and Context	Receptive	Receptive	Receptive
Policy and Programme Delivery	Receptive	Receptive	Receptive
Public Service Delivery and Operations Risk	Cautious	Cautious	Cautious
People	Cautious	Cautious	Cautious
Financial and Fiduciary	Minimal	Cautious	Cautious
Safeguarding	Minimal	Cautious	Cautious
Reputational	Cautious	Cautious	Cautious

Specific risks arising to are set out in the programme risk register overleaf:

Risk	Gross Likelihood	Gross Impact	Mitigation	Residual Likelihood	Residual Impact
Strategy and context / A change in political direction means government reform agenda moves away from evidence-based policy and international best practice, limiting the extent to which the programme can support reform efforts.	Possible	Severe	Work quickly to provide support to reforms, maximising impact while the current government focus is on improving the business environment and delivering growth-enhancing reforms.	Possible	Severe
Policy and Programme Delivery / Limited uptake from government prevents work from engaging meaningfully with policy formulation	Possible	Major	Early, sustained engagement with policy officials ensures close co-operation on policy formulation. Ensuring implementing partner has strong links into government, and an adaptive, flexible approach to support will identify opportunities for collaboration.	Unlikely	Moderate
Policy and Programme Delivery / Scope creep of support into broader range of policy areas undermines focus on binding constraints to growth	Possible	Moderate	Close monitoring of programme workstreams and oversight of delivery partner to ensure workstreams are clearly linked to the theory of change and areas of focus established during inception.	Unlikely	Minor
Financial and Fiduciary / Project implementer has insufficient safeguards and oversight leading to the mismanagement of project funds, diverting funds away from the outputs of the project.	Unlikely	Major	Close work with project implementers, including regular discussions and checks on project management approaches and close inspection of financial reporting, will lessen the chances of mismanagement and increase the chance of catching any inappropriate use of funds.	Unlikely	Moderate
Safeguarding / Unethical behaviour, abuse of power, or prohibited conduct by a programme partner leads to reputational and financial impacts on HMG.	Unlikely	Major	Due diligence on delivery partners and regular conversations with implementers to ensure robust safe-guarding frameworks are in place.	Unlikely	Moderate