Business Case Template - Smaller Projects in programmes

Country Business Plan Summary / Use our diplomacy and humanitarian / development programming to address fragility and support regional stability. Play a leading role, alongside key partners, to ensure an effective humanitarian response in Eastern Chad. Support the population of one of the least developed countries on earth, by building human capital, saving lives and intensifying our investment in long term resilience, and leveraging our development expertise and global influence. Deepen our relationship with the Government of Chad to support British interests and be prepared for crises and agile as opportunities/threats arise.
Programme Title: Strengthening Evidence Based Responses to Mixed Migrant Flows in Northern Chad
Programme summary (100 words maximum): The project aims to strengthen evidence-based and protection-oriented responses to mixed migration flows in northern Chad, particularly those triggered by the Sudan crisis. It seeks to improve migration data collection and analysis to better understand whether Chad is increasingly functioning as a transit country for Sudanese migrants en route to Libya and Europe. The project also enhances protection and assistance for vulnerable migrants (including victims of trafficking) and raises awareness about safe migration pathways. Through expanded monitoring, direct support, and capacity-building for local authorities, it will contribute to safer, more informed migration decisions and reinforce Chad’s institutional capacity.
Programme Value: £250,000		Directorate/Department/Post/ Region or Sector: / British Embassy N’Djamena, Chad
Post confirmation of review processes		Yes, all review processes have been followed.
Contact names		SRO: Alexander Green, Development Counsellor / PRO: Jean Dider Bidzogo, Programme Manager
Threshold for final approval of Business Case: Head of Mission Approval
Business Case approval:	17/11/2025	Name and role of Approver:
Programme Code:	Programme Start Date: / 1 December 2025		Programme End Date: / 31 March 2026
Overall risk rating:	Moderate
Teams link:	IOM NORTHERN CHAD PROJECT

Business Case
For a Smaller Projects programme

Strategic Case

What are the context issues/ problem you plan to address through your programme outcomes?

The programme seeks to address the escalating challenges posed by mixed migration flows in northern Chad, particularly those caused by the Sudan crisis. The region has witnessed a sharp rise in the movement of refugees and migrants, including those expelled from Libya, transiting through remote provinces with limited state presence and humanitarian access. However, it remains unclear to what extent Chad is functioning as a transit country for Sudanese migrants en route to Libya and Europe. The programme contributes to filling some of this gap by improving migration data systems to clarify these patterns, while also enhancing protection mechanisms and supporting safer, more informed migration decisions. Migrants face significant vulnerabilities, including exposure to trafficking, gender-based violence, and exploitation, especially in mining zones and desert transit hubs.

What are the intended policy objectives/outcomes for the programme?

The programme aims to strengthen evidence-based migration management and protection responses in northern Chad through three core outcomes. First, it will improve the availability and use of migration data to inform policy and operational decisions. Second, it will enhance protection and assistance for migrants in vulnerable situations, including victims of trafficking and those stranded or expelled. Third, it will increase awareness among migrants and stakeholders about safe migration pathways, rights, and available services. Deliverables include the production a migrant presence survey, protection assistance to over 500 migrants, training of 15 government officials on data governance, and outreach migrants through awareness campaigns. These outcomes will contribute to more coordinated, humane, and effective migration responses.

What is the rationale for FCDO spending?
This IOM-led project directly responds to the UK Government’s strategic priority on migration and is aligned with British Embassy N’Djamena’s Country Business Plan. We think that northern Chad has become a critical corridor for onward movement of Sudanese refugees and other migrants toward Libya and Europe. However, there is a lack of reliable data on the scale and nature of these flows, limiting the effectiveness of policy and programmatic responses. It is clear that we need to understand this better. The project contributes to addressing this gap by expanding IOM’s Displacement Tracking Matrix operations across remote northern provinces, and through the development of a migrant presence survey, generating timely and detailed data on migration dynamics, vulnerabilities, and emerging risks. It also delivers targeted protection assistance to migrants in vulnerable situations - including victims of trafficking - and builds the capacity of local authorities to manage migration safely and humanely.
This programme is funded by the Home Office, under the Rome Process, which supports coordinated migration responses in key transit and origin countries. The FCDO will hold a Memorandum of Understanding with the Home Office to facilitate the transfer and management of funds. As the only UN agency present in key northern areas, IOM is uniquely positioned to implement this initiative. The project complements Dutch-funded efforts under the COMPASS programme and fills critical gaps in data and protection coverage. By funding this programme, the UK reinforces its commitment to humanitarian leadership, conflict prevention, and evidence-based migration management – ensuring that interventions are informed, coordinated, and aligned with UK foreign policy objectives in the Sahel region.

What are the risks associated with this programme and potential individual projects?

The programme faces several risks, including security threats from non-state armed groups operating in remote areas, which could limit access and endanger staff and beneficiaries. There is also a risk of migration flows exceeding operational capacity, potentially straining resources and response mechanisms. Coordination challenges among stakeholders and logistical constraints in desert regions may further complicate implementation. These risks will be mitigated through close coordination with UNDSS for security monitoring, prioritisation of assistance based on vulnerability, and flexible planning to adapt to changing migration dynamics. The very short duration of the project means that, in programmatic and FCDO policy terms, there is a risk that insufficient or insufficiently-reliable data is collected, as well as the risk of a lack of sustainability of this data and its collection methods - in a context where migratory flows are dynamic and evolving.

How will the programme ensure compliance with FCDO rules/commitments on:
- ODA eligibility
- Gender equality
- Disability inclusion
- Public Sector Equality Duty
- Inclusive Data Charter Action Plan - GOV.UK (www.gov.uk)
- Safeguarding, against Sexual Exploitation, Abuse and Harassment.
- Impact on climate and the environment.
- Human rights (HR) assessment.

The programme is fully aligned with FCDO commitments. It meets ODA eligibility by directly supporting the development of Chad through humanitarian assistance and institutional strengthening. Gender equality is addressed through sex and age disaggregated data, and protection-sensitive programming. The programme supports the Public Sector Equality Duty by promoting equitable access to services and capacity-building. It adheres to the Inclusive Data Charter by collecting inclusive, disaggregated data to inform HMG policy. Safeguarding against sexual exploitation, abuse, and harassment is embedded through IOM’s protocols, staff training, and survivor-centered referral mechanisms. Finally, human rights are upheld through protection-sensitive assistance, legal referrals, and coordination with UNHCR for asylum seekers, ensuring that the programme does not contribute to rights violations.

Appraisal Case

Describe the criteria under which each Project in the programme will selected for funding.

This programme is made up by one project with IOM. This project has been selected based on its relevance to UK Government priorities, particularly migration, and is aligned with the British Embassy N’Djamena’s Country Business Plan. Selection criteria included alignment with Country Plan objectives – especially those related to migration, humanitarian protection, and conflict prevention. The Embassy has also considered their oversight capacity as a small embassy team. All projects will be reviewed and approved through the Embassy’s internal programme board, ensuring strategic fit, risk management, and accountability.

How will value for money be delivered throughout the programme and in each project?

Value for Money will be delivered through strategic targeting of resources to areas where UK support fills critical gaps, particularly in data collection and protection services in northern Chad. The programme complements existing Dutch-funded efforts, ensuring synergy and avoiding duplication. IOM will be required to demonstrate efficiency, effectiveness, and equity in their proposals. Overhead costs will be kept at 7%, and all procurement will follow UN standards for transparency and cost control. Monitoring and evaluation frameworks will be established from the outset, with regular reporting and internal reviews to ensure accountability and adaptive management.

What do you anticipate the maximum project value will be?

The maximum project value will be £250,000.

Commercial Case

How will delivery partners be selected? What funding arrangements are likely to be used?

Delivery of this programme will be implemented through a Memorandum of Understanding with IOM, a UN agency with longstanding operational presence in Chad and unique access to remote northern provinces. IOM is the only UN agency currently active in Tibesti and Borkou, making it the most suitable partner for delivering migration-related data collection and protection services in these high-risk areas. Given the strategic nature of the intervention and the need for rapid deployment in response to evolving migration dynamics, the programme will not be tendered through open competition. Instead, it will build on IOM’s existing infrastructure and complement ongoing Dutch-funded programming under the COMPASS initiative. This approach ensures continuity, operational efficiency, and alignment with UK migration priorities. This is in line within PrOF guidance, and we have completed the relevant direct tender documentation.

How will the programme manage the risk associated with delivery through each partner?

Risks associated with delivery through IOM will be managed through a proportionate DDA, drawing on the Central Assurance Assessment held by FCDO for IOM Headquarters. This central assessment provides assurance on IOM’s financial management, governance, and safeguarding standards. The Embassy will supplement this with contextual checks specific to IOM’s operations in Chad, including monitoring of field activities (where possible), and regular financial reporting. Given the relatively small scale and sensitivity of the intervention, upfront due diligence will be complemented by ongoing post-activity checks, including site visits (where possible), and beneficiary feedback. This dual approach balances risk management with operational agility and is consistent with the Embassy’s risk appetite for programming in fragile and remote contexts.

Financial Case

Outline the total budget, its source and where applicable the allocations for each financial year for the programme.

This project is a 4 month intervention, with a total budget allocation of £250,000 for the financial year 2025/26, funded entirely by the Home Office, but transferred to FCDO baseline. The funding will support IOM’s implementation of expanded migration data collection, protection services, and capacity-building activities in northern Chad. While the programme complements ongoing Dutch-funded efforts under the COMPASS initiative, no co-funding is requested for this specific intervention. All activities are scheduled to be completed within the implementation period to March 31, 2026.

How will you manage financial risks?

Financial risks will be managed through a combination of robust oversight mechanisms and close coordination with IOM. Funds will be disbursed in accordance with the agreed schedule outlined in the MoU, and the British Embassy N’Djamena will provide monthly forecast updates and monitor expenditure against planned activities. IOM will submit regular financial and activity reports, including receipts and documentation of services delivered. Embassy staff will verify delivery through field visits where feasible, and post-event checks will be conducted to confirm implementation.

Management Case

Governance arrangements and Programme Management Team
How will the programme be managed and governed?

The programme will be governed and managed through a structured oversight mechanism led by British Embassy N’Djamena. The Development Counsellor will serve as the Senior Responsible Owner (SRO), providing strategic leadership and ensuring alignment with UK Government priorities, including the migration objectives set out in the Country Business Plan. The Programme Manager will act as the Programme Responsible Owner (PRO), overseeing day-to-day programme delivery, coordination with implementing partners, and reporting. The Embassy team will be supported by a range of regional advisers, including humanitarian and conflict specialists, to ensure technical quality and contextual relevance. The programme will work closely with the Home Office, which is providing the funding, and with FCDO migration colleagues in the UK, ensuring coherence with broader UK migration policy and programming.

The data collected from this project will take place in parallel with an internal FCDO Migration Diagnostic being developed to inform our future work in this space, given the priority Ministers are attaching to tackling irregular migration, and the fact that Chad has been identified as a priority country in light of the flows of Sudanese nationals (we believe are) travelling through it (Sudanese nationals currently represent the 4th biggest nationality of those travelling across the English Channel in Small Boats). We intend for this IOM project and our internal Diagnostic to be mutually-reinforcing.

Monitoring and Reporting
Please describe the lines of accountability, responsibility, and reporting from projects to the programme and the portfolio. Also describe how projects delivery will be monitored

Although funding for this project comes entirely from the HO, it will be FCDO – specifically, British Embassy N’Djamena - which oversees and monitors delivery on behalf of HO, with whom we will stay in close contact and consultation throughout.

Project delivery under this programme will be monitored through a combination of regular reporting, direct engagement, and structured oversight mechanisms. IOM will submit narrative and financial reports at project completion and at agreed quarterly intervals during implementation. The British Embassy N’Djamena will hold monthly coordination meetings with IOM to review progress, address challenges, and ensure alignment with programme objectives. Subject to a travel risk assessment, Embassy staff aim to conduct a site visit in January or February to assess implementation on the ground.

Progress will be formally reviewed during Programme Board meetings and reported regularly to the Country Business Plan and Post Leadership Committees. These updates will include achievements, risks, and planned activities. Additionally, programme performance and data will be reviewed through joint Home Office/FCDO coordination mechanisms, including the Rosella Taskforce, which provides strategic oversight on migration programming in priority countries.

Risks
Summarise the main risks to the programme and mitigation measures as appropriate.

The overall risk level for this programme is assessed as moderate, primarily due to the operational challenges in northern Chad and the political sensitivity of migration issues. However, these risks are considered within the FCDO’s risk appetite, given the strategic importance of migration in UK foreign policy and the mitigation measures in place. The Embassy’s monthly engagement with IOM, planned site visit (Jan/Feb, subject to TRA clearance), and quarterly reporting to the Country Business Plan and Post Leadership Committees will ensure strong oversight. Additionally, joint Home Office/FCDO coordination, including through the Rosella Taskforce, will provide strategic guidance and ensure risks are monitored and managed across the UK migration portfolio.

Risks	Likelihood (no mitigation)	Impact (no mitigation)	Mitigation
Unpredictable migration flows may exceed the programme’s operational capacity	Low	Medium	This will be mitigated by prioritising assistance based on vulnerability and maintaining close contact with the government and humanitarian actors.
Security risks posed by non-state armed groups in Northern Chad, particularly Tibesti and Borkou Provinces.	Low	High	This will be mitigated by IOM close coordination with UNDSS. Should security conditions deteriorate, activities will be paused or relocated, and the risk escalated.
Safeguarding risks may mean that migrants, especially women and children, may face exploitation, trafficking or abuse during transit.	Medium	Medium	This will be mitigated by IOM applying its global safeguarding protocols, including protection screening and referral mechanisms. Embassy oversight will include safeguarding checks during site visits.
Fraud risk or a misuse of funds/poor delivery could undermine UK credibility and trust.	Low	Medium	This will be mitigated through IOM’s internal audit and compliance systems and complimented by Embassy financial oversight and spot checks