IOM STRENGTHENING EVIDENCE BASED RESPONSES TO MIXED MIGRANT FLOWS IN NORTHERN CHAD LOG FRAME
The project seeks to strengthen evidence-based and protection-oriented responses to the growing onward movement of Sudanese refugees and migrants through northern Chad toward Libya and Europe. In response to the current gaps in data on mobility patterns, risks, and migrant intentions, the project aims to improve information systems, reinforce local protection mechanisms, and increase awareness among refugees and migrants about the dangers of irregular migration and reduce reliance on dangerous migratory routes and promote safer, more informed decisions. This will be implemented through three outcomes: / Outcome 1: An improved evidence base on the impact of the Sudanese crisis strengthens data-driven migration management and response efforts in northern Chad / Outcome 2: Migrants in Vulnerable situations, including victims of trafficking, along northbound routes in Chad, access protection and assistance services that uphold their rights, safety, and dignity. / Outcome 3: Migrants at risk and key stakeholders have enhanced access to reliable information on safe migration pathways, ensuring migrants are aware of their rights, risks, and available alternatives
Indicator(s):	Baseline		Sources		Milestones	Target & Date
Percentage of key stakeholders (government, humanitarian, and development actors) reporting increased access to and use of migration data in planning and decision-making by the end of the project / Number of identified migrants in vulnerable situations and other populations on the move (including VoTs) who receive tailored assistance. / Number of migrants and stakeholders reached through awareness-raising activities (e.g. leaflets, radio broadcasts, theatre performances) and trained on safe migration, rights, and available services (disaggregated by stakeholder and gender)	0 / 367 / 0		Post-implementation survey / Referral and activity reports / Activity reports		Final report / Final report / Final report	75% / 527 / 230
Outcome 1: An improved evidence base on the impact of the Sudanese crisis strengthens data-driven migration management and response efforts in northern Chad.
Output 1.1: Timely and detailed migration data on movements along Chad’s northern migratory corridor is available.
Indicator(s):	Baseline		Sources		Milestones	Target & Date
Number of flow monitoring and migrant presence survey reports produced.	62 reports		DTM reports		Final report	65 (2 FMP quarterly reports published and 1 Survey report on migrant presence)
Activities linked to Output 1	Activity 1.1.1 - Strengthening Flow Monitoring at key point of entry and transit locations / This activity will focus on strengthening IOM’s presence at key points of entry and transit by reinforcing existing Flow Monitoring Points (FMP) across the north of Chad, situated in Faya, Ounianga Kebir, and Zouarke. By expanding these strategic FMPs through strengthening data collection tools, the aim is to collect more comprehensive and detailed information about migration flows, routes, and the profiles of those on the move. Enhanced coverage at these sites will ensure the capture of timely and accurate data, ultimately supporting more informed policy and programmatic responses to evolving migration dynamics. Surveys (FMS) will be conducted on migrants flows during their journey to collect comprehensive and detailed information on migrant profiles, intentions, vulnerabilities, and needs. Through these surveys, data collection on migration and trafficking will be strengthened. / Activity 1.1.2 - Implementation of Migrant Presence Survey (MPS) / This activity involves conducting targeted thematic studies to produce detailed profiles of migrants present in key regions, particularly those drawn by economic opportunities. The Migrant Presence Survey (MPS) aims to study and characterize both refugee and migrant populations to better understand and define these groups, including their overlaps and differences in needs and objectives. / The surveys will cover a wide range of topics, including: / Demographic profile, socio-economic background, employment status, and access to services before departure and after arrival. / Motivations for leaving, travel preparation (e.g. people involved in decision-making, travel costs and financing, possible use of smugglers). / Routes taken, including means of transport, travel duration, intended destination, and any changes in itinerary. / Living conditions in destination or transit areas, such as livelihoods, access to land and basic social services, and levels of social cohesion (e.g. the extent to which migrants support each other). / Protection concerns, including any abuse, violence, or exploitation experienced during the journey or upon arrival. / This activity will be conducted in economically attractive areas and will complement flow monitoring efforts, offering critical insights into why people move, how they prepare for their journeys, and the routes they take, which is crucial for anticipating future migration trends and managing mobility more effectively.

Output 1.2: Government counterparts and stakeholders have strengthened capacities on migration data governance
Indicator(s)	Baseline		Sources		Milestones	Target & Date
Number of government counterparts trained and certified (disaggregated by gender) / Number of workshops on data governance	0 / 0		Training reports and participant list / Workshop report		Final report / Final report	15 persons trained and certified / One national workshop conducted
Activities linked to Output 1.2	Activity 1.2.1 – Capacity building for relevant stakeholders on migration data collection and usage / As part of this activity, IOM seeks to strengthen the capacity of national counterparts within a broader strategy to enhance national data management systems. The overarching goal is to progressively increase national ownership of data-related activities. / To support this objective, IOM will provide training to national and local authorities, as well as relevant organizations, on data collection methodologies and tools. At the national level, two key institutions will be engaged: / The National Institute for Statistics, Economic and Demographic Studies (INSEED), which holds the mandate for producing official statistics and demographic data, ensuring methodological consistency and alignment with national standards. / The National Commission for the Reception and Reintegration of Refugees and Returnees (CNARR), which plays a central role in managing displacement contexts, making its involvement essential for accurate and context-specific data collection and coordination. / In addition, IOM will collaborate with national non-governmental organizations as needed to support their capacity development. A minimum of 15 national actors will receive training on the Displacement Tracking Matrix (DTM), covering key areas such as data collection, usage, management, and data protection principles. / Activity 1.2.2 – Workshop to strengthen data governance and harmonisation / IOM, in partnership with INSEED and CNARR, will organize a national workshop bringing together key stakeholders involved in migration management in Chad. The workshop will serve as a platform to present and discuss the main findings from recent surveys and studies on migration, including data collected through Flow Monitoring and Migrant Presence Surveys in the north of Chad. It will also provide an opportunity to gather recommendations from participants, identify priority information needs, and highlight existing data gaps that need to be addressed to strengthen the national understanding of migration dynamics. In addition to fostering dialogue and collaboration among government ministries, national institutions, and partners, the workshop will support the establishment or reinforcement of a national coordination unit on migration data. This unit will bring together relevant ministries and serve as a central mechanism for harmonizing data collection efforts, improving data sharing, and enhancing national ownership of migration information systems.
Outcome 2: Migrants in vulnerable situations, including victims of trafficking, along northbound routes in Chad, access protection and assistance services that uphold their rights, safety, and dignity.
Output 2.1: Strengthened referral and protection coordination mechanisms are in place for migrants in vulnerable situations in key border and transit locations
Indicator(s)	Baseline		Sources		Milestones	Target & Date
# of coordination mechanisms established.	0		Coordination meeting report		Final report	One.
Activities linked to Output 2.1	Activity – 2.1.1. Establishment of a coordination committee to identify, assist and refer stranded migrants in transit and migrants expelled from Libya / This activity aims to establish a local coordination mechanism for lifesaving and emergency response to migrants in distress in the desert regions of Chad. Two coordination meetings will be organized, bringing together government representatives, non-governmental organizations, and civil society actors operating along key migratory routes in the northern corridor. These meetings will serve to define clear standard operating procedures (SOPs) outlining roles and responsibilities in providing assistance to stranded migrants, including those expelled from Libya. / The coordination committee will focus on locating, stabilizing, and evacuating injured or migrants in vulnerable situations, and referring them to appropriate organizations or services for further support. To enhance their operational capacity, committee members will receive training in emergency first aid, security protocols, and protection principles. / This activity will specifically target localities along the northern migration route toward Libya, where migrants are frequently stranded without access to assistance. Priority will be given to areas within the BEET provinces, which are known for their harsh desert conditions and limited humanitarian presence.
Output 2.2: Migrants in vulnerable situations receive direct assistance, including psychosocial, food, and safe return support
Indicator (s)		Baseline		Sources	Milestones	Target & Date
# of persons exposed to protection risks provided with protection services (disaggregated by gender) / # of migrants who received tailored reintegration support (disaggregated by gender)		0 / 0		IOM data centralization tool / IOM data centralization tool	Final report / Final report	160 individuals / 4 individuals
Activities linked to Output 2.2	Activity –2.2.1. Dignified transportation for stranded migrants / Migrants expelled from Libya, including individuals in vulnerable situations along migratory routes such as unaccompanied and separated children (UASC), pregnant women, and victims of trafficking, will be provided with safe and dignified transportation from Ounianga Kebir to the Faya transit centre. At Faya, they will receive immediate support and case management services, as detailed under activities 2.2.2 and 2.2.3. / For Chadian nationals, IOM will coordinate with local authorities and transportation providers to ensure that onward travel to their communities of origin is conducted in a manner that respects their rights, safety, and dignity. In the case of non-Chadian migrants, IOM will work in close coordination with the diplomatic representations of their countries of origin and relevant IOM missions in the region. This coordination will facilitate their safe transport from Faya to N’Djamena, including the provision of escorts and daily subsistence allowances as needed. Once in N’Djamena, migrants will be assisted to return to their countries of origin by air, through IOM Chad’s existing EU-funded project on Migrant Protection and Reintegration (MPRR). / Activity – 2.2.2. Provision of Mental Health and Psychosocial Support (MHPSS) and medical assistance / IOM will provide Mental Health and Psychosocial Support (MHPSS) services at the Faya transit center to migrants in need of emotional, psychological, and medical assistance. For urgent medical cases, immediate support will be arranged in collaboration with local clinics. In cases requiring specialized care, referrals will be made to appropriate health facilities in N’Djamena to ensure continuity of care. / MHPSS services will include psychological first aid, individual and group counselling sessions, and referrals for more specialized mental health care when needed. Special attention will be given to groups in vulnerable situations, including victims of violence, survivors of trafficking, and individuals suffering from trauma related to displacement or abuse experienced during their migratory journeys. / Activity – 2.2.3. Delivery of immediate assistance (food and non-food items) / To address the urgent needs of migrants in vulnerable situations at the Faya transit centre, IOM will provide emergency assistance that includes both food and essential non-food items. This support will ensure that migrants have access to basic necessities upon arrival and during their stay. Non-food items will include hygiene and personal care products such as soap, toothbrushes, sanitary pads for women, blankets, and other essential supplies to maintain dignity and well-being. / Activity – 2.2.4. Reintegration assistance for victims of trafficking (VoTs) / Identified and potential (VoTs), including Chadian migrants expelled from Libya and those stranded along migratory routes, will receive reintegration assistance kits designed to support income-generating activities within their communities of return. This support aims to promote sustainable reintegration and reduce the risk of re-trafficking or further uninformed decision of displacement. A case management approach will be applied to ensure that assistance is tailored to each individual’s specific vulnerabilities, needs, and aspirations. / For individuals seeking asylum or recognized as refugees, cases will be referred to UNHCR for appropriate handling and access to international protection mechanisms.
Outcome 3: Migrants at risk and key stakeholders have enhanced access to reliable information on safe migration pathways, ensuring migrants are aware of their rights, risks, and available alternatives
Output 3.1: Populations on the move have improved access to information on risk of irregular migration
Indicator(s)	Baseline		Sources		Milestones	Target & Date
# of migrants directly reached with information on safe migration pathways along the northern migration corridor / # of IEC materials developed in local languages and disseminated	0 / 0		Awareness activity reports / Visibility reports		Final report / Final report	200 individuals / 2 tools
Activities linked to Output 3.1	Activity – 3.1.1. Provision of awareness raising activities in border communities and transit hubs / IOM will implement a series of awareness-raising campaigns targeting migrants and refugees in the Zouarke and Kalait areas, which host a high concentration of stranded migrants due to their proximity to gold mines in the north of Chad. These individuals often face multiple forms of exploitation, including forced labor and human trafficking, leaving them highly vulnerable and with limited access to protection services. The campaigns will provide essential information on the risks associated with irregular migration, as well as migrants’ rights and available protection mechanisms. / To ensure accessibility and effectiveness, IOM will collaborate with local community leaders, border officials, and local authorities to deliver the sessions in the languages commonly spoken by the targeted migrant populations. In addition, awareness-raising activities will be extended to Sudanese refugees along migration routes to Libya. For this purpose, mobile community outreach teams will be recruited and trained to disseminate information on the dangers of irregular migration and available support services. / Activity – 3.1.2. Develop and distribute information, education and communication (IEC) materials on safe migration in local languages / To support access to accurate and up-to-date information on safe migration options and the risks associated with trafficking in persons, IOM will develop and disseminate targeted awareness-raising materials. These materials will include leaflets, posters, radio broadcasts, and community theatre performances, all tailored to reach diverse audiences along key migratory routes. Activities will be implemented in strategic locations such as border crossings and Flow Monitoring Points (FMPs), where migrants and mobile populations are most likely to be present. The aim is to equip individuals with practical knowledge to make informed decisions, reduce exposure to exploitation, and promote safer migration practices. These outreach efforts will also contribute to broader community awareness and engagement on migration-related protection issues.
Output 3.2: Local authorities and community leaders have expanded migration management capacities and are able to support migrants in vulnerable situations
Indicators	Baseline		Sources		Milestones	Target & Date
# actors trained on counter trafficking, and provision of assistance to victims (disaggregated by gender)	0		Training report		Final report	1 training (30 participants)
Activities linked to Output 3.2	Activity – 3.2.1. Training of local authorities, border agents on counter trafficking, identification and support to victims / IOM will provide targeted training for local authorities, border agents on counter trafficking and victim assistance. The sessions will cover identifying and supporting victims, in line with local legislation, the National Referral Mechanism for victims of trafficking as well as the international legal framework and approaches to combat trafficking, including the prevention, protection, persecution, and partnership components. The training will also be implemented in collaboration with the newly established National Commission against trafficking in persons under the Ministry of Justice. Training will include theory and practical exercises such as case studies and simulations to improve detection and response skills. / Emphasis will be placed on strengthening identification and referral systems so personnel can direct survivors to the right services. This effort aims to enhance institutional capacity, leading to more effective migration management and better protection for vulnerable individuals.