Business Case Template - Smaller Projects in programmes

Portfolio/ Business/Country Plan Summary [300 words maximum]: [insert a summary of the relevant Portfolio/Business/Country Plan from your department here] / The British Embassy Dakar’s country plan for FY 2025/26 sets out an agenda to deepen the UK–Senegal partnership at a time of significant economic and political transition. Our mission is to build a strategic, responsive, and mutually beneficial relationship that aligns UK expertise and investment with Senegal’s development priorities, while advancing mutual growth, security, and influence in West Africa. / Senegal remains one of the most stable democracies in the region, but faces acute challenges: very high levels of debt following unprecedented debt misreporting by the previous government, suspension of IMF support (though new programme negotiations are underway), and significant development needs (i.e. youth unemployment, inequalities, malnutrition and food insecurity, climate resilience, infrastructure and energy, industrialization and private sector development etc.). These challenges are coupled with strategic opportunities for the UK: Senegal is actively diversifying partnerships and has formally approached the UK as a partner of choice on debt and economic reform, particularly on public financial management. / Senegal is a ‘category 3’ Investment and Expertise Development Partnership country for the UK. The Embassy’s priorities are organised around three interconnected goals: / Growth and Development: – Growth is by far the largest aspect of our bilateral relationship; the UK is the largest investor in energy, with sizeable investments in infrastructure, telecommunications and agriculture, including by UKEF, BII and PIDG. The UK is a partner to Senegal’s JETP, and Manufacturing Africa operates here. We also launched a £13 million partnership with Institut Pasteur de Dakar to strengthen health research and pandemic preparedness, and through the WISH programme, we are supporting SRHR, helping avert thousands of unintended pregnancies and unsafe abortions. / Defence and Security – Collaborating on defence and security to enhance Senegal’s capacity to counter violent extremism, organised crime, and malign state actors, while growing UK operational access and influence through defence cooperation. / Core Service Delivery – maintaining a high-performing embassy platform, delivering consular and crisis services, and leveraging cultural and educational programmes to strengthen soft power.
Programme Title: Amplifying Reform: Strategic Communications Support for Senegal’s Economic Reform Agenda
Programme summary (100 words maximum): The Senegalese Ministry of Finance has requested UK support for PFM reform in Senegal. Communications technical assistance is a crucial component to help the Government of Senegal (GoS) build public support during critical economic reforms and expected difficult IMF conditions. This was emphasised during the visit by FCDO’s Deputy Chief Economist visit in May 2025. This programme proposes to provide technical assistance (TA) that combines UK Government (UKG) expertise with local knowledge to develop sustainable communications to build public trust and to support the successful implementation of challenging economic reforms.
Programme Value: £124,910		Directorate/Department/Post/ Region or Sector: Senegal
Post confirmation of review processes		All processes for BC approval have been followed
Contact names		Maty.ngom@fcdo.gov.uk (PRO) / Raveena.kaur@fcdo.gov.uk (SRO)
Threshold for final approval of Business Case: HoM
Business Case approval:	21/11/2025	Name and role of Approver: Carine Robarts, HMA Dakar
Programme Code: 400851	Programme Start Date: 1 October 2025		Programme End Date: March 2026
Overall risk rating:	Moderate
Teams link:	This document and the approval email have been saved in our teams channel: / 2025-09-23 Business Case - Small Projects Programmes GCSI BE Dakar.docx / GCSI business case approval.eml

Business Case
For a Smaller Projects programme

Strategic Case

What are the context issues/ problem you plan to address through your programme outcomes?

Following the election of a new Government of Senegal (GoS) in early 2024, serious fiscal and debt misreporting by the previous administration was uncovered. Investigations revealed that central government debt has reached 132% of GDP - a dramatic increase from pre-audit figures of 74% at the end of 2023 enabled by fragmented debt management and weak PFM controls. These findings mean that programme targets previously assumed to have been met – with funding released – had in fact been missed. The current IMF programme has been suspended with no further disbursements. A fresh Debt Sustainability Analysis is underway, which is expected to show Senegal entering debt distress or at high risk of debt distress. GoS has announced a GDP rebasing exercise, which could impact this analysis. A new IMF programme is anticipated once past loans have been dealt with, which will require remedial actions to address public finance weaknesses.

In response to this crisis, the GoS, via the Cabinet Secretary-equivalent, the Minister of Finance, the Secretary General of Ministry of Economy and Planning, and the President’s Diplomatic Advisor, has formally requested UK support to help restore macro-fiscal stability and rebuild public trust. The UK has a unique opportunity to shape Senegal’s reform agenda and elevate the bilateral relationship, in line with the Foreign Secretary’s growth and development objectives. This programme forms part of a broader package of UK support including three other HMG institutions: technical assistance from the FCDO’s Public Finance Resource Centre (PFRC), HMT peer-to-peer engagement, and support from the NAO. Together, these interventions aim to support Senegal in meeting IMF conditions and implementing reforms that promote inclusive growth and protect the most vulnerable.

Communications has been identified by both GoS and UK stakeholders as a critical area requiring immediate support. For example, during his visit in May this year, the FCDO’s Deputy Chief Economist identified that across government ministries, between government and the private sector, and between government and the public, communication is fragmented and inconsistent. Virtually every private sector firm consulted reported receiving contradictory messages from frontline agencies such as tax administration and customs, resulting in delays, frustration, and financial penalties. The UK can play a constructive role here by supporting the government to project a coherent vision of its economic direction so that the private sector and delivery arms of government can align their plans and investments accordingly. This is not currently happening in Senegal, and the business community has expressed concern over the absence of a clear economic roadmap.

Furthermore, working closely with the Government of Senegal on its communications strategy around IMF-related economic reforms and debt management is essential to ensure transparency and build public trust. These reforms are often complex and can be misunderstood, so clear messaging helps citizens see that the measures are designed to strengthen long-term economic stability rather than impose undue hardship. This is especially important given recent messaging from the government referencing the lingering impacts of painful 1980s structural adjustment. Notably, the Prime Minister recently described the current situation as a “humiliation,” while the Minister of Economy argued that structural adjustment is unnecessary because the debt remains sustainable. This divergence in public statements highlights the need for strengthened communication support to ensure coherence and clarity. It has already shaken creditors, with the last statement from the PM causing Senegal’s credit rating to drop further. Effective communication also aligns key stakeholders, i.e. civil society, private sector, and international partners, around shared objectives, reducing resistance and fostering collaboration. Without a proactive approach, misinformation and scepticism could lead to social unrest or political backlash, while strong, consistent messaging reassures investors and signals Senegal’s commitment to fiscal responsibility. Finally, a well-crafted strategy enhances Senegal’s reputation globally, positioning the country as a leader in economic resilience and demonstrating that reforms are part of a broader vision for sustainable growth.

The Government Communication Service International (GCSI) will therefore provide strategic communications assistance to help the GoS articulate its reform agenda, manage public expectations, and build confidence among domestic and international audiences. This will complement technical work led by PFRC, HMT and NAO and ensure coherence across the UK’s support offer.

GCSI will be part of a joint scoping team with PFRC, HMT and NAO, delivering a four-month intervention focused on rapid technical assistance, insights gathering, and strategy development. This will lay the groundwork for a longer-term programme of support. The intervention is designed to be responsive, targeted, and aligned with the Country Business Plan’s Goal 2: Growth and Development, which prioritises macroeconomic stability, governance strengthening, and sustainable development.

Time is of the essence. The GoS request was made in March, and the UK commitment was confirmed by the Minister for Africa during his visit to Dakar in September. Mobilisation is expected in early December. The programme will be structured to deliver measurable outcomes, provide value for money, and reinforce the UK-Senegal partnership at a pivotal moment for the country’s economic future.

What are the intended policy objectives/outcomes for the programme? Include any specific deliverables where known.
## Project Objectives
Build GoS capability to communicate effectively about forthcoming economic reforms in response to the debt crisis, building public support whilst implementing necessary but potentially unpopular measures.

Strengthen cross-government coordination on communications.

Develop audience-centred, evidence-based communications approaches, including for the private sector and for the general public

Embed sustainable communications capabilities during and beyond the immediate economic reform launch period.

## Project Outcomes
1. Adoption of a co-developed, insights-led communications strategy.
2. Establishment of a cross-government economic communications working group with an agreed communications gridding process, if deemed appropriate.

Increased public understanding of the GoS strategy for resolving its debt crisis, and increased public confidence in the wider GoS economic reform agenda based on policy objectives.

Positive change in the number of GoS officials who can confidently deliver economic communications by using best practice communications frameworks and tools.

Key deliverables include;
- Communications audit
  - Conduct a joint scoping mission with PFRC, HMT and NAO to clarify the areas of focus for this technical assistance
  - Contributions to the scoping mission report making recommendations for areas of follow engagement until March 31st
Following the scoping mission, GSCI will submit a finalized workplan outlining activities and budget through the end of the financial year.

Indicative deliverables:
- Baseline assessments
  - Conduct comprehensive review of current communications capabilities across the three key ministries (the Ministry of Finance and Budget; Ministry of Economy, Planning and Cooperation; and the Office of the Prime Minister)
  - Map existing structures, resources, and processes to baseline capabilities, identify critical capacity gaps, and inform project design
- Audience insight and media analysis
  - Research to understand public sentiment and attitudes towards the IMF and its mandated economic reforms; public opinion on GoS economic management; and identify key influencer networks
  - Map business leaders, civil society groups, youth organisations, and local authority structures
  - Assess current government relationships with these groups and the communication channels used to reach them
- Strategic communications advisory and training
  - Establish clear communications coordination mechanisms between ministries through a new cross-government economic communications working group
  - Co-develop a comprehensive OASIS strategy and communications grid based on policy objectives, using behavioural insights to identify and address barriers to public acceptance of reforms
- Civil Society engagement scoping
  - Identify potential civil society partners relevant to public finance management reforms in Senegal.
  - Conduct initial scoping to assess partner capacity, credibility, and alignment with programme objectives.
  - Engage in exploratory discussions with shortlisted partners to evaluate collaboration opportunities.
  - Document findings and recommendations to inform the programme’s civil society engagement strategy.

What is the rationale for FCDO spending?
#### 1. Senegal’s economic stability matters to the UK
A stable Senegal matters to the UK for economic, political and security reasons. Trade between the UK and Senegal has grown five-fold over the last 10 years, reaching £1.1 billion. The UK’s exposure to the debt crisis in Senegal is £XX, and UKEF’s largest guarantee in sub-Saharan Africa is in Senegal. Senegal is staunchly democratic, and the only country in West Africa not to have suffered a coup. Its stability at a time when the Sahel region, and in particular its neighbour Mali, is under threat from terrorists matters to the UK’s interests in the region.
The UK has a strategic opportunity to shape the government’s response to the recent audit and strategy for managing its debt, including potentially supporting the rollout of a new IMF programme. This moment is critical to ensure corrective measures strike the right balance between restoring macro-fiscal stability, rebuilding market confidence, driving economic growth, and protecting the most vulnerable. While the new administration enjoys strong popular legitimacy, particularly among youth, its messaging remains rooted in opposition-style rhetoric rather than reform-oriented communication. Without targeted support, reforms in energy, taxation, and public sector efficiency risk losing public backing. GoS communications to date have spooked the market, significantly worsening Senegal’s predicament. Effective communication will be essential to prevent unrest, maintain public trust, reassure creditors and investors, and stabilise Senegal’s macroeconomic environment. The current timeline offers a unique window to act, leveraging strong political will within the GoS. UK technical assistance will play a pivotal role in helping Senegal plan and deliver PFM reforms, meet IMF prior actions, and ensure successful programme implementation.
Engagement will also allow the UK to complement and influence the efforts of key donor partners, including multilaterals (IMF, World Bank, AfDB) and bilateral actors such as France and the EU.
#### 2. The proposed intervention aligns with FCDO Country Business Plan goals and the UK Africa approach
The British Embassy Dakar CBP 2025/26 identifies supporting Senegal’s economic reform process as a key UK objective. Goal 2 of the CBP is about deepening the UK-Senegal investment and expertise development partnership. It aims to “Support inclusive and sustainable growth and development in Senegal through expertise exchange and responsible investment in areas of shared, strategic priorities and through leveraging of multilateral investments.” Senegal has been identified as a ‘category 3’ development partnership, where our support should respond strategically to asks from the Senegalese for UK expertise, in line with the UK’s Africa approach. The Government of Senegal has formally approached the UK as a partner of choice for technical support on public financial management. Supporting strategic communications is a part of this technical assistance: it ensures that reforms are politically and socially viable. Spending here therefore underpins
3. UK comparative advantage
While BE Dakar does not have a tradition of delivering significant levels of bilateral ODA, we have successfully mobilised Centres of Excellence and centrally managed programmes (CMPs), including Manufacturing Africa (MA), the Women’s Integrated Sexual Health programme (WISH), and AI for Development (AI4D). Most recently, we signed a new partnership with the Institut Pasteur de Dakar on global health security. This growing demand for UK investment and expertise reflects the deepening UK-Senegal relationship and has been matched by increased resourcing at post. Through GCSI, the UK can offer world-class expertise in strategic communications, behaviourally informed messaging, and government coordination mechanisms. This is a unique comparative advantage: other donors may fund macroeconomic reforms or fiscal support, but few can provide trusted, discreet, and practical advisory support on how to build government capacity to communicate reforms and maintain public confidence. This builds on the UK’s credibility as a transparent, reform-minded partner, and supports the CBP ambition of positioning the UK as a partner for Senegal.
#### 4. Catalytic, Sustainable and Value-for-Money Impact
At a cost of £124,910, the project is designed for high leverage. It embeds cross-government communications structures, builds long-term capability in ministries, and equips officials with sustainable tools that outlast the programme period. This ensures that UK resources create durable institutional change, not dependency. The phased approach (diagnostics, strategy co-development, training delivery) allows real-time adaptation to political developments and maximises cost-effectiveness. By strengthening Senegal’s ability to carry out reforms successfully, FCDO spending delivers outsized impact in relation to the investment, directly advancing CBP goals of inclusive growth, stability, and stronger UK influence.
What are the risks associated with this programme and potential individual projects?

Type of risk	Risk	Likelihood	Mitigation
Operational	Limited engagement from the GoS	L/M	Engagement levels to be tested beforehand and working closely with Post to manage points of disengagement
Operational	Limited capacity by the GoS	L	Capacity levels to be assessed beforehand and working closely with stakeholders to manage any gaps
Operational	The GCSI team may not have sufficient knowledge of the local socio-political dynamics in Senegal, which could lead to misaligned communication strategies, reduced effectiveness of engagement with stakeholders, and potential reputational risks for both the programme and the Government of Senegal (GoS).	M/H	Engage local consultants or advisors with deep knowledge of Senegal’s socio-political landscape to support the GCSI team in all phases of the project. / Ensure all communications strategies and materials are co-developed with GoS counterparts and validated by local stakeholders before implementation. / Establish regular feedback loops with GoS officials and target audiences to monitor the effectiveness of communications and adapt approaches as needed.
Political	Changes in government or appointments officials derails the programme	M	Ensure that GCSI work with civil servants and sustains several points of contact to avoid single points of failure and sustainability
Reputation	UK engagement in Senegal’s economic reform process is seen as western meddling, in a context of historical distrust in the IMF	M	Ensure engagement with GoS is discreet and built on trust and understanding, working closely with stakeholders to understand context and needs
Reputation	GoS refusal to restructure its debt causes messy default, with which UK is associated	M/H	Ensure communications with GoS and IMF remain open and transparent / Work closely with CSOs and other local organisations to understand citizen concerns and needs, ensuring any communications addresses these

How will the programme ensure compliance with FCDO rules/commitments on:

ODA eligibility
Senegal is eligible for ODA. The intervention is capacity-building technical assistance that enables GoS ministries to communicate, coordinate and deliver macro-economic reforms (energy, tax, public-sector efficiency) that underpin poverty-reducing, sustainable growth squarely within ODA purposes. It contributes to achieving Post’s Goal 2 on Growth and Development and responds to a formal GoS request for UK support, ensuring partner-country ownership. The Business Case objectives, outcomes and deliverables (audit, audience insight, strategy, training) are all non-commercial, public-sector strengthening activities.
Gender equality, disability inclusion, Public Sector Equality Duty
The programme will: (i) ensure training venues/materials are accessible; (ii) disaggregate participation and feedback where feasible; and (iii) embed accessibility checks in comms products (plain-language guidance; alternative formats) so reform messaging reaches people with disabilities.
Inclusive Data Charter Action Plan - GOV.UK (www.gov.uk)
In line with IDC principles, audience insight and M&E will prioritise inclusive, disaggregated data (sex, age, geography where feasible) and clear data-governance practices.
Safeguarding, against Sexual Exploitation, Abuse and Harassment.
Delivery will follow UK civil service standards. We will use a Memorandum of Understanding with explicit SEAH clauses, due-diligence, and fortnightly governance meetings. Staff are vetted (SC/DV), and reporting lines include monthly reporting, bi-monthly (every two months) reviews, and activity-based budgets to surface and address risks promptly.
Impact on climate and the environment.
The project will not deal with climate issues.
Human rights (HR) assessment.
Programme design will: (i) embed rights-based, transparent communication practices; (ii) engage civil society/youth channels identified in the audience mapping; and (iii) include safeguards against misinformation that could inflame tensions. We will escalate concerns via Post governance if any activity could adversely affect rights or civic space.
GCSI is a HMG department therefore no due diligence assessment is required.

Appraisal Case

Describe the criteria under which each Project in the programme will be selected for funding.
Instead of an appraisal of delivery options, Posts or Directorates should set out proportionate processes and criteria for selecting and approving individual Projects within the Business Case.
We have chosen to undertake this programme in response to the Government of Senegal’s (GoS) urgent need for effective communication around economic reforms, following a period of significant economic distress and a renewed national commitment to transparency and good governance. Importantly, this programme is part of a comprehensive package of PFM support, which also includes HMT peer-to-peer support and support from the Public Finance Resource Centre of Excellence. It directly responds to a formal request for assistance from the GoS and is designed to provide value for money by focusing on sustainable, long-term capacity building.
When developing this programme, we considered alternative options, including a proposal from the Tony Blair Institute (TBI) to establish a delivery unit within the Ministry of Finance. While the proposal was well-developed, the Minister ultimately declined it, expressing a preference to work directly with the UK government, which reflects the strength of our bilateral relationship and the trust placed in our approach.
How will value for money be delivered throughout the programme and in each project?

Aligned with PrOF guidance on Value for Money (VfM), the programme clearly demonstrates all four principles: economy, efficiency, effectiveness, equity.

Dimension	Definition	How the Programme Delivers VfM	Evidence / Monitoring
Economy (minimising the cost of inputs)	Procuring and deploying resources at the best price.	• Use of HMG delivery partner (GCSI), avoiding costly external procurement. / • Flights, accommodation, and subsistence capped at FCDO GEG rates to maximises the proportion of spend going directly to technical delivery and capacity-building rather than administrative costs / • Activity-Based Budgets (ABBs) will be used to track spending against deliverables, ensuring transparency and accountability.	• Activity-Based Budgets (ABBs). / • Financial reconciliation of invoices against agreed milestones.
Efficiency (maximising outputs from inputs)	Converting inputs into outputs with minimal waste.	• Phased design (needs assessment → co-development → training) allows real-time course correction and allowing costs to be monitored in real time at each stage / • Shared learning and templates from previous GCSI projects in Ghana, South Africa, and Somalia reduce duplication and speed delivery. / • Use of remote/virtual support where possible to reduce travel costs.	• Monthly financial and narrative reporting. / • Benchmarking against cost profiles of prior GCSI programmes.
Effectiveness (achieving intended outcomes)	Ensuring outputs deliver the planned results.	• Co-development with GoS ensures strong ownership and relevance. / • Delivery focused on building sustainable capability (communications strategy, cross-government working group, maturity model) to reduce risk dependency and increase LT return on investment. / • Regular reviews against Theory of Change and Results Framework ensure activities remain outcome-focused.	• bi-monthly (every two months) reports aligned to Results Framework. / • Maturity Model Assessment (before and after). / • Evidence of adoption of tools and improved public understanding of reforms.
Equity (ensuring fairness and inclusion)	Ensuring benefits are distributed fairly, reaching the most marginalised.	• Audience insight research disaggregated by gender, age, geography where feasible. / • Communications messaging to address concerns of vulnerable groups, particularly women, youth, and people with disabilities. / • Embedding inclusion checks into comms outputs to ensure accessibility.	• Equality Impact Assessment (EiA) updated during delivery phases. / • Monitoring of participation (gender, disability inclusion). / • Engagement with CSOs and youth groups to validate inclusiveness of messages.

What do you anticipate the maximum project value will be?

Approximately £125k (£124,910)

Commercial Case

How will delivery partners be selected? What funding arrangements are likely to be used?

Delivery partners will be the UK Government’s Government Communication Service International (GCSI). GCSI was chosen because it is uniquely positioned to deliver this programme:
- It has proven experience providing technical assistance in similar contexts (e.g. Ghana, South Africa, Somalia) and brings the latest best practice.
- It is a government-to-government partner, ensuring discretion, credibility, and alignment with the UK’s wider reform support package with other UK institutions (FCDO, HMT, NAO).
- The programme explicitly requires skills and expertise that are not available locally, but which the UK can provide as a comparative advantage, particularly in strategic communications frameworks (OASIS), behavioural insights, and cross-government coordination mechanisms.
In this context, no competitive procurement is required. The selection of GCSI is justified because it is the best suited and sole delivery body able to provide this level of UK expertise, and because it ensures value for money by leveraging existing HMG resources. Post will cover professional fees for the deployment of two full-time personnel assigned to this mission, as well as associated logistical costs for two field visits: one-week design mission in Q3 and a two-week delivery period in Q4. This mission aims to facilitate direct engagement with government stakeholders and will include expenses such as travel, accommodation, and operational support.
To ensure accountability, funds will be channelled through a UK Government Memorandum of Understanding (MoU) between FCDO and GCSI, with robust oversight through monthly reporting and quarterly reviews. This approach guarantees both value for money and assurance that delivery is consistent with FCDO standards and ODA eligibility.
How will the programme manage the risk associated with delivery through each partner?
Specifically how you will approach due diligence on partners in a proportionate way beyond the necessary background checks on potential partners.
Proportionate Due Diligence Approach
Because the delivery partner is part of the UK Government, the programme benefits from a high degree of built-in assurance. GCSI staff are subject to the Civil Service Code, FCDO safeguarding standards, and robust UK Government recruitment and vetting processes, including SC and DV security clearances. This significantly reduces fiduciary, safeguarding, and delivery risks compared to external contractors.
However, to ensure compliance with FCDO rules and to maintain accountability, the programme will adopt a proportionate due diligence framework beyond baseline checks. This will include:
1. Formal Agreements
  1. A Memorandum of Understanding (MoU) between FCDO and GCSI will set out roles, responsibilities, and conditions of engagement.
  2. The MoU will explicitly cover:
    1. Safeguarding and SEAH obligations.
    2. Aid diversion prevention measures.
    3. Financial probity requirements, including invoicing procedures and verification of deliverables.
2. Governance and Oversight
  1. A Senior Responsible Owner (SRO) (Development Counsellor) will hold ultimate accountability for delivery.
  2. A Programme Responsible Owner (PRO) (Senior Programme Manager) will oversee day-to-day implementation, including close engagement with GCSI counterparts.
  3. Oversight will be embedded through fortnightly programme meetings, where delivery progress, risks, financial forecasts, and lessons learned will be reviewed.
3. Monitoring and Verification
  1. The team will engage in fortnightly governance meeting to get progress updates and problem solve on risk and issues.
  2. GCSI will provide monthly reports and quarterly reviews, which the PRO will quality-assure.
  3. Deliverables (communications audit, insights analysis, training outputs, maturity model) will be validated by Post through spot-checking (e.g., attending training, reviewing comms products) to confirm delivery has taken place as reported.
  4. Financial oversight will be maintained through activity-based budgets and reconciliation of invoices against agreed milestones.
4. Escalation and Contingency
  1. Any material risks identified (e.g., disengagement by GoS counterparts, slippage on deliverables, or safeguarding concerns) will be escalated to the SRO and, if needed, the Head of Mission.
  2. Corrective action will be agreed in programme review meetings, and activities may be paused or re-scoped if risks cannot be adequately managed.

Delivery Risks	Likelihood (no mitigation)	Impact (no mitigation)	Mitigation Measures	Risk Owner
Delays in deployment due to GCSI staff availability or scheduling conflicts with other country programmes.	Medium	Medium	Plan deployments well in advance; build flexibility into scheduling; ensure contingency by identifying back-up experts from GCSI roster.	PRO (Senior Programme Manager)
Capacity overstretch: risk that GCSI is supporting multiple posts simultaneously, reducing focus on Senegal.	Low	Medium/High	Agree dedicated FTE allocation in MoU; hold fortnightly check-ins to confirm resource availability; escalate to SRO if resourcing gaps emerge.	SRO (Development Counsellor)
ScDelivery slippage: outputs not delivered to agreed quality or timeframe.	Low	Medium	Agree plans in advance with Cabinet Office ensuring resources are available to deliver on time. Regular coordination discussions. PRO to quality-assure all outputs before acceptance.	PRO, with oversight by SRO
Reputational risk if GCSI comms advice is perceived as political messaging rather than technical assistance.	Low/Medium	High	Ensure all outputs are framed as technical capacity-building; GoS officials to be the public-facing messengers; Post Comms Team to advise on sensitive outputs.	SRO, supported by Comms Team

Financial Case

Outline the total budget, its source and where applicable the allocations for each financial year for the programme.

Indicative budget (to be finalized after the scoping mission through the workplan):

Total budget and source
The programme has a total budget of £124,981.45 for FY 25/26, funded through FCDO resources. The budget allocation is weighted towards the second half of the year, with £65,982.80 (53%) in Q3 and £58,998.65 (47%) in Q4, reflecting the project's alignment with the GoS x IMF programme timeline and the UKG design mission now scheduled for November 2025.
Main cost drivers
The primary cost drivers for this project stem from the specialist nature of the intervention and operational requirements in Senegal.
Professional fees represent the largest component at £90,986.25 (73% of total budget), reflecting the need for experienced UK Government strategic communications experts with English and French-language capabilities and (ideally West) African economic reform experience. GCSI will deploy teams of 2 members to carry out programme activities. The multi-grade structure reflects the complexity of the project and the need for appropriate expertise levels in delivering complex economic reform communications in challenging political environments.
Travel and accommodation costs constitute £33,995.20 (27% of budget), driven by two deployments including the one-week design mission in Q3 and a two-week delivery period in Q4, totalling around 44 days in-country for three consultants over the course of the project. Distance from the UK to Senegal necessitates long-haul flights at approximately £1,600 per person per return journey. Hotel accommodation costs of £180 per night reflect security and quality requirements for UK Government officials operating in Dakar. However, in practice, individual travel, accommodation and related subsistence costs may likely end up cheaper than the maximum allowance set out in the Geographical Expenditure Guide (GEG) allowing for a reallocation of resources for more staff days.
Efficiency measures
The budget demonstrates efficiency through phased delivery aligned with IMF timeline developments, avoiding premature deployment costs. Audience insight activities include benchmarked public opinion polling costs of £15,000, representing value-for-money research in the Senegalese market. The project structure maximises impact by front-loading capability assessment and strategic planning before intensive delivery phases, ensuring targeted intervention where GoS needs are greatest.

Activity 1: Project Management (including financial management and reporting)					YTD
Description	Calculator	Stage	Cost/Unit	Unit	Units	Cost
G6 oversight	G6	Professional Fee	895	Per Day	4.00	£3,580.00
G7 reporting and coordination	G7	Professional Fee	795	Per Day	12.00	£9,540.00
SEO reporting and coordination	SEO	Professional Fee	695	Per Day	10.00	£6,950.00
					Fees	£20,070.00
					Costs	£0.00
					Total	£20,070.00

Activity 2: Communications Audit and Baseline Needs Assessment (including a one-week design mission deployment)					YTD
Description	Calculator	Stage	Cost/Unit	Unit	Units	Cost
G6 stakeholder interviews, writing, review and clearance	G6	Professional Fee	895	Per Day	12.00	£10,740.00
G7 stakeholder interviews, writing	G7	Professional Fee	795	Per Day	14.00	£11,130.00
G7 insights, research, evaluation	G7	Professional Fee	795	Per Day	1.00	£795.00
Flights	Flights	Staff Cost	1600	Per Person Per Flight	2.00	£3,200.00
Hotel	Accommodation	Staff Cost	180	Per Person Per Night	16.00	£2,880.00
Subsistence	Expenses	Staff Cost	66	Per Person Per Day	16.00	£1,056.00
Vaccinations, antimalarials, etc.	Expenses	Staff Cost	300	Per Person	2.00	£600.00
Taxis	Expenses	Staff Cost	6.60	Per Trip	48.00	£316.80
					Fees	£22,665.00
					Costs	£8,052.80
					Total	£30,717.80

Activity 3: Audience Insight and Media Analysis					YTD
Description	Calculator	Stage	Cost/Unit	Unit	Units	Cost
G6 insights, research, evaluation, oversight	G6	Professional Fee	895	Per Day	1.00	£895.00
G7 insights, research, evaluation	G7	Professional Fee	795	Per Day	2.00	£1,590.00
SEO insights, research, evaluation	SEO	Professional Fee	695	Per Day	8.00	£5,560.00
Public opinion polling	Research and Insight	Insights	15000	Per Poll	1.00	£15,000.00
					Fees	£8,045.00
					Costs	£15,000.00
					Total	£23,045.00

Activity 4: Strategic Communications Advisory and Training (including a two-week deployment)					YTD
Description	Calculator	Stage	Cost/Unit	Unit	Units	Cost
G6 oversight	G6	Professional Fee	895	Per Day	1.75	£1,566.25
G7 planning, delivery	G7	Professional Fee	795	Per Day	22.00	£17,490.00
SEO planning, delivery	SEO	Professional Fee	695	Per Day	22.00	£15,290.00
Flights	Flights	Staff Cost	1600	Per Person Per Flight	2.00	£3,200.00
Hotel	Accommodation	Staff Cost	180	Per Person Per Night	28.00	£5,040.00
Subsistence	Expenses	Staff Cost	66	Per Person Per Day	28.00	£1,848.00
Vaccinations, antimalarials, etc.	Expenses	Staff Cost	300	Per Person	1.00	£300.00
Taxis	Expenses	Staff Cost	6.60	Per Trip	84.00	£554.40
					Fees	£34,346.25
					Costs	£10,942.40
					Total	£45,288.65

Activity 5: Monitoring and Evaluation (including Theory of Change, Results Framework and GESI Analysis)					YTD
Description	Calculator	Stage	Cost/Unit	Unit	Units	Cost
G7 insights, research, evaluation	G7	Professional Fee	795	Per Day	3.00	£2,385.00
SEO insights, research, evaluation	SEO	Professional Fee	695	Per Day	5.00	£3,475.00
					Fees	£5,860.00
					Costs	£0.00
					Total	£5,860.00

How will you manage financial risks?
This includes how you will ensure funding is paid to the intended recipient and only be used for the purposes formally agreed. This could be as simple as, for example, receiving receipts, checking that an event took place by attending, or doing (post event/delivery) checks. Where applicable, indicate how FCDO funding will be tracked, and how often forecasts will be updated.

- Monthly invoices, receipts attached
- Monthly Activity Based Budgets with actuals and forecasts - discussions on an any major shifts in spend
- Monthly reporting providing update on delivery and quarterly reports on delivery
- Monitoring and evaluation of delivery

Management Case

Governance arrangements and Programme Management Team
How will the programme be managed and governed?
Include the governance mechanism for selection and approval of individual projects, who will take on the roles of the Senior Responsible Owner and Programme Responsible Owner, and how Project Officers/Leads will be assigned.

Governance Mechanism
Given that this is a single, stand-alone programme with a budget under £250,000 and limited scope, governance will be deliberately light and proportionate. Oversight will be embedded within Post’s existing structures to ensure coherence and alignment with the Country Business Plan, without the need for multiple project officers or leads. The HMA acts as the overall risk owner for all development spend in country, ensuring consistent oversight and accountability. GCSI will work closely with the PRO to manage the budget and provide regular updates through fortnightly meetings, monthly reports, and bi-monthly reviews. The SRO will receive frequent updates from the PRO and participate in bi-monthly meetings to assess progress against agreed targets and trajectories. Delivery and decision-making are further supported by the monthly programme board, chaired by the HMA, which provides a structured forum for monitoring progress, managing risks, and enabling timely decisions. This setup strengthens coordination, ensures strategic alignment, allows for early identification of challenges, and enables rapid escalation when needed.
Senior Responsible Owner (SRO)
The Development Counsellor, who is the equivalent of a Development Director, will act as the SRO. The Development Counsellor leads the Growth and Development country business plan goal and is best placed to provide strategic direction, ensure alignment with UK objectives, and maintain high-level engagement with the Government of Senegal and HMG stakeholders.
Programme Responsible Owner (PRO)
Day-to-day management will be led by the Senior Programme Manager, who will serve as the PRO. The PRO will be responsible for operational delivery, budget management, coordination with GCSI, and regular reporting.
Project Officers/Leads
Given the programme’s scale and the fact it is a single technical assistance project, there will be no dedicated Project Officers or Project Leads. Instead, the SRO and PRO will jointly manage delivery, supported as necessary by the Embassy’s corporate and programme teams for financial compliance and reporting.
Decision-Making
- Selection and approval of programme activities will rest with the SRO, based on the Business Case criteria.
- The PRO will provide regular updates to the SRO and discuss key decisions and developments.
- The PRO will provide recommendations and oversee implementation, ensuring compliance with FCDO standards.
- Regular updates will be provided through monthly reports and quarterly reviews, with escalation to the HoM as required through the monthly programme board.
Monitoring and Reporting
Please describe the lines of accountability, responsibility, and reporting from projects to the programme and the portfolio. Also describe how projects delivery will be monitored
Accountability and oversight
- The SRO – the Development Counsellor – holds ultimate accountability for ensuring that the programme delivers its objectives and remains aligned with Post’s strategic priorities and the Country Business Plan. The SRO will provide strategic steer, approve any major adjustments, and report to the Head of Mission as required.
- The PRO – the Senior Programme Manager – has day-to-day responsibility for delivery. The PRO will manage engagement with GCSI, track budgets and deliverables, and escalate risks or issues to the SRO in a timely way.
- The delivery partner (GCSI) is responsible for carrying out the agreed work programme and for submitting regular updates, reports, and evidence products to Post.
Reporting lines
- GCSI will report directly to the PRO, who will synthesise and quality assure their inputs.
- The PRO will provide weekly updates and monthly reporting to the SRO, including budget, progress against milestones, and risk management.
- The SRO will consolidate programme-level reporting into the wider growth portfolio, ensuring visibility in embassy-wide programme boards and into London where required.
### Monitoring and evaluation of delivery
To ensure effective monitoring and learning, GCSI will embed standard FCDO-compliant M&E tools into delivery, which the PRO will review and validate:
- Monthly updates and quarterly reports capturing progress, risks, spend, and lessons learned.
- A clear Theory of Change, co-developed with Post, setting out the causal pathways linking inputs to outcomes, and reviewed at mid-point and close-out.
- A Results Framework, with agreed baselines and indicators, used to track progress against outcomes such as improved government communications capacity and public understanding of reforms.
- A Maturity Model Assessment to benchmark GoS communications capability at the start and end of the programme, providing tangible evidence of capacity development.
Monitoring mechanisms
- The PRO will convene fortnightly programme meetings with GCSI to review deliverables and discuss risks and issues.
- GCSI will share monthly reports on progress, financial forecasts and risks.
- A bi-monthly (every two months) review meeting, chaired by the SRO, will test progress against outcomes, provide political steer, and authorise any adaptive changes to delivery.
- A monthly programme board will allow for internal oversight and monitor alignment and consistency with Post CPB and escalation to HMA when needed.
- Independent validation of activities will be carried out by Post (e.g., attending training sessions, reviewing communications products, consulting GoS counterparts) to ensure delivery is real and impactful.
Risks
Summarise the main risks to the programme and mitigation measures as appropriate.
Describe who owns the risks for the programme, and where appropriate for individual projects. For example, stating the name of the specific team that owns the risk.

You may wish to use a table like this to summarise risks.
State the overall programme risk assessment, and whether it is within the overall risk appetite.
This programme operates in a highly sensitive environment, where Senegal is navigating a severe debt crisis, IMF negotiations, and politically challenging reforms. The risks are primarily operational, political, and reputational. They are proportionate to the small programme size but need to be managed carefully.
Risk Type	Description	Likelihood (no mitigation)	Impact (no mitigation)	Mitigation Measures	Risk Owner
Operational	Limited engagement from the GoS – ministries deprioritise communications, or coordination mechanisms are not adopted.	Low/Medium	Medium	Engagement levels tested upfront via audit; phased delivery to identify gaps early; Post will use senior relationships to re-engage.	PRO with oversight by SRO
Operational	Limited capacity within GoS to sustain outputs and apply tools post-programme.	Low	Medium	Baseline assessment of skills and resources; co-development of tools; training-of-trainers approach; maturity model to track progress.	PRO with GCSI.
Political	Changes in government personnel (reshuffles or turnover) disrupt continuity.	Medium	High	Focus engagement on career civil servants, not just political appointees; maintain multiple contacts across ministries to avoid reliance on single individuals.	SRO
Political	Distrust of the IMF escalates into opposition to reforms, undermining the programme’s relevance.	Medium	High	Maintain open dialogue with GoS; integrate public sentiment insights into comms outputs; work with CSOs to ensure citizen concerns are addressed in messaging.	SRO, supported by PRO and Post Political/Economic Team.
Reputational	UK engagement in Senegal’s economic reform process is seen as western meddling, in a context of historical distrust in the IMF	Medium	High	Ensure engagement with GoS is discreet and built on trust and understanding, working closely with stakeholders to understand context and needs	SRO, with Comms Team at Post.