Guidance on completing this form can be found in Annex 1 of the Managing Smaller Projects in Programmes PrOF Guide

Business Case Template - Smaller Projects in programmes

Portfolio/ Business/Country Plan Summary [300 words maximum]: [insert a summary of the relevant Portfolio/Business/Country Plan from your department here] / The British Embassy Dakar’s country plan for FY 2025/26 sets out an agenda to deepen the UK–Senegal partnership at a time of significant economic and political transition. Our mission is to build a strategic, responsive, and mutually beneficial relationship that aligns UK expertise and investment with Senegal’s development priorities, while advancing mutual growth, security, and influence in West Africa. / Senegal remains one of the most stable democracies in the region, but faces acute challenges: very high levels of debt following unprecedented debt misreporting by the previous government, suspension of IMF support (though new programme negotiations are underway), and significant development needs (i.e. youth unemployment, inequalities, malnutrition and food insecurity, negative impact of climate change). / These challenges are coupled with strategic opportunities for the UK: Senegal is actively diversifying partnerships and has approached the UK for further support for their Just Energy Transition Partnership, to support their ambition for 40% renewable energy by 2030. / Senegal is a ‘category 3’ Investment and Expertise Development Partnership country for the UK. The Embassy’s priorities are organised around three interconnected goals: / Growth and Development: – Growth is by far the largest aspect of our bilateral relationship; the UK is the largest investor in energy, with sizeable investments in infrastructure, telecommunications and agriculture, including by UKEF, BII and PIDG. The UK is a partner to Senegal’s Just Energy Transition Partnership, and Manufacturing Africa operates here. We also launched a £13 million partnership with Institut Pasteur de Dakar to strengthen health research and pandemic preparedness, and through the WISH programme, we are supporting SRHR, helping avert thousands of unintended pregnancies and unsafe abortions. / Defence and Security – Collaborating on defence and security to enhance Senegal’s capacity to counter violent extremism, organised crime, and malign state actors, while growing UK operational access and influence through defence cooperation. / Core Service Delivery – maintaining a high-performing embassy platform, delivering consular and crisis services, and leveraging cultural and educational programmes to strengthen soft power.
Programme Title: Unlocking the potential of the clean energy-water nexus in Senegal’s Just Energy Transition Partnership
Programme summary (100 words maximum): / This programme will be delivered by the Global Green Growth Institute (GGGI) and strengthen Senegal’s capacity to mobilise private investment for its energy transition by improving project bankability and institutional capability through two main projects. Firstly, to support FONSIS (Senegal’s sovereign wealth fund ) through a feasibility study for 50 solar-powered water-pumping stations in the Northern Senegal, under the Renewable and Efficient Energy Fund (REEF) — a specialised investment vehicle to accelerate renewable energy and energy‑efficiency projects in the country. Secondly, the programme will support capacity-building within Senegal’s Ministry of Energy to develop a bankable JETP project in water-energy.
Programme Value: £221,687.87		Directorate/Department/Post/ Region or Sector:
Post confirmation of review processes		All processes for BC approval have been followed
Contact names		SRO: Nafissatou BALDE / PRO: Maty NGOM
Threshold for final approval of Business Case: Carine Robarts (HoM, BE Dakar)
Business Case approval:	19/12/2025	Name and role of Approver: Carine Robarts, HoM
Programme Code: 400869	Programme Start Date: 10/01/2026		Programme End Date: / 30/06/2026
Overall risk rating:	Moderate
Teams link:	GGGI business cases approval.pdf 20251229_GGGI-FONSIS_Business Case Template for Small Projects Programmes.docx

Business Case
For a Smaller Projects programme

Strategic Case

What are the context issues/ problem you plan to address through your programme outcomes?

Senegal joined the Just Energy Transition Partnership (JETP) in 2023 with a headline target to lift renewables to 40% of the power mix by 2030 and expand total generation capacity by 40%. The International Partners Group (IPG) announced €2.5 billion over 3–5 years to back Senegal’s JETP, including £46 million of UK support channelled through PIDG. Yet, since signature, the JETP has struggled to attract private finance, primarily because the project pipeline is not well developed, and government counterparts have historically prioritised public financing (grants/concessional loans). With fiscal space tightening amid a debt crisis, Senegal now needs to mobilise private capital to meet energy‑transition and energy‑access (100% national access by 2030) goals.

The government has designated REEF as the key instrument for channelling the IPG’s JETP financing to the private sector; however, the maturity of the project pipeline and the readiness of governance arrangements still fall short of partners’ requirements and standards, including the UK’s. To close these gaps, Senegal’s Ministry of Energy and GGGI signed an MoU to strengthen institutional and technical capacity for bankable energy-water nexus investments.

As an IPG member, the British Embassy (BE) Dakar has therefore decided to collaborate with GGGI by financing targeted technical assistance (TA) for two workstreams aligned with the JETP and REEF priorities:
(i) Preparing a feasibility study and scale‑up business case for solar‑powered irrigation in 50 sites in Senegal, under the REEF (which will include update to CAPEX/OPEX, refining revenue models, the investment pitch; ~50 pumping stations for Société nationale D'Aménagement et d'Exploitation des Terres du Delta de Fleuve Sénégal (SAED) as the initial cohort) to inform the creation of a Special Purpose Vehicle. (ii) Supporting the Ministry of Energy in structuring one high‑priority energy-water nexus project (gap assessment, development of a methodology and knowledge products) and strengthen the Ministry’s capacity on project structuration.

What are the intended policy objectives/outcomes for the programme? Include any specific deliverables where known.

The overarching key purpose of the programme is to strengthen Senegal’s capacity to mobilise financing for energy-water nexus projects by improving the project pipeline and enhancing the Ministry of Energy’s capabilities in project structuring. This should be reached via the following objectives over a 5 month period (mid Jan to end of June):

Impact
Outcome: Increased investment readiness for energy –water nexus projects within the JETP framework
Output 1: Feasibility and business case prepared for scaling solar-powered irrigation through a proposed SPV, aligned with REEF investment principles	Output 2: One JETP – aligned Energy-Water Nexus project structured to investment-ready level	Output 3: Institutional capacity strengthened to structure energy-water nexus projects under the JETP
Output 1.1: / A feasibility study of 50 of the 200 pumping stations already identified is being updated representing approximately 10 MWp / design data collection tools, report templates, analyze field surveys, estimate CAPEX and OPEX, and conduct financial analysis. / Output 1.2: / Development of a revenue model for the SPV: indicative revenue and cash-flow model for a proposed SPV to inform investment structuring and investor engagement developed by March 2025. / Output 1.3: / Investor-facing pitch deck to support engagement with potential financiers created by March 2025.	Output 2.1: / Assessment of gaps in WEN Projects in the JETP Investment Plan conducted by March 2025 and one selected for effective structuring by March 2025. / Output 2.2: / Project structuring investment readiness.	Output 3.1: / Capacity built on financial structuring of WEN projects including an Implementation guide through 3 capacity-building workshops for the ministries of energy and water and their related agencies. / Output 3.2: / One policy brief for effective stakeholder engagement developed to operationalize energy-water nexus approaches in projects. / Output 3.3: / A Nexus evaluation model (NEM) for investments in energy and water projects developed

By completion, GGGI will have delivered:

- A feasibility and scaling business case for solar irrigation, including financial analysis and SPV model.
- An improved project package for a clean energy–powered water system.
- A practical guide for structuring future JETP-aligned projects.

All outputs will be formally handed over to MoE and partners (e.g., SAED, FONSIS) for next-phase implementation, including SPV establishment and investor engagement. GGGI will not retain operational responsibilities beyond the project period, ensuring local ownership and continuity.

What is the rationale for FCDO spending?

The programme supports delivery of BE Dakar’s Country Business Plan (Goal 2: Growth and Development) and UK priorities under the UK’s Africa Approach, which emphasises renewable energy development and the shift from donor to investor. To deliver this in Senegal, we need to maintain UK credibility and influence within Senegal’s Just Energy Transition Partnership (JETP) while addressing systemic barriers to finance mobilisation, to ensure a sustainable JETP that is not reliant on grants. The Government of Senegal remains strongly committed to JETP objectives but increasingly voices concern about its ability to secure the necessary investments.

While all parties acknowledge that the quality of the project pipeline is a major obstacle to unlocking finance, few funders have the flexibility or resources to improve project readiness. Under these circumstances, the most effective way for the UK to maintain credibility with Senegalese authorities and the IPG is to respond positively to targeted requests from the Ministry of Energy. This approach has already proven successful and delivered value for money on two previous occasions, when the British Embassy in Dakar funded technical assistance to shape the JETP’s strategic direction and develop its monitoring and evaluation system. Reaffirming this responsiveness now would strengthen the UK’s reputation as a pragmatic and flexible partner, even if not the largest financial contributor to the JETP. It would also ensure that UK support translates into tangible outcomes: high-quality projects developed with FONSIS and MEPM that can later serve as credible candidates to mobilise private capital, including through PIDG and other UK investors.

What are the risks associated with this programme and potential individual projects?

The programme faces several risks related to delivery, governance, and external factors. These risks will be managed through proportionate controls embedded in the governance structure described in E.1, with clear ownership assigned to the British Embassy Dakar and delivery partners.

Risk Ownership
- Programme-level risks: owned by the Senior Responsible Owner (SRO) – British Embassy Dakar Climate Adviser – who reports to the Development Counsellor.
- Operational risks: managed by the Programme Responsible Owner (PRO) – Senior Programme Manager – with escalation to the SRO.
- Delivery risks: shared with GGGI for technical implementation and MEPM/FONSIS for institutional engagement.
- Strategic risks: escalated to the Development Counsellor through the Programme Steering Committee.

Category	Risk	Likelihood	Impact	Mitigation Measures
Programme-Level	Safeguarding (SEAH)	Low	High	GGGI applies zero-tolerance SEAH policy, mandatory training, and clear reporting pathways. Embassy oversight ensures compliance with FCDO safeguarding standards.
	Environmental and Social Safeguards	Low	Medium	Compliance with GGGI’s ESSP and FCDO standards. Screening and mitigation plans integrated into project design.
	Data Protection	Low	Medium	Adherence to GGGI’s Rules on Protection of Personal Data and FCDO requirements. Secure data handling and privacy-by-design principles applied.
Operational	Tight implementation timeline creates a significant risk that the project will not be launched and executed effectively within the available window, limiting its ability to achieve meaningful results	Medium	High	Maintain close coordination with the UK Embassy and FCDO for rapid decision-making; pre-clear documentation and legal reviews to avoid bottlenecks; prioritize critical-path activities; adopt agile planning with contingency buffers; and sequence deliverables to maximize early impact.
	Delay in feasibility study consultant procurement	Medium	High	Begin selection process early and secure clearances before contract signature to enable rapid mobilization post-signature.
	Government responsiveness in validating deliverables	Moderate	High	Establish an ad-hoc project monitoring committee and maintain high-level engagement between the resident representative and relevant directors/ministers.
Delivery	Delay in JETP project identification and confirmation	Low	High	Project prioritization completed with MEPM; seek formal confirmation before contract signing to ensure readiness at project start.
	Failure of the consulting firm in charge of feasibility studies	Low	High	Apply a rigorous selection process and require a multidisciplinary team to ensure quality and resilience.
Strategic	FONSIS project supported through this programme may ultimately not be approved by the future REEF governance board	Medium	High	Close engagement with MEPM and FONSIS through biweekly Steering Committee meetings. Rapid escalation to Development Counsellor or Ambassador if delays or policy shifts occur.
	Change in government counterparts	Low	Medium	Identify multiple points of contact (principal and deputy) for each institution to ensure continuity.

How will the programme ensure compliance with FCDO rules/commitments on:

ODA eligibility
Senegal is fully eligible for ODA. Furthermore, by supporting project structuring and institutional capacity for energy–water nexus investments, the programme directly contributes to SDG6 (Clean Water and Sanitation) and SDG7 (Affordable and Clean Energy), ensuring that UK ODA resources are used to accelerate inclusive and sustainable development.
Gender equality
The programme will integrate gender considerations throughout its design and delivery, guided by GGGI’s Gender and Social Inclusion (GESI) Strategy. Gender risk screening and action planning will be applied at project level, and Gender Policy Markers based on OECD DAC methodology will ensure that gender equality is mainstreamed. GGGI’s corporate target is that at least 75% of projects significantly integrate gender and/or poverty dimensions. Capacity-building workshops will actively promote women’s participation when possible.
Disability inclusion
Disability inclusion is embedded within GGGI’s broader social inclusion approach, applying an intersectionality lens to identify and address barriers faced by marginalised groups. Accessibility considerations will be integrated into the design and delivery of capacity-building activities, and monitoring and evaluation will capture participation by persons with disabilities. This ensures that the programme promotes equal opportunity and avoids reinforcing existing inequalities.
Public Sector Equality Duty
The programme will uphold principles of non-discrimination and equality of opportunity in all activities. Institutional strengthening will include inclusive stakeholder engagement and the development of policy briefs that reflect the energy–water nexus approach, ensuring that public institutions are equipped to design and implement projects that benefit all segments of society.
Inclusive Data Charter Action Plan - GOV.UK (www.gov.uk)
The programme will collect, and report disaggregated data on gender and social inclusion in line with IDC principles and GGGI’s GESI Strategy. Data management will comply with GGGI’s Rules on Protection of Personal Data, which mandate lawful, fair, and transparent processing, strong security measures, and privacy by design. These safeguards ensure responsible handling of personal information while enabling robust monitoring of inclusion outcomes.
Safeguarding, against Sexual Exploitation, Abuse and Harassment.
Delivery will follow UK civil service standards. We will use a MoU with explicit SEAH clauses, due-diligence, and fortnightly governance meetings. As well, GGGI applies a zero-tolerance policy to SEAH, as outlined in its Rules on Preventing Sexual Exploitation, Abuse and Harassment. All staff and consultants will undergo mandatory training on prevention of sexual exploitation and abuse (PSEA). Clear reporting pathways and whistle-blower protections are in place, and SEAH risk assessments will be integrated into project planning and risk management processes. These measures ensure that all programme activities are delivered in a safe and respectful environment. Reporting lines include monthly reporting, bi-monthly (every two months) reviews, and activity-based budgets to surface and address risks promptly.
Impact on climate and the environment.
The programme consists primarily of studies and capacity‑building activities, so no significant negative impacts are expected. However, it will indirectly contribute to the development of 50 solar‑powered pumping stations, which could reduce approximately 10,000 tonnes of greenhouse gas emissions annually by replacing fossil‑fuel‑based pumping systems with clean energy solutions. By promoting renewable energy for water supply systems and strengthening national capacities to attract financing across the Energy-Water nexus, the programme supports both mitigation and adaptation objectives while enhancing food security and improving sustainable livelihoods.
Human rights (HR) assessment.
GGGI’s Environmental and Social Safeguard Policy (ESSP), effective January 2026, provides a risk-based framework for identifying and managing human rights risks. All activities will undergo systematic risk screening and impact assessment, and mitigation measures will be incorporated into project design. This ensures that the programme respects and promotes human rights throughout its implementation. A comprehensive due diligence will be conducted to assess and assert GGGI’s trustworthiness as a partner to deliver on this mission.

Appraisal Case

Describe the criteria under which each Project in the programme will selected for funding.
Instead of an appraisal of delivery options, Posts or Directorates should set out proportionate processes and criteria for selecting and approving individual Projects within the Business Case.
The projects were selected through consultations between BE Dakar and GGGI. GGGI returned to FONSIS and MEPM to validate the selected projects, secure institutional anchoring, and clearly define the scope, activities, and expected deliverables. This step ensured full ownership by national counterparts and alignment with existing investment pipelines. Notably, the SPV project had already been assessed and retained by PwC during its REEF scoping mission based on its maturity, profitability, and expected impact, reinforcing its suitability for rapid implementation.
Selection criteria (applied to both projects)
1. Strategic alignment
  1. Direct alignment with MEPM/FONSIS priorities, Senegal’s JETP commitments, and the Energy–Water Nexus approach.
  2. Contribution to SDG6 (Clean Water and Sanitation) and SDG7 (Affordable and Clean Energy).
2. Maturity and feasibility (time-bound delivery)
  1. Availability of baseline technical and financial information and access to operational data.
  2. Finalize the feasibility and business case (Project A) within the 4–5 months window or Credible readiness to advance to investment ready (Project B).
3. Investment potential and value for money
  1. Clear pathways to finance under REEF/JETP (e.g., bankability, revenue model robustness, risk allocation).
  2. Ability to unlock existing commitments (rather than designing new policy frameworks), with proportionate TA costs relative to mobilised and catalysed capital.
4. Impact potential
  1. Anticipated GHG emission reductions, and contribution to resilience in rural communities.
  2. Replicability and scalability beyond the project period.
5. Institutional ownership and delivery practicalities
  1. Formal endorsement and nominated focal points from MEPM/FONSIS and relevant agencies (e.g., SAED, ANER, OFOR, ASER).
  2. Absorptive capacity to deploy funds rapidly and validate decisions in time (e.g., ability to convene data owners, approve assumptions, and sign off outputs).

How will value for money be delivered throughout the programme and in each project?

Aligned with PrOF guidance on Value for Money (VfM), the programme clearly demonstrates all four principles: economy, efficiency, effectiveness, equity.

Dimension	Definition	How the Programme Delivers VfM	Evidence / Monitoring
Economy (minimising the cost of inputs)	Procuring and deploying resources at the best price.	• Use of GGGI as a non-profit delivery partner with existing in-house expertise, avoiding costly recruitment and high-fee private consultants. • External inputs procured by GGGI under British Embassy oversight to ensure competitive pricing and quality. • Operational costs minimised by hosting meetings and workshops at British Embassy, MEPM, or GGGI premises rather than rented venues.	• Activity-Based Budgets (ABBs) tracking spend against deliverables. • Financial reconciliation of invoices against agreed milestones. • Procurement records and competitive selection documentation.
Efficiency (maximising outputs from inputs)	Converting inputs into outputs with minimal waste.	• Programme design leverages GGGI’s existing technical capacity and prior pilot results, reducing duplication and accelerating delivery. • Short implementation window (5 months) with focused outputs ensures resources are concentrated on high-impact deliverables. • Use of virtual/remote sessions where feasible to reduce travel costs. • Shared logistical arrangements with Embassy and MEPM to avoid overheads.	• Monthly financial and narrative reporting. • Benchmarking against cost profiles of similar technical assistance programmes. • Progress reviews at mid-point and end of project.
Effectiveness (achieving intended outcomes)	Ensuring outputs deliver the planned results.	• Co-development with MEPM and FONSIS ensures strong ownership and relevance. • Outputs directly linked to unlocking larger volumes of finance under JETP and REEF pipelines • Delivery focused on investment-ready project packages and SPV business case to catalyse future financing. • Regular reviews against Theory of Change and Results Framework.	• Bi-monthly progress reports aligned to Results Framework. • Validation of outputs by MEPM and FONSIS. • Evidence of investor engagement and readiness of structured projects.
Equity (ensuring fairness and inclusion)	Ensuring benefits are distributed fairly, reaching the most marginalised.	• Capacity-building workshops designed to ensure participation of women and marginalized groups. • Disability inclusion embedded through accessibility considerations. • Inclusive data collection disaggregated by gender and social group.	• Monitoring of participation (gender, disability inclusion). • Workshop attendance records and feedback surveys.

What do you anticipate the maximum project value will be?
£221,687.87.

Commercial Case

How will delivery partners be selected? What funding arrangements are likely to be used?

Delivery Partner Selection
Given the urgency and technical specificity of the intervention, GGGI has been identified as the most suitable delivery partner for the following reasons:
- Institutional anchoring: GGGI is the historical technical supporter of FONSIS in structuring the REEF and has signed an MoU with MEPM to strengthen institutional capacity for project structuring.
- Technical expertise: GGGI brings proven experience in renewable energy, energy-water nexus, and investment structuring, and has published extensively on just transition, gender equality, and green jobs.
- Operational efficiency: As a non-profit intergovernmental organization, GGGI offers cost-effective delivery by leveraging in-house expertise and avoiding high-fee private consultants.
- Existing recent arrangements with FCDO: GGGI maintains existing Memoranda of Understanding with FCDO in other countries, which simplifies due diligence and reduces delivery risk by leveraging established governance and compliance frameworks.
In this context, no competitive procurement is required. The selection of GGGI is justified because it is the best-suited and sole delivery body able to provide this level of technical expertise within the required timeframe, and because it ensures value for money by leveraging existing institutional relationships and technical capacity.

Funding Arrangements
Post will cover professional fees for GGGI’s technical team assigned to this mission, as well as associated logistical costs for two key phases:
- Design and diagnostic phase (initial work sessions with MEPM and FONSIS to confirm scope and criteria).
- Delivery phase (structuring of one investment-ready project and preparation of the SPV business case for solar-powered irrigation).
Expenses will include travel, accommodation, and operational support for any required field visits, although these will be minimized through virtual engagement and use of existing premises (British Embassy, MEPM, GGGI offices).

To ensure accountability, funds will be channelled through an MOU between FCDO and GGGI, with robust oversight through:
- Activity-Based Budgets (ABBs) linked to outputs and milestones.
- Milestone-based disbursement upon delivery of agreed outputs (e.g., feasibility update, SPV financial model, investor pitch deck).
- Monthly reporting and bi-monthly reviews to monitor progress and compliance with FCDO standards and ODA eligibility.

This approach guarantees both value for money and assurance that delivery is consistent with programme objectives, while enabling rapid deployment of technical assistance to unlock significantly larger volumes of future investment under JETP and REEF.

How will the programme manage the risk associated with delivery through each partner?
Specifically how you will approach due diligence on partners in a proportionate way beyond the necessary background checks on potential partners.

Approach to Delivery Risk
The programme will adopt a proactive and proportionate approach to managing delivery risks associated with both GGGI (as the implementing partner) and the Ministry of Energy (MEPM) (as the primary government counterpart). Key measures include:
1. Regular coordination: fortnightly catch-up meetings between GGGI, the British Embassy Post, and monthly review meetings with MEPM and FONSIS to monitor progress, address emerging issues, and maintain alignment with agreed milestones.
2. Rapid escalation: Any significant delays or risks will be escalated immediately to the Development Counsellor for resolution, ensuring timely intervention.
3. External oversight: The programme will leverage the existing JETP Steering Committee and the International Partners Group (IPG) for strategic guidance and troubleshooting, providing an additional layer of governance and accountability.

Proportionate due diligence beyond background checks
Due diligence will go beyond basic checks and include:
- Institutional assessment: Review of GGGI’s governance, financial management systems, and compliance frameworks. GGGI already operates under robust international standards and has existing MoUs with FCDO in other countries, reducing risk and simplifying assurance.
- Benchmarking existing DDA: GGGI has completed Due Diligence Assessments (DDA) with FCDO in other countries. These will be used as a benchmark to expedite and complete the DDA for Senegal, ensuring consistency and reducing administrative burden while maintaining compliance.
- Performance and capacity review: Assessment of GGGI’s technical capacity and track record in Senegal, including prior delivery under REEF and JETP-related initiatives.
- Safeguards and inclusion compliance: Verification that GGGI applies its Environmental and Social Safeguard Policy, Gender and Social Inclusion Strategy, and SEAH prevention rules, ensuring alignment with FCDO standards.
- Financial controls: Activity-Based Budgeting (ABB) and milestone-linked disbursement will be applied, with monthly reporting and quarterly reviews to ensure transparency and accountability.
- Government counterpart engagement: MEPM’s role will be limited to strategic guidance and validation of outputs, reducing fiduciary risk. Institutional anchoring will be confirmed through formal letters and designated focal points.

Financial Case

Outline the total budget, its source and where applicable the allocations for each financial year for the programme.

Total Budget and Source
The programme has a total budget of £221,687.87 for FY 2025/26, funded through FCDO resources. The detailed budget shared previously did not include overhead costs. The difference in totals is explained by the 13% overhead (£25,503.87) applied to the subtotal of the detailed budget. This overhead covers essential administrative and operational support required for successful delivery.

Main Cost Drivers
The primary cost drivers reflect the technical complexity of the energy-water nexus intervention and operational requirements in Senegal:
- Professional Fees: This is the largest component of the budget, representing the need for senior investment and energy specialists, regional teams, and associates to deliver feasibility studies, project structuring, and capacity building. These roles are critical to ensuring investment readiness and alignment with Senegal’s energy transition priorities.
- Outsourcing: This line item covers the direct payment to the consulting firm responsible for conducting the feasibility study of 50 pumping stations.
  Clarification: Recruitment processes and other administrative expenses are not included in this line; they are covered through the 13% overhead and internal staff time allocated to the project.
- Travel and Events: Costs are driven by in-country missions for feasibility assessments and stakeholder engagement, as well as capacity-building workshops on financial structuring of the energy-water nexus.

Efficiency Measures
The budget demonstrates value for money through phased delivery aligned with project milestones, avoiding premature deployment costs. Activities such as feasibility studies and revenue model development are sequenced to maximise impact and ensure readiness for investment structuring. This approach ensures targeted interventions where Government of Senegal needs are greatest, while leveraging internal resources efficiently. Although the fees may appear high, they remain significantly lower than those charged by consultants for similar technical assistance. For instance, other UK programs in Senegal are paying approximately 525K (including VAT) for local consulting firms, and 463K for international consultancy within the same timeframe, underscoring the cost-effectiveness of this arrangement.

Activity 1.1: Project management (Month 1-6)
Category	Staff or budget item	Grade	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Country Representative	X11XINT	6	£ 817	£ 4, 901
1. Staff	Investment Lead, PM	X10INT	4	£ 698	£ 2, 792
1. Staff	Communication Associate	X5MID	10	£ 128	£ 1, 282
1. Staff	M&E Associate	X5MID	10	£ 128	£ 1, 282
5. Others			1	£ 7, 692	£ 7, 692
Total					£ 17, 949

Activity 1.1: Conduct assessment of gaps in energy-water nexus Project (Month 2-3)
Category	Staff or budget item	Grade (if staff)	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Investment Lead, PM	X10INT	3	£ 698	£ 2, 094
1. Staff	Senior Associate	X7MID	12	£ 202	£ 2, 430
1. Staff	Regional Investment team	X9INT	1	£ 582	£ 582
1. Staff	Regional Energy team	X9INT	2	£ 582	£ 1, 165
Total					£ 6, 271

Activity 1.2: Project structuring investment readiness (Month 4-6)
Category	Staff or budget item	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Investment Lead, PM	5	£ 698	£ 3, 490
1. Staff	Senior Associate	30	£ 202	£ 6, 074
1. Staff	Regional Investment team	5	£ 582	£ 2, 912
1. Staff	Regional Energy team	1	£ 582	£ 582
Total				£ 13, 058

Activity 2.1: A feasibility study of 50 pumping stations (Month 1-4)
Category	Staff or budget item	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Investment Lead, PM	8	£ 698	£ 5,584
1. Staff	Senior Associate	60	£ 202	£ 12,149
1. Staff	Regional Investment team	1	£ 582	£ 582
1. Staff	Regional Energy team	5	£ 582	£ 2,912
2. Outsourcing	Consulting firm	250	£ 346	£ 86,538
3. Travel		1	£ 7,692	£ 7,692
Total				£ 115,457

Activity 2.2: Development of a revenue model for the SPV. (Month 4-5)
Category	Staff or budget item	Grade (if staff)	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Investment Lead, PM	X10INT	5	£ 698	£ 3,490
1. Staff	Senior Associate	X7MID	12	£ 202	£ 2,430
1. Staff	Regional Investment team	X9INT	3	£ 582	£ 1,747
1. Staff	Regional Energy team	X9INT	2	£ 582	£ 1,165
Total					£ 8,831

Activity 2.3: Creating an investor-facing pitch deck financier. (Month -5)
Category	Staff or budget item	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Investment Lead, PM	1	£ 698	£ 698
1. Staff	Senior Associate	10	£ 202	£ 2,025
1. Staff	Regional Investment team	1	£ 582	£ 582
1. Staff	Regional Energy team	0	£ 582	£ -
Total				£ 3,305

Activity 3.1: Capacity building on financial structuring of energy-water nexus (Month 3-6)
Category	Staff or budget item	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Investment Lead, PM	1	£ 698	£ 698
1. Staff	Senior Associate	10	£ 202	£ 2,025
1. Staff	Regional Investment team	3	£ 582	£ 1,747
1. Staff	Regional Energy team	3	£ 582	£ 1,747
4. Events		3	£ 3 846	£ 11,538
Total				£ 17,755

Activity 3.2: Development of one policy brief. (Month 5)
Category	Staff or budget item	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Investment Lead, PM	1	£ 698	£ 698
1. Staff	Senior Associate	5	£ 202	£ 1,012
1. Staff	Regional Investment team	0	£ 582	£ -
1. Staff	Regional Energy team	1	£ 582	£ 582
3. Travel		1	£ 7,692	£ 7,692
Total				£ 9,985

Activity 3.3: A Nexus evaluation model (NEM) for investments in energy and water projects developed (Month 5)
Category	staff or budget item	Unit (days, number)	Unit Cost (e.g. COR)	Amount
1. Staff	Investment Lead, PM	2	£ 698	£ 1,396
1. Staff	Senior Associate	5	£ 202	£ 1,012
1. Staff	Regional Investment team	1	£ 582	£ 582
1. Staff	Regional Energy team	1	£ 582	£ 582
Total				£ 3,573

How will you manage financial risks?
This includes how you will ensure funding is paid to the intended recipient and only be used for the purposes formally agreed. This could be as simple as, for example, receiving receipts, checking that an event took place by attending, or doing (post event/delivery) checks. Where applicable, indicate how FCDO funding will be tracked, and how often forecasts will be updated.

Deliverables-based invoicing
Activity Based Budgets with actuals and forecasts - discussions on an any major shifts in spend
Monthly reporting providing update on delivery
Monitoring and evaluation of delivery

Management Case

Governance arrangements and Programme Management Team
How will the programme be managed and governed?
Include the governance mechanism for selection and approval of individual projects, who will take on the roles of the Senior Responsible Owner and Programme Responsible Owner, and how Project Officers/Leads will be assigned.

Governance Mechanism
Given that this is a single, stand-alone programme with a budget under £250,000 and a short implementation window, governance will be light but robust, embedded within Post’s existing structures to ensure alignment with the Country Business Plan and FCDO standards. Oversight will be complemented by a dedicated Programme Steering Committee to maintain strategic direction and rapid decision-making.

The Steering Committee will comprise:
- Senior Responsible Owner (SRO): British Embassy Dakar Climate Adviser
- Programme Responsible Owner (PRO): Senior Programme Manager
- GGGI Renewable Energy Expert
- Head of the JETP Unit at the Ministry of Energy.

The committee will meet fortnightly to review progress, validate deliverables, and address emerging issues. Key points will be shared with the Development Counsellor and discussed during weekly Development Team meetings and monthly Growth and Development meetings with the Ambassador. Where deeper discussion is required, ad hoc meetings will be convened with escalation to the Ambassador if necessary.

Roles and responsibilities
- SRO: The Climate Adviser will act as the Senior Responsible Owner, providing strategic oversight and reporting to the Development Counsellor.
- PRO: The Senior Programme Manager will lead day-to-day delivery, manage the budget, and coordinate with GGGI and MEPM.
- Project Leads: Given the programme’s scale, there will be no separate Project Officers; the PRO will manage both workstreams directly, supported by Embassy corporate teams for compliance.

Monitoring and Reporting
Please describe the lines of accountability, responsibility, and reporting from projects to the programme and the portfolio. Also describe how projects delivery will be monitored.

Accountability and oversight
- The SRO holds ultimate accountability for programme success and alignment with strategic priorities.
- The PRO manages operational delivery, budget tracking, and risk escalation.
- GGGI is responsible for implementing activities and providing regular updates and evidence of progress.
  - External consultants: Specialized consultants will be competitively recruited by GGGI to deliver time-bound technical assignments where external expertise and field capacity are required. In particular, consultants will be engaged to:
    - Conduct the feasibility update and scaling analysis for solar-powered irrigation systems
    - Support preparation of the business case for scaling, including technical annexes and supporting analysis.
    - Provide inputs to the SPV business case, as required, under GGGI’s technical direction.
Reporting lines
- GGGI reports directly to the PRO, who quality-assures inputs and consolidates updates.
- The PRO provides weekly updates and monthly reports to the SRO, covering progress, budget, and risks.
- The SRO integrates programme-level reporting into Post’s portfolio and escalates to the Head of Mission as needed.
- The consultant will work under GGGI supervision, with all outputs reviewed and validated by GGGI before submission to MEPM and partners.

Monitoring and evaluation
- Monthly updates capturing progress, risks, and lessons learned.
- Delivery tracked against the Theory of Change and Results Framework included in the business case.
- Indicators monitored for both workstreams:
  - Workstream 2: Feasibility study and SPV business case completed.
  - Workstream 1: Investment-ready project package delivered.
- Independent validation by Post through participation in workshops and review of outputs.
- Biweekly Steering Committee meetings to review milestones and authorize adaptive changes.

Risks
Summarise the main risks to the programme and mitigation measures as appropriate.

The risk table can be found in section A.4

State the overall programme risk assessment, and whether it is within the overall risk appetite.

The overall programme risk assessment is moderate.