Business Case – February 2026

Summary Sheet

Portfolio/ Business/Country Plan Summary: this programme will support delivery of the Eastern Neighbourhood (EN) countries’ Country Business plans and the EN regional Theory of Change.

Title: / Partnerships for Resilience in the Eastern Neighbourhood (P4R)
Programme summary (100 words maximum): / The programme will strengthen democratic, societal and economic resilience and socio-economic development across the Eastern Neighbourhood by supporting democratic institutions, inclusive governance, civic space, and effective public services. It will counter hybrid threats, disinformation and external interference by investing in civil society, independent media, and local leadership. Targeted technical assistance will help reform minded governments deliver sustainable, citizen focused change, while economic support will improve regulatory quality and reduce vulnerability to external shocks.
What is the rationale for UK Aid spending? (200 words maximum): / The Eastern Neighbourhood’s (EN) development is strategically vital to UK national security. The region faces a range of development challenges, such as structural governance weaknesses, corruption, societal polarisation, inequalities and unresolved conflicts, these heighten instability and create entry points for external coercion. Russia’s invasion of Ukraine has further intensified pressures, increasing disinformation, cyberattacks and energy insecurity across the region.
Programme Value: Up to £39m		Country/ Region or Sector: / Eastern Neighbourhood (EN)
Department/Country Office confirmation of review processes		EN Heads of Missions and relevant Eastern Europe & Central Asian Deputy Directors

Threshold for final approval of Business Case: Director
Date of Approval of Concept Note:	16/01/2026	Name and role of Approver / Minister Doughty, Minister of State for Europe, North America and UK Overseas Territories
Date of Approval of Business Case:	27/02/2026	Name and role of Approver / Chris Allan, Eastern Europe and Central Asia Director
Programme Code:	AMP Start Date: / 01/04/2026	AMP End Date: / 31/03/2031
Overall programme risk rating:	Major

Strategic Case

Context

The stability and resilience of countries in the Eastern Neighbourhood (EN) is critically important to the United Kingdom’s national security. Moldova, Georgia, Armenia and Azerbaijan sit within a geopolitically sensitive region, whilst continuing difficult post-Soviet transitions and navigating a contested geopolitical environment. This vulnerability has become more acute since Russia’s full-scale invasion of Ukraine. Whilst each country’s challenges are specific and unique, their political and economic institutions are often vulnerable and face common threats. Hybrid threats are used to undermine societal resilience, sowing divisions and destabilising societal cohesion. As a major European security actor, the UK has a direct interest in ensuring that EN countries are equipped to tackle these challenges, emerging as stable, independent and constructive supporters of the rules-based international order. We also have interests in building mutually beneficial economic partnerships that support resilience and strengthen bilateral relations.

The UK has a strong track record as an investor in democratic and economic resilience across the region. Our diplomatic influence has been projected through close bilateral ties as well as membership of key multilateral organisations. Earlier British investments in the Know-How Fund (1989-2003) and the Good Governance Fund (2015 – 2026) have been highly valued by partner governments in the region, deploying technical assistance to build institutional capability and support democratic and market reforms. These programmes have been complemented by projects under the Conflict Security and Stability Fund (CSSF) and Integrated Security Fund (ISF), that had also included gender equality and wider societal resilience initiatives. The stated goal of the FCDO’s EN portfolio is to help countries ‘create inclusive economic and political pathways, allowing them to determine their own future, thereby improving their long-term resilience to external shocks and internal fragility’.

Partnerships for Resilience (P4R) will give His Majesty’s Government (HMG) the tools to address reduce local vulnerabilities to destabilising threats in an increasingly complex regional context. The programme will seek to strengthen institutions that help countries inclusively prevent or peacefully manage internal conflict and external threats, as well as recover after negative shocks. Encompassing very different country contexts, P4R is structured to allow the FCDO to rapidly scale up or down in response to local and regional demands and lesson-learning.

Challenges to Resilience in the Eastern Neighbourhood

1. The countries of the EN emerged from Soviet rule in the 1990s with limited experience of democratic politics or market competition. After attaining independence, these countries were dominated by Soviet-era political and economic elites who captured the state and newly privatised industries. In the absence of institutions such as an independent judiciary and media, active civil society or the rule of law, the benefits of growth were concentrated within a narrow circle of oligarchs and elites, then entrenched through corruption. The legacy of Soviet institutions cast a long shadow in EN countries, where there was little historical experience or cultural acceptance of liberal democratic norms. After a decade of instability and retrenchment in the 1990s, Russia re-emerged as a power seeking to dominate what it saw as its ‘sphere of influence’ or ‘near abroad’, illegally occupying territories in Georgia, as well as Ukraine. Structural weaknesses and social divisions within these neighbouring countries made them more vulnerable to attack and malign influence.
2. Over the last two decades, countries of the EN have followed diverging political and economic trajectories. The trajectories followed have been non-linear, with backsliding to authoritarianism an ever-present risk. After independence, Moldova was ruled by an unreformed Communist Party until 2009, when it entered a period of alternating power with the pro-European parties. With a reformist government since 2021, Moldova is taking rapid steps towards its goal of European accession. Georgia was, for many years, seen as the region’s most pro-reform countries since its Rose Revolution in 2003. However, over the last decade this progress has begun to reverse, and space for civil society has narrowed significantly.

The region’s progress towards democracy, inclusion, rule of law and socio-economic development is tenuous. As the case of Georgia demonstrates, shifts towards European integration and democratic reforms can rest on narrow social foundations. Recent elections in Moldova demonstrated that democratic resilience and free and fair elections can be effectively supported. Both Armenia and Azerbaijan have, after decades of conflict, taken substantive steps towards a negotiated peace, despite significant challenges still to be overcome. This represents a marked shift and the opportunity to resolve a long running conflict, which would provide stability as well as enhancing the conditions for regional cooperation and connectivity. It may also catalyse societal shifts inside each country, creating space for new actors. A vibrant and active civil society is instrumental in placing pressure on political decision-makers and represents a key enabler for future progress.

Gendered and social inequalities are promoted and exploited by malign actors to further instability and polarisation. A 2025 evidence review found ‘women and girls in Armenia, Azerbaijan, Georgia, and Moldova face systemic economic, social, and political marginalisation due to a “set of traditional patriarchal gender norms, intersecting with conservative religious identities and harmful customary practices” [1]. Autocratic and patriarchal power structures are well aligned. The legacy of Soviet rule, shifting national borders and conflict-displacement means that all EN countries host significant ethnic minority populations. These ethnic minorities are often systematically excluded from political participation and can be vulnerable to discrimination or marginalisation.[2] Very minimal information is available on disabilities across EN, indicating limited focus in this area. Where strong legislation exists, its implementation is limited.
[1] Ball, K. (2025). Gender, equality, disability and social inclusion trends in Armenia, Azerbaijan, Georgia, and Moldova. K4DD Rapid Evidence Review 348. Brighton, UK: Institute of Development Studies
[2] Haider, H. (2022) Addressing political exclusion of ethnic minorities, IDPs and refugees in the Eastern Neighbourhood. K4D Helpdesk report 1115. Institute of Development Studies.

Unresolved conflicts and the legacies of former conflicts across the region are a source of ongoing instability. The collapse of the Soviet Union led to rising tensions between ethnic and national minorities. The breakaway region of Transnistria, a sovereign part of Moldova, continues to contain Russian troops, was the focus of armed conflict in 1992, and has been in an uneasy political stalemate since that time. Russian troops invaded Georgia in 2008 and continue to occupy around 20 percent of its territory with Abkhazia and South Ossetia declaring their independence from Tbilisi. Armenia and Azerbaijan fought each other over Karabakh, most recently in 2023 when Azerbaijan established control and large numbers of ethnic Armenians left the area. The two countries initialled a draft peace deal, marking intent for further progress in Washington DC in Summer 2025, with the US and EU contributing large amounts to unlock the promise of enhanced regional connectivity. However, legacy hostilities and entrenched public sentiment, despite recognition of the value of peace, provide opportunities for malign external actors to disrupt the positive trajectory.

Since 2000, poverty has decreased across the region. However, significant development challenges remain. In Moldova, for example, more than six in ten people face poor sanitation conditions (61.2%), over half of the population still rely on polluting fuels for cooking and heating (54.1%), one in three lack medical insurance leaving them exposed to health costs (33.2%), and about one in five lack safe drinking water, posing health risks (22.2%)13. Poverty is not distributed evenly across the population of the region – typically, poverty is more prevalent in rural areas, children and youth tend to be more affected, and women often face an additional poverty risk as a result of their lower earning power and care responsibilities.

The disruption caused by climate change presents a direct threat to EN countries with likely political, economic and social consequences. Increased water scarcity and extreme weather events will damage EN countries, many of whom are primarily agricultural economies, with potential implications for food security. Rising temperatures are already estimated to have contributed to the loss of over 11 billion tonnes of freshwater in the Caucasus region14. Better water management strategies are widely needed. A major energy exporter to Europe, Azerbaijan’s oil reserves are declining, and the country will need to diversify its industrial base if it is to thrive in a low-carbon global economy. P4R will be compliment by the EECAD Humanitarian Preparedness and Response Mechanism which provides a vehicle to support EN countries in preparing, anticipating and responding to climate, conflict and economic related risks.

Despite these difficulties, there are signs of resilience across all country contexts that warrant international support. Citizens are increasingly well-educated, exposed to global influences, and eager to see political, economic, and often social change. Voters in Moldova have expressed confidence in the government’s pursuit of EU accession and liberalising reforms. An important driver of this resilience has often been the growth of businesses outside of state patronage, such as the ICT sector in Armenia. Intelligently designed and well-targeted international support can bolster internal resilience and help EN countries find alternative development pathways.

South Caucasus regional connectivity initiatives have the potential to establish major new East-West transit routes linking Central Asia to Europe, bolstering UK and European economic security. Successful development of the Middle Corridor would provide competition with existing routes. Alongside the EU, Turkey, and the US, we will influence this regional agenda, using our expertise and engaging with partners, particularly International Finance Institutions. Increased regional connectivity also has the potential to deliver economic and development benefits to countries in the region. For example, land-locked Armenia faces high transit costs and limited access to regional markets with a reliance on north-south routes – enhanced trade and transport links with its neighbours could bolster its economic development and resilience.  Improved South Caucasus connectivity will require significant infrastructure investment sourced from large-scale private sector finance, while development assistance can be catalytic in crowding in additional funding, developing institutional capacity, and ensuring dividends are felt inclusively. Investing in building accountability and transparency is required to ensure that economic gains do not entrench inequalities and corruption is stamped out.

As middle-income countries with their own domestic resources, overseas development assistance and cooperation makes a relatively small contribution to their economies, and our support needs to be designed in this context. All countries have the potential to graduate from ODA eligibility on the horizon, particularly in the case of Moldova’s ambition for EU accession and also face a continued decline in global ODA funding availability. The region benefits from concessional lending through multilateral development banks, such as the World Bank and EBRD, as well as forming part of the EU’s European Neighbourhood Policy. The EU is currently delivering a €1.9bn funding package of highly concessional loans and grants to Moldova through the Growth Plan, the disbursement of which is contingent on Moldova’s satisfactory progress against the Reform Agenda. As an active member of multilateral organisations, including the development banks, we can use our influence and support to advocate improvements in the quality of assistance. UK leadership within these multilateral bodies coupled with responsive and adaptive programming, that compliments the work of our allies, can have a catalytic impact.

Why UK Support is Needed

1. Critical weaknesses within state institutions in EN countries can be addressed through the provision of ‘smart’ technical assistance[3], which both provides shorter term support and builds the capacity for longer term sustainability. The capacity of government institutions is often undermined by challenges in the recruitment, retention and development of public sector human resources. Civil servants can come under intense political pressure and there are limited incentives for strategic thinking across government. Public administration is often inefficient and expensive, with decision making pushed to the top, but public sector reform meets with resistance. This means that governments can struggle to ensure that reforms are effectively delivered with benefits being felt inclusively by ordinary citizens. Well-evidenced and politically astute technical assistance can unlock a virtuous cycle of improved state capability and increased faith in democratic institutions.
  [3] Understanding and using smart technical assistance, April 2025 - GOV.UK
2. While the UK has a modest footprint relative to other funders, we can leverage our unique assets and capability to complement larger investments. The UK’s has three clear USPs, we are relatively agile and flexible meaning we can respond to local changes in context at pace, we have a wide network of relationships with host Governments, IFIs, business and civil society, many of whom we have worked with for many years in EN to drive change, and we can leverage expertise from across HMG and UK institutions to support delivery of targeted and well-designed assistance. Positioned within our broader regional portfolio approach, P4R will complement and leverage other programming and diplomatic efforts to tackle complex themes more holistically.
3. The context for UK assistance is highly complex and dynamic, requiring flexibility and a willingness to adapt. Countries that offer promising entry points for support by demonstrating reform appetite can rapidly close. Equally, seemingly dismal prospects for progressive reform can be transformed by the mobilisation of citizenry or geopolitical imperatives. Small country-based allocations are vulnerable to these shifting dynamics. However, a regional portfolio approach, drawing on a full suite of tools and capabilities, can help the UK act responsively and intelligently. Furthermore, the significant change in the US’ focus and presence in the region, has left critical gaps, especially within civil society, and demonstrates the value of a responsive and flexible approaches.

The UK has already shown, through its previous development investment, that it is able to effectively support the resilience of EN partners. An independent evaluation of the Good Governance Fund (GGF) found good evidence[4] of the portfolio delivering impact across a variety of challenging country contexts, as well as identifying important lessons for future programming. For instance, our assistance to Moldova has helped build capacity within the Central Electoral Commission and enhance public awareness of the electoral process, contributing to successful free and fair elections in the face of significant foreign information manipulation and interference. Even where shrinking civic space has made it more difficult to work, GGF projects have facilitated the establishment of new mechanisms to support the priorities of local communities where possible. These examples are indicative of the impact that can be realised through the provision of targeted small-scale support, alongside larger donors and funders.
[4] https://iati.fcdo.gov.uk/iati_documents/S30145457.odt
Our Approach
The UK’s approach to improving resilience in EN countries reflects lessons learned and shifts from earlier programming. Experience from GGF and ISF projects point to the central importance of targeting efforts where political economy analysis suggests there are viable pathways of change, as well as opportunities for long-term impact, in line with the FCDOs new development approach. P4R will shift focus away from individualised training and capacity-building interventions, where effectiveness can be fleeting, and towards a more holistic approach that considers how this capacity is embedded in systems and institutions, reducing the vulnerabilities in society to shocks and malign influence. While the GGF was able to deliver impact across many areas, programme reviews pointed to the proliferation of ad-hoc modular demand-led projects. The multitude of projects potentially detracted from the coherence and purpose of the GGF. With scarce resources and an increasingly fragile region, a new approach is needed. P4R will be grounded in more strategic, selective partnerships that integrate either responsive or adaptive ways of working with clear goals and outcomes, guided by UK expertise and focussed on enabling local capacity and momentum. Finally, the P4R delivery model will more closely bind political and development teams across the region and draw upon HQ teams to better join-up programmatic implementation with diplomatic influence.

Support for EN countries under P4R will be informed by three guiding principles. These principles will help to distinguish the unique role for UK, alongside our likeminded allies and multilateral partners, and ensure that our resources are being deployed to the fullest effect.
  1. Agile. With lower levels of funding, the UK can respond at pace to entry points as they emerge, informed by a politically astute approach able to identify an alignment of interests. We will empower posts and frontline teams with a deeper understanding of the political economy of country and regional contexts, and ensure they have the tools and skills to navigate fast-changing dynamics and effectively prioritise.
  2. Strategic. Among the lessons learned from delivering programmes in the EN is the importance of developing a clear purpose and strategy, whilst allowing for flexibility in implementation. Our prioritisation decisions will therefore be informed by a clear overarching regional theory of change, which will guide our use of resources and drive coherence with other regional programme activity. We will also embed decision-making processes that allow project teams to adapt their activities in accordance with the shifting and complex environments in which they are working.

  1. Innovative and catalytic. Our higher risk appetite will enable P4R to test the effectiveness of new interventions, where larger donors with lower risk appetites might be unwilling to fund. To the extent that the innovations prove to be successful, they can be adopted and scaled by other partners, as has been the case under the GGF and ISF.
P4R will deliver impact through three mutually reinforcing thematic pillars of activity. The complex and uncertain operating environment will require flexibility, blending the right combination of programme interventions, alongside our diplomatic weight and influence. The programme will provide targeted support to drive systematic change, putting a premium on investment in knowledge and relationships, the ability to spot opportunities and respond at pace, and use of different modalities. Working in partnership with receptive governments and a broad range of actors, including IFIs, this programme aims to support the building of EN countries’ resilience through;
1. Democratic and societal resilience: strong and inclusive public institutions and systems, effective public service provision and democratic accountability are a pivotal part of supporting EN countries to build their resilience to withstand malign influence and shocks. Partnering with receptive governments and a range of actors to strengthen national and district institutions will support countries in building systems which respond to local needs, but also to decide their own democratic development pathways and geo-political positioning. Gender equality and the broader inclusion of marginalised groups are a critical enabler of democratic and societal resilience. This pillar of the programme, alongside pillar B below, will also address the challenges of societal polarisation and exclusion underpinned by gender, political economy and conflict sensitivity analysis.
2. Local leadership and civil space: The foundations of a representative and inclusive democracy are dependent on a thriving civil society, strong local leadership and independent media, who ensure contextually smart decision making, accountability and sustainability. Women’s movements are typically at the forefront of promoting democracies and work to prevent democratic backsliding.[5] An environment that allows diverse people to come together, express opinions and take action is central to democratic resilience, as well as tackling democratic backsliding. Civil society and civic space, including independent media and grassroots civil actors, help to define and deliver development outcomes, represent and reach marginalised parts of society, and act as a critical friend to authorities, improving political accountability and transparency.
  [5] Khan and Sharp, ’How women’s movements lead demands for democracy in the face of backlash and politicised religion, February 2025, ODI, ODI Report
3. Economic resilience: Limited or slow economic growth, compounded by external shocks, such as conflict and energy price volatility, present significant challenge in the region, both in terms of household-level deprivation, and macro-level system vulnerabilities. To improve diverse people’s lives and to secure long-term resilience, inclusive economic growth and reform is critical. Strengthening economic governance and private sector development is a central part of this and will reduce vulnerability to external influence, supporting the economic stability and reliability required for increased trade and investment. Where governments are receptive, this programme will develop smart and targeted coalitions and partnerships with IFIs, multilateral agencies, and the private sector to support the building of inclusive economic resilience, without displacing local capability.

Across these three pillars, gender, equalities and social inclusion will be mainstreamed, with this being an explicit objective of the programme recognising that gender inequality and social exclusion remain key vulnerabilities that are used to undermine efforts to build resilience. The inception phase will develop this mainstreaming approach further, including agreeing focus areas.

For P4R to be effective it will be vital to develop a deep understanding the political economy of the EN countries to inform decision-making and design. High quality political and institutional analysis and technical advice across the three pillars, alongside Monitoring, Evaluation and Learning, will enable effective responsive and adaptive management (see the Management case for detail), efficient targeting of resources, and building capacity of partners.

P4R decision-making will be guided by the regional portfolio theory of change prioritising and tailoring interventions for each EN country. The political and economic context varies significantly across the EN region. The uncertainty of constantly shifting political dynamics in the region will require the programme to regularly revisit how it is prioritising and allocating resources against two criteria: (1) the extent to which there are drivers of positive change and reform momentum based on an understanding of the political economy, incentives, power dynamics; and (2) the UK’s ability to support and influence these drivers of change (Fig 1 below), as well as alignment with the key strategic drivers of UK interests set out above.
Expected Impact and Outcome
As an overarching outcome, P4R is expected to strengthen national and local institutions and systems, reducing societal vulnerabilities to state threats, and contributing to the long-term resilience, sovereignty and sustainable development of EN partner countries. The intended impact is for resilience across EN countries to be improved, including to setbacks in democratic and development trajectories, as well as from external shocks/threats and internal fragility. This will reduce knock-on impact of shocks to regional security and stability, making Europe, including the UK, safer. This would mean that citizens and governments of these countries are better able to navigate geopolitical pressures stemming from their location between Europe and Russia, supported by progress on socio-economic development and poverty reduction across the region, thereby increasing resistance to malign influence of external partners and adapting to emerging shocks. While P4R will be constrained in its ability to directly shift the incentives and dynamics behind processes of democratic backsliding in EN countries, it can help create ‘shock-absorbers’ that allow societies to ‘bounce back’ from periods of autocratisation.
Strategic Fit
The P4R programme is aligned with relevant HMG strategies HMG’s National Security Strategy as well as to FCDO’s development re-set and the establishment of modern development partnerships. This programme will primarily deliver on the Foreign Secretary’s Security priority, while also contributing to other relevant priorities over the course of the programme (e.g. the Development and Climate, Women and Girls, and Agile Alliances priorities). In line with the FS’ reaffirmation of the UK commitments to women and girls’ rights, to UNSCR 1325 on Women, Peace and Security (WPS[6] and the HMG ‘freedom from violence and abuse: a cross-government strategy’), this programme will include [7]objectives on gender and equalities. Furthermore, Ministers have reconfirmed UK support for democracy and human rights are both an expression of British values, as well as being instrumental to the achievement of broader interests. The P4R programme is aligned with the Country Business Plans of the EN countries and will be informed by future country business planning processes and the regional Theory of Change.
[6] Freedom from violence and abuse: a cross-government strategy - GOV.UK, link
[7] As Lord Collins stated in a keynote speech on Human Rights Day on 10 December 2024, rule of law and democratic governance are ‘powerful enablers for the key missions of this government’. GOV.UK, link
Compliance
The programme is fully compliant with legal and best practice requirements as follows:
  1. Gender: The programme will be designed with a consideration of gender issues and will be compliant with the Gender Equality Act. It will include gender objectives and programme delivery will take due account of the needs of persons in public sector institutions and bodies providing finance, including by gender.  Any wider social and economic support provided will ensure that women are included and have appropriate access, and that other vulnerable groups are addressed.
  2. Disability: In all support, implementing partners will be expected to give due consideration to the particular needs and vulnerabilities of persons with disabilities, in accessing required information and support. Efforts will be made to ensure that programme implementers engage with the relevant organisations representing persons with disabilities.
  3. Public Sector Equality Duty: The programme’s approach to public sector capability will include a specific focus on inclusion as an aspect of the quality of public sector institutions. In line with this, the programme will contribute positively to advancing equality of opportunities. Implementing partners will be expected to uphold standards and principles relating to non-discrimination and no harassment or victimisation, as well as international human rights provisions.
  4. Safeguarding: The programme’s close collaboration with posts, including UK Delegations with multilateral bodies, will provide both risk mitigation and local oversight to manage arising concerns. In line with FCDOs policy, partners will be required to have appropriate safeguarding policies and procedures in place, and FCDO will provide information on how to raise safeguarding concerns related to our programme.
  5. Climate and Environment: This programme will not have a large climate focus but will identify entry points at the intersection with environmental sustainability and the capacity of host Government’s to manage and mitigate climate risks, and the successful implementation of broader spending commitments to adaptation and resilience.
  6. Partnership Principles: The programme is consistent with the four partnership principles being a commitment to reduce poverty, respect human rights, strengthen financial management and public accountability. Where any direct bilateral aid is provided, the Partnership Principles will apply and be followed closely.
  1. Counter Terrorist Financing: The risk of UK aid being diverted to support terrorist groups or activities is low. All implementing partners will have passed due diligence or fiduciary risk assessments and have a strong track record of delivery. The FCDO programme team will identify, mitigate and manage risks in accordance with a risk management framework.
  2. Risks: An initial programme risk matrix is included in the management case below.
Appraisal Case

To derive the best option for the delivery of the programme a multi-criteria analysis has been conducted considering how different options would best deliver on critical success factors aligned with the HMT Green Book, including strategic fit and business needs, potential value for money, potential achievability of the programme, and delivering equity and inclusion. These factors are weighted according to the importance to the programme and then the different options scored against these factors, scores adjusted for weighting, and weighted totals calculated to determine the preferred option. The critical success factors are detailed below, the options for the programme set out and the relative scores presented.

Objective: strengthen national and local institutions and systems, reducing societal vulnerabilities to state threats, and contributing to the long-term resilience and sovereignty of EN partner countries.

Criteria for assessment

Key Critical Success Factors	Description	Weighting
Strategic fit and meets business needs	How well the option: - meets the agreed spending objectives, related business needs and service requirements - provides holistic fit and synergy with other strategies, programmes and projects / How effectively will the option address local vulnerability? / How effectively will it support the resilience of the states in the region? / How much will the proposed option bring about systematic change?	0.4
Potential Value for Money	How well the option: - optimises social value (social, economic and environmental), in terms of the potential costs, benefits and risks / What is the effectiveness of the funding mechanism? / Does it buy us leverage over larger amounts from other? / Does it represent value for money?	0.2
Potential achievability	How well the option: - is likely to be delivered given an organisation's ability to respond to the changes required - matches the level of available skills required for successful delivery / Are the delivery mechanisms feasible in all of the contexts? / Will the option enable the programme to adapt to shifting political opportunities and threats? Does the mechanism allow us to prioritise within a finite amount of resources?	0.2
Delivering Equity and Inclusion	How well do the described options help deliver greater equity and social inclusion. / To what extent are excluded people targeted? / What mechanisms exist to ensure equity and inclusion are considered? / To what extent is gender equality being promoted through this work?	0.2

Appraisal Options

Option 1: Do nothing No further programming in this area. Continue diplomatic activity as normal.

Option 2: Multiple Regional Programmes on Specific Priority Themes: Focusing on a few narrowly defined priority themes (e.g. rule of law, gender, climate), providing thematic clarity and a concentrated ODA focus across UK EN Embassies. Benefits include programming efficiencies, potential Value for Money (VfM), and greater knowledge sharing. The UK would be recognised as a leader on a few specific topics in the EN.

Option 3: Programme via Multilaterals/IFIs: Only providing grant funding to influential regional IFIs, leveraging larger amount of IFI spend to enhance their effectiveness and align with UK objectives. It requires minimal HMG project management resources and can be executed with a limited budget.

Option 4: Individual Country Programmes Having specific programmes for individual countries – this would include a large programme for Moldova and perhaps a smaller programme focused on the Armenia and Azerbaijan peace process. Expertise would be focused on particular countries rather than being regional.

Option 5: Responsive Democratic, Social and Economic Resilience Programme (recommended): Incorporating country-specific and multi-country projects aligned with an integrated programming and policy portfolio theory of change for the region and Country Business Plans. It offers flexibility to respond to emerging opportunities through responsive programming and selective adaptive management, harnessing learning from previous engagements. This approach supports regional efficiencies and navigates sensitivities by scaling interventions across countries based on VfM. It also allows for a diversified portfolio of delivery partners.

Option 6: Continuation of GGF: A continuation of the current programme. The Good Governance Fund (GGF) Phase 3 is delivering demand-led support to governance reforms that supports open societies and economies to flourish. The GGF focuses on improving democratic and economic governance, through strategically targeted technical assistance and grant projects. The GGF is delivering interventions on a flexible basis, based on identified needs and/or requests from government counterparts or civil society in beneficiary countries, supporting governance and economic reforms.

Scoring

Criteria	Weighting	Option 1: Do Nothing		Option 2: Thematic programmes		Option 3: Multilaterals / IFIs		Option 4: Country Programmes		Option 5: Adaptive Programme		Option 6: Continue GGF
Score	Weighted score	Score	Weighted score	Score	Weighted score	Score	Weighted score	Score	Weighted score	Score	Weighted score	Score	Weighted Score
Strategic Fit	0.4	1	0.4	2	0.8	2	0.8	3	1.2	4	1.6	3	1.2
VFM	0.2	1	0.2	2	0.4	3	0.6	2	0.4	3	0.6	2	0.4
Potential Achievability	0.2	1	0.2	3	0.6	2	0.4	2	0.4	3	0.8	4	0.8
Equity and Inclusion	0.2	0	0	4	0.8	2	0.4	3	0.6	3	0.6	3	0.6
Total	1	3	0.8	11	2.6	9	2.2	10	2.6	13	3.6	12	3.0

Appraisal Score Narrative

Option 1: Do Nothing
The do-nothing option would provide no specific programming to build resilience. Activity in the region would be limited to on-going security focused work from the ISF and diplomatic engagement providing some limited strategic fit. Harnessing diplomatic and ISF levers for impact alone would not have the combined impact of a complimentary set of programmes. In this option the FCDO would not be able to respond to specific shifts in context, address threats or respond to opportunities. There would be limited progress towards equity and inclusion.

Option 2: Thematic Programmes
This option would provide limited flexibility in manging resources – both people and budget. In a rapidly changing context having a narrowly defined set of themes to work on would limit the programme’s ability to both deliver on the strategic case and also adapt to the context to deliver results if a theme became less relevant or appropriate. It would also present lower value for money as overheads would be higher across the individual programmes with limited ability to provide efficiencies with a small annual budget. The existence of separate thematic programmes would allow for a dedicated programme to Gender, Disability and Social Inclusion, with targeted results and clear analysis and action. However, it would risk gender and inclusion equities not being mainstreamed across the set of thematic programmes.

Option 3: Multilateral Programming
The option to programme only through multilateral organisations would limit the portfolio’s ability to respond to the full range of threats due to the framing and nature of multilateral organisations. We would be restricted by their engagement with host governments which has certain political restraints. It would also limit our ability to flex the programme to changes in context. This style of programming would represent savings on VfM as FCDO management would be fairly light touch. However, it would rely on the efficiencies and delivery mechanisms within multilateral organisations which we would not be able to control. The potential achievability of the results may be limited by the lack of ability to flex to the change of contexts and to target problems our analysis has identified. While multilateral organisations often have good equity indicators and targets, we would have limited ability to influence these.

Option 4: Individual Country Programmes
Having distinct country programmes would restrict the portfolio’s ability to flex and adapt to respond to changes in context in a highly volatile region, lessoning the strategic fit. There have been large swings in the political trajectories across the region and so maximum flexibility is needed to move money across emerging priorities, which this model would restrict. Separate programmes across different countries/geographies would also require separate processes to manage the programmes. Any efficiencies of scale would be lost, resulting in a lower VFM score. It would also be harder to react to emerging treats as resources could be less easily moved across contexts.

Option 5: Responsive Programming
This flexible model of programming will allow the programme to respond to the local conditions that will build long-term resilience and address the specific vulnerabilities in each context. It will allow for specific targeting of systematic change by working politically and responding to how change happens on the ground, drawing on lessons learnt from across the region. This responsive approach to programming will allow differing approaches in different contexts but also identify opportunity for multi-country projects where appropriate to drive VFM. By having a single programme, this will increase VFM, through streamlining of procedures and sharing of resource and expertise. However, having a small selection of projects managed using an adaptive methodology will require an additional investment of staff time (from the implementers and FCDO) to interpret results to determine appropriate follow up actions. The extra costs associated with adaptive management approach should lead to an improvement in the sustained impact of our project work and an increased potential for transformative results, while requiring a high-risk appetite for failure. The programme will need to strike a balance, with the majority of elements taking of responsive approach and delivering expected results, while a minority of projects, where the political context is particularly complex and outputs unknown, will have a greater emphasis on innovation and learning. Equality and inclusion will be mainstreamed into programme, which means there will be gender and equalities objectives developed in the inception phase, with the associated targeted programme activities. Standalone gender projects will also be considered.

Option 6: Retaining the current Good Governance Fund
A continuation with the current GGF would allow for key issues to be addressed but mainly through contained projects rather than a systematic approach, which would limit the strategic effect. Further, with reduced ODA budgets, having a wide portfolio of projects for each country in the region is no longer possible. Having a small number of small number of projects per country does not deliver the same VFM or impact. Equality and gender would be mainstreamed across the programme.

Recommended option: Option 5, Responsive Democratic, Economic and Social Resilience Programme
The fourth option of responsive programming achieved the highest score following the multi-criteria analysis, providing the best balance of flexibility and VFM to address the shifting challenges in a volatile region. Effective mainstreaming of gender and inclusion issues will be needed to ensure this option does address equity concerns.

Theory of Change (ToC):

P4R aims to strengthen the democratic, societal and economic resilience of EN countries to enable them to withstand external pressures and state threats, reduce internal fragility, and accelerate inclusive socio-economic development. This theory of change assumes that IF we provide targeted support to democratic institutions, diverse civil society and their organisations and inclusive economic systems THEN these countries will be better equipped to manage hybrid state threats, reduce vulnerability to malign influence and sustain reform momentum AND SO as a result we expect to enable a more resilient, sovereign and inclusive EN region able to develop and deliver for their people

This ToC is underpinned by the idea that resilience is built through a series of interconnected systems; democratic institutions, diverse civic participation, economic stability and social resilience. P4R aims to deliver through three pillars (democratic and societal resilience, local leadership and diverse civic space and economic resilience), using responsive and adaptive approaches to respond to rapidly changing contexts. Activities such as strengthening electoral bodies, supporting independent media, exploration of gendered social norms, and enabling regulatory reforms are expected to lead to intermediate outcomes of improved, inclusive, accountability, improvements in conditions for equalities, expanded and diverse civic space and stronger economic governance. This should then reduce vulnerability to malign influence and create conditions for inclusive economic growth. The programme will embed monitoring, evaluation and learning (MEL) throughout to test the assumptions and adapt as necessary. More detail on MEL for this programme can be found in the Management Case.

Figure 2: Diagram describing the Theory of Change for the P4R programme approach.

Key Assumptions underpinning this ToC which are not in our control:
1. Sustained appetite for reform exists in at least one EN country
2. Backsliding does not fully close civic space in all countries and viable entry points still exist
3. External malign influence and internal threats do not increase to levels which make safe and effective delivery possible
4. Like-minded partners and IFIs remain engaged and willing to co-fund reforms and programming

Key assumptions which are in our control:
1. Roll-back against rights can be monitored
2. FCDO has capacity and capability in place to responsively and adaptively manage the programme

Value for Money statement and measurement:

P4R will design a VFM Framework to monitor VfM using FCDO’s 4E Framework. VFM indicators will be agreed with delivery partners before activities commence, subject to available data. This will be particularly important for projects using the adaptive management. Activities carried out under P4R will take into account existing analysis and evidence of their effectiveness, drawing on the FCDO Best Buys research. VFM of P4R will depends on how effective it is in supporting EN countries to build resilient, independent development paths, which will lead to more prosperous, democratic and inclusive secure states. While the impact of P4R’s contribution to these outcomes and impact set out in figure 2 are difficult to isolate, the P4R VfM statement will consider:

Economy (the cost of inputs) - possible indicators include primarily salaries & programme funded posts and costs of activities, such as advice and capacity support. The programme will contract at competitive rates to ensure economy.

Efficiency (how quickly and easily the programme produces outputs) - possible indicators include unit cost of outputs and timeliness of output delivery. For adaptive elements of the programme this will focus on the pace and quality with which the programme elements test their core assumptions and adapt as necessary.

Effectiveness (outcome-level results) - possible indicators include relative unit cost of comparable outcomes, for example when technical assistance contributes to substantive policy commitments by a government. For adaptive programme elements, effectiveness measures will focus on the contribution the programme is making to its theory of change and if there are initial signs of a good return (financial, social or otherwise) on investment, recognising the learning process may modify objectives. It will also be assessed whether the programme is still relevant to the bigger picture changes being pursued.

Equity (how the benefits of P4R are conferred to excluded groups) - possible indicators include identify the percentage of activities meeting GEM2 targets. This will also be considered as part of how gender and inclusion is mainstreamed across the programme.

Operational costs for delivery partners will be benchmarked with that of other implementers. This is unlikely to fully capture the complexity of risk mitigation and the uncertainty associated with delivery under a highly dynamic and political context, which we will track throughout programme delivery with monitoring and evaluation support to implement lesson learning on an ongoing basis. P4R will continue to assess if the project benefits exceed costs through outcome specific monitoring. Lessons from previous programming will also help to inform our VFM framework.

       VfM will be embedded through:

- Strategic Alignment: Ensuring all activities contribute to the programme’s overarching objectives and deliver measurable outcomes that align with HMG and FCDO priorities.
- Flexibility: Both responsive and adaptive programming will be employed, allowing resources to be reallocated based on evidence and learning, ensuring interventions remain relevant and cost-effective.
- Risk Management: Continuous assessment of delivery risks and mitigation strategies to avoid inefficiencies and safeguard public value.
- Stakeholder Engagement: Incorporating feedback loops and participatory approaches to ensure interventions are equitable and inclusive.

Commercial Case

Following the outcomes of the options appraisal, the programme will implement Option 5: an Adaptive Democratic, Economic and Social Resilience Programme. This approach incorporates country-specific and multi-country projects aligned with an integrated programming and policy portfolio theory of change for the region and Country Business Plans. It offers flexibility to respond to emerging opportunities through responsive and adaptive management, harnessing learning from previous engagements. It supports regional efficiencies and navigates sensitivities by scaling interventions across countries based on VfM. It also allows for a diversified portfolio of delivery partners, best suited to the unique challenges and opportunities in the region.
Early Market Engagement and Strategic Sourcing
Early Market Engagement (EME) is expected to be conducted to generate interest within the market, foster competition, and gain a comprehensive understanding of the market’s capacity and capability. The findings from the EME will directly inform the development of the Strategic Sourcing Strategy, ensuring that procurement decisions are evidence-based and responsive to market realities.

Strategic Sourcing Strategy
The Strategic Sourcing Strategy will include an in-depth analysis of the market to identify procurement channels that are most effective and efficient, tailored to the diverse contexts and requirements across the region. This approach will encompass engagement with potential partners, the use of competitive tendering processes where appropriate, and leveraging pre-qualified supplier frameworks to facilitate rapid mobilisation of activities. The strategy will place a strong emphasis on cultivating a varied supplier base, incorporating local and regional providers. This not only enhances programme resilience but also contributes to building local leadership (thematic pillar 2), encourages innovative locally built solutions and local economic development (thematic pillar 3).

Supplier and Partner Market Analysis
A market analysis of suppliers and potential partners will be carried out to pinpoint any gaps in capacity. The results of this analysis will shape targeted actions to develop the market where needed. In some cases, small-scale interventions may be piloted to test market responsiveness and reinforce the effective implementation of responsive or adaptive programming.

The commercial case will contribute to enabling:
- Responsive or adaptive programming in volatile contexts;
- To align delivery mechanisms with the type of interventions expected under each pillar;
- To leverage partners with comparative advantage, including IFIs and experienced civil society actors;
- To maximise VfM through catalytic use of UK ODA; and
- To maintain appropriate levels of fiduciary control, assurance and accountability.

Delivery Mechanisms
Aligned with the Concept Note P4R will use the below delivery mechanisms to implement both responsive and adaptive programming, depending on what best suits the issue and context at hand. The below mix balances flexibility, accountability, and efficiency while aligning with FCDO procurement rules and best practice. Values are indicative.

Pillar One: Democratic and societal resilience - Delivery is expected to be via a combination of instruments (Memorandums of Understandings, Contracts, and Accountable Grants) chosen based on political feasibility, reform appetite, and delivery risks.
  - Memorandum of Understandings (MoUs), will be the primary mechanism when working with International Financial Institutions (IFIs) and Multilateral Organisations, where influencing reform design, standards, and implementation quality is a priority. We do not expect to undertake MoUs with state institutions directly but will continue to assess if this option is appropriate, politically feasible and within risk appetite.
  - Contracts will be the primary mechanism for delivering Technical Assistance supporting structured commercial project delivery and institutional strengthening where outputs or outcomes and deliverables are clearly defined, delivery requires specialist expertise, and robust performance management and VfM assurance are critical.
  - Accountable Grants (AGs) will be used to support non‑state actors where government engagement is constrained, politically sensitive, or carries heightened reputational risk.

Drawing on relevant delivery experience activity understanding in Moldova and Armenia through the GGF programme, this blended approach will allow the UK to remain engaged across a range of democratic trajectories, flex delivery routes as political conditions change and maintain influence even where direct cooperation with central government is narrow or not possible. This mix strengthens programme resilience while preserving the UK’s ability to pivot between state and non‑state delivery partners.

Pillar Two: Local leadership and civil space - Delivery under this pillar is expected to be through AGs and commercial contracts. Delivery will be competitive by default (through grant competition and tenders, as appropriate), with provision for direct awards where operating environments are highly restrictive and competition is not feasible or would pose undue risk and where permitted under the Procurement Act 2023, with appropriate justification and transparency.

During the inception phase, it is expected that the programme will develop plans for a commercially procured adaptive contract or call for proposals ultimately implemented through accountable grant. These will be designed to support and build the resilience of local civic space across multiple countries in the region, where outcomes are known, but not outputs, working in volatile and rapidly changing contexts. Suppliers will be expected to be able to demonstrate, a track record in adaptive management, strong political economy and gender analysis, the ability to operate effectively in volatile contexts, and strong experience of working with civil society.

The Commercial Lead will advise on procurement design of this contract to ensure that the contract incentivise learning and adaptation, allow for iterative delivery, and prioritise VfM over rigid, activity‑based delivery models. To support an adaptive programming approach, the Terms of Reference (ToR) will be designed with sufficient flexibility to allow for amendments and updates to the scope during the inception and mobilisation phases. This flexibility will enable the programme team and supplier to refine and adjust activities as new evidence emerges, while maintaining alignment with the programme’s overarching outcomes, which will remain fixed. The ToR will be structured in such a way that ensures any changes are managed compliantly through agreed contract mechanisms, preserve VFM, and allow the supplier to respond effectively to evolving delivery conditions without altering the fundamental intent or outcome of the programme.

Further adaptive contracts – across other pillars of the programme – may also be considered, subject to results achieved in through this contract, the operating context and the development of FCDO in-house adaptive management skills.

Pillar three: Economic resilience - the primary delivery route under this pillar will be MoUs with IFIs and Multilateral Organisations, supplemented where necessary by small, targeted technical assistance contracts. Interventions will focus on strengthening economic governance and regulatory reform, enhancing trade and regional connectivity, building institutional capacity to reduce vulnerability to external economic shocks, and supporting reforms aligned with EU accession pathways and relevant international standards.

Given the scale, complexity, and political sensitivity of economic reform processes, delivery will predominantly be undertaken through partnerships with IFIs, such as the World Bank and the European Bank for Reconstruction and Development (EBRD).

MoUs are the most appropriate delivery instrument under this pillar for several reasons:
- IFIs bring deep sectoral expertise and established relationships with Ministries;
- They have significant institutional capacity and experience in designing and implementing reforms at scale, drawing on funding from a range of likeminded partners to deliver increased impact;
- UK funding can therefore be deployed catalytically, providing targeted grant finance and technical assistance that leverages significantly larger volumes of IFI lending and investment;
- The UK can influence reform design, safeguards, and implementation quality, while minimising transaction and administrative costs compared to stand‑alone bilateral delivery, particularly in a lower ODA environment.

This approach reflects lessons learned from previous EN programming, where UK impact has been greatest when complementing and shaping IFI led interventions rather than duplicating them, thereby maximising VfM and sustainability of outcomes.

These IFI partnerships may be complemented by limited use of contracts to address discrete technical gaps or provide specialised expertise where IFI engagement alone would not be sufficient.

Programme MEL – MEL will be approached in a tailored manner relating to the different delivery modalities; i.e. adaptive or responsive components. Distinct approaches will be applied to the adaptive and nonadaptive elements of the programme to ensure MEL is proportionate, credible, and decision focused. For adaptive components, MEL will be embedded within delivery rather than treated as a parallel reporting function. Adaptive programming requires structured learning, regular evidence synthesis, and iterative decision making to respond to changing contexts and emerging insights. Funding for adaptive elements will therefore support an implementing partner which is able to conduct adaptive programming and the necessary structured learning and adaptive reviews across flexible projects. Independent evaluations will be contracted where appropriate through an FCDO MEL contract referenced below.

For responsive components, MEL will follow a more standard, flexible approach, while remaining important given the complex operating environments. Where required, MEL resources will be contracted from external suppliers through an FCDO central MERL framework covering the Eastern Europe and Central Asia (EECAD) region, ensuring consistency, value for money, and access to appropriate technical expertise. This builds on lessons from the GGF, where embedded learning enabled timely course correction and improved sustainability of outcomes.
Programme Gender Equality, Disability, and Social Inclusion (GEDSI) – GEDSI technical support for this programme will be delivered through a defined allocation of the EECAD Regional Social Development Advisor (SDA)’s time, maximising the use of existing in-house capability. No separate GEDSI technical support contract is budgeted. The EECAD Social Development Advisor (SDA) will provide technical oversight and work with EN colleagues to identify appropriate internal technical support, including helpdesks and Centres of Expertise, and to identify programme partners capable of meeting GEDSI requirements.

Programme funded roles, L&D and contingency - Detailed information on programme‑funded roles is set out in the Management Case. In summary, given the scale, complexity and adaptive nature of delivery, a proportion of programme funding will be allocated to providing regional expertise, supporting capacity building, learning and development (L&D), and an appropriate level of contingency. This provision will enable effective programme oversight, technical leadership, and adaptive decision‑making, while ensuring sufficient flexibility to manage delivery, fiduciary and contextual risks in uncertain and evolving operating environments. This allocation is consistent with the programme’s risk profile and complexity and represents good VfM by strengthening delivery resilience, safeguarding outcomes, and supporting timely and accountable implementation.

Expected Suppliers
The programme will engage a diverse supplier market, including:
- IFIs and multilaterals: such as World Bank, EBRD, ADB, and relevant UN agencies;
- Civil society: national and regional CSOs, independent media organisations, and umbrella bodies; and
Commercial suppliers: commercial companies and consortia with experience in delivering responsive and adaptive governance, economic reform, and resilience programming. Call-down-contracts and HMG frameworks will be used.

Procurement Timeline FY 26/27
Following approval of this Business Case in March 2026, the programme will move into an initial design and preparation phase across all three pillars. Between March and June 2026, teams will conduct strategic design, confirm delivery approaches, and undertake early engagement with prospective partners to ensure clarity of scope and readiness for relevant procurements.

Accountable Grant processes will be developed as part of this design and preparation phase. Similarly, MoUs will be designed, scoped, drafted as part of this phase.

Commercial procurement is expected to run in parallel with the design and preparation phase, with ToR development and market engagement expected to be undertaken in the Spring, before ITT publication in the summer and contract award by the autumn. Mobilisation will follow thereafter, with delivery expected to commence late 2026/early 2027.

Projects currently delivered under GGF Phase 3 that align with P4R’s strategic focus, including the thematic pillars, may be extended under this programme, where appropriate.

 Advantages and Disadvantages of the preferred approach
Advantages:
- Flexibility to respond to emerging opportunities.
- Ability to scale interventions across countries based on VfM.
- Builds trusted partnerships and potential to leverage additional donor funding.

Disadvantages:
- Requires strong programme management, particularly for adaptive elements.
- Potential delays in mobilising multilaterals and procurement processes.
- Developing multi-year long-term interventions that extend beyond the spending review period means including break-clauses, providing less certainty to suppliers.

All delivery modalities will follow FCDO standard templates and terms to ensure:
- Innovation and flexibility are enabled,
- Transparency and accountability,
- Strong focus on performance, audit, data protection, PSEAH, safeguarding, climate/sustainability compliance (as applicable), and conflict of interest management.

The FCDO team will ensure funding commitments are only made to organisations capable of delivering quality interventions and services within the EN context, fostering programme sustainability. For new agreements, existing enhanced due diligence assessments will be refreshed for suggested organisations to help identify and manage risks that could threaten the effective use of our funds. Prior to entering into any formal agreements and contracts, we will have a satisfactory level of assurance that each partner has the requisite capacity to deliver, account for funds and reporting. Any risks within identified tolerance levels will be included in the risk matrix, mitigated, and managed. Selected organisations will be expected to conduct enhanced due diligence assessments of their downstream implementing partners before FCDO will enter into a funding agreement with them. These partners are expected to robustly monitor their downstream partners and continuously manage risks across the programme delivery chain. The programme will review the evidence of what works through the programme performance reviews and based on this, FCDO could change the allocation of funding to partners to maximise impact.

      Performance‑based Reallocation of Funding Under the Procurement Act 2023
To support adaptive elements of this programme, noting that the majority of elements are expected to responsively managed, and ensure value for money throughout implementation, the programme’s commercial model will include a clearly defined mechanism enabling FCDO to reallocate funding between contracted delivery partners based on evidenced performance. This mechanism will be explicitly set out in the contract and reflected in the original procurement documentation, including the call‑for‑competition notice and contract award notice, in line with the requirements of the Procurement Act 2023 (PA23) governing “permitted modifications”. This approach ensures any future reallocation is lawfully provided for within the original terms and transparent to the market.

Under this model, FCDO will retain the option to adjust the distribution of funding between partners during implementation where programme evidence demonstrates differential performance, impact, or value for money. Exercising this option will not alter the overall nature or scope of the contract and will remain within the pre‑defined financial envelope and delivery parameters approved in this Business Case, consistent with FCDO Programme Operating Framework (PrOF) Rules 13–14 governing approved budgets, contract amendments and transparency obligations.

Any reallocation of funds will be supported by robust and documented contract management processes, including the ongoing monitoring of supplier performance against defined KPIs and reporting requirements. These arrangements meet the PA23 emphasis on strengthened in‑life contract performance reporting and transparency. Where reallocation is required, FCDO will publish a Contract Change Notice (CCN) prior to implementing the modification, as required under Sections 75–77 of the Act, ensuring compliance with legal obligations and maintaining an open audit trail.

This performance‑based reallocation mechanism enables the programme to remain responsive to emerging evidence and contextual changes while safeguarding accountability, competition principles and value for money. It also aligns with FCDO’s commercial guidance that the Commercial Case should set out how supplier performance will be managed and how the chosen commercial model will deliver VfM throughout implementation.

Delivery Model and Contracting Approach
The programme will utilise FCDO‑standard delivery modalities, applying established templates and contractual terms to ensure a compliant, transparent and well‑governed procurement approach. This will enable commercially sound delivery arrangements that promote innovation and flexibility while maintaining clear accountability and auditability. All delivery partners will be required to meet FCDO standards on performance management, safeguarding (including PSEAH), data protection, security, climate and sustainability compliance (as applicable), and conflict‑of‑interest controls. These expectations will be fully embedded within contract terms, reporting requirements, and oversight mechanisms.

Commercial Risk Management and Oversight
Full contract management and risk‑monitoring processes will be implemented in line with PrOF requirements, ensuring appropriate assurance, supplier oversight and escalation pathways. Selected partners will be expected to continuously monitor downstream delivery performance and manage risks proactively, with material issues escalated to FCDO. Review points and performance‑based mechanisms (for example PbR) will be built into the contractual structure to safeguard public funds, reflect the adaptive nature of some elements of the programme, and enable reallocation of resources if performance, context or evidence changes. FCDO retains the option to redirect funding to higher‑performing partners during implementation where programme evidence indicates stronger impact or value for money. This ensures the commercial model can support adaptation without undermining accountability or contractual clarity.

Cost elements that affect the overall price for different programme components
Benchmarking data from comparable programmes will be considered in context with the specific requirements including the nature and scope of the programme interventions. Cost breakdown for all components is as follows:
- Fee and direct expenses: Management fees, technical expert costs, and direct delivery costs for interventions are expected to constitute the majority of the budget. Especially when delivering adaptive programming.
- Exchange rate fluctuations: Budgets will be based on GBP commitments and managed in line with the PROF. Suppliers will be expected to manage FX and inflation risk within contracts, unless otherwise specified.
- Security: Contextual insecurity may increase administrative/duty of care costs relative to implementation. Security risk assessments and cost realism will be considered in bid appraisal.
- Price Reasonableness & Caps: FCDO’s commercial colleagues will provide assurance through-out the procurement and contracting process to ensure that a) costs reflect market prices; b) overheads are reasonable and in-line with fee caps pre-determined by FCDO; and c) organisations have the capacity to implement the programme effectively. The existing fee and cost data for similar programmes will be a useful benchmark to compare costs quoted by the contracted organisations. Implementing partners will be responsible for managing changes in costs due to currency fluctuations, inflation, changing security situations and for managing local taxes.

FCDO will set out clear expectations for its implementing partners on driving VfM. If required, FCDO will hold awareness raising sessions for all implementing partners to improve understanding of the concept of VfM. A VfM framework will be developed and maintained throughout the life of the programme. FCDO will ensure costs savings by using robust economy indicators within the agreed VfM framework.

Supplier Performance Management
Performance will be managed through KPIs and incentives (set-out in ToRs), including but not limited to:
- On time delivery of outcomes/milestones.
- Gender equality disability and inclusion compliance.
- Risk management responsiveness.
- Adaptive learning integration.
- Contracts will include flexibility conditions.
Workplans will be mutually agreed by FCDO and respective partners for each quarter of implementation linking to the logical framework. For each individual milestone, means of verification will be set out and agreed as part of this process. Agreements will follow the latest PROF suggested templates.

Payment Mechanisms
FCDO will apply payment mechanisms that incentivise effective delivery, ensure accountability, and protect value for money. The preferred mechanisms include:
- payments by Results (PbR) for specific outputs where feasible.
- payments on milestone-based to ensure accountability where feasible.

Contract Tiering and Management Resources
All commercial contracts under this programme are expected to be bronze, silver or gold tier, subject to final risk assessment using the Commercial Contract Tiering Tool. The programme will consider using call-down frameworks, where relevant. A dedicated Contract Manager (with appropriate accreditation) will oversee supplier performance. Governance includes quarterly performance reviews, annual audits, and proportionate assurance visits (subject to security).

Programme Delivery Cycle
The programme will be implemented in phases to enable adaptation and scale‑up of interventions that demonstrate effectiveness. All phases will follow four core stages: mobilisation, inception, implementation and closure. This phased approach is designed to support adaptive programming, informed by evidence, learning, and contextual change.

Mobilisation: Immediately after approval of the Business Case, the funding arrangements for implementing partners will be set up as per FCDO guidelines in line with PROF rules and templates. Milestones are:
  - initiation of the inception phase for programme and project design.
  - refresh of due diligence and assurance assessments to reflect Programme‑specific requirements and delivery risks.
  - early market engagement and analysis, where relevant, to map routes to market and identify appropriate procurement approaches for new or adaptive Programme activities.
  - signature of funding or delivery agreements with selected implementing partners.
  - Mobilisation activities will ensure that partners are fully aligned with Programme objectives, delivery expectations, and adaptive management requirements.

Inception Phase: All programme components will include an inception phase of up to three months, depending on start dates and delivery modality. The inception phase will be critical to refining programme design and operationalising the adaptive strand of the programme. Milestones are:
- detailed GEDSI analyses will be undertaken and integrated into delivery plans;
- assumptions within the theory of change will be tested and refined;
- learning and adaptation mechanisms will be confirmed where appropriate, including decision‑making thresholds for adjusting activities or approaches.
- procurement requirements necessary to support adaptive delivery will be identified and confirmed.
- All implementing partners will be required to submit a refined proposal, workplan, and detailed budget setting out how programme outcomes and impact will be achieved, including how adaptive approaches will be applied in practice.

Implementation Phase: During implementation, programme performance will be clearly linked to the actions and outputs of respective implementing partners. Delivery will be managed using either a responsive or adaptive methodology, with the latter requiring more regular and structured engagement than a traditional linear delivery model. Milestones are:
- periodic progress reporting against the programme log-frame, milestones, and KPIs;
- annual reviews to assess performance, value for money, and continued relevance;
- regular engagement between the programme team and implementing partners to review evidence, risks, and emerging learning;
- ongoing engagement with relevant FCDO policy teams to ensure alignment between delivery, policy priorities, and changing context.

Closure and Exit Strategy: As highlighted earlier, projects which are managed adaptively will follow a phased approach that allows uplift based on learning and delivery experience. The programme team will ensure that deliverables are sustainable and that there are appropriate government and stakeholder buy‑in to support a responsible and orderly exit by FCDO. Learning generated through adaptive delivery will be captured and documented to inform future programming and policy development.

FCDO will incorporate review points into delivery arrangements to support structured oversight, learning, and adaptive management. These reviews will enable FCDO and implementing partners to assess progress, validate assumptions, and refine delivery approaches where required.

Break clauses already included within FCDO’s standard Terms and Conditions (both fault‑based and no‑fault) provide FCDO with the contractual discretion to end an agreement where justified. These break rights may be exercised at inception or any point thereafter, should this be necessary due to spending review outcomes, shifts in programme priorities, or implementation difficulties.

Progression beyond review points will be informed by FCDO’s assessment of programme need, delivery progress, and alignment with strategic objectives. Underperformance will continue to be managed through the contract’s existing performance management mechanisms, including KPIs, reporting, and contractual remedies, and does not rely on the existence of review points.

Risk Management
Risks will be assessed during the tendering and mobilisation phases and will be incorporated into the Programme risk register where appropriate which will be updated on a regular basis. Risk will be monitored and mitigated through due diligence, delivery chain mapping, and adaptive contracting. The risk register is provided as Annex B.
Financial Case
Affordability and Funding Sources
The total programme value will be up to £39m over five years funded from FCDO ODA allocations within the Eastern Europe and Central Asia Directorate (EECAD). P4R will complement other programmatic activity across the EN portfolio, including with the Integrated Security Fund (ISF) (ODA and Non-ODA funding), and centrally managed programmes. Funding will be managed flexibly through the programme lifecycle to respond to contextual change while remaining within the approved ceiling. There are no capital costs (CDEL); all expenditure will be Resource DEL (RDEL).

The programme will combine multi‑country and regional interventions, provision of technical expertise and programme‑funded roles, and country‑specific programming – informed by political economy and contextual analysis. Delivery will include responsive and adaptive programming approaches, with the latter approach used in the most complex, political and volatile environments and allowing for reallocation of resources in response to evidence, learning and changes in the operating context. This blended approach reflects lessons from GGF and ISF programmes, where regional shocks, political shifts, changes in the donor landscape have required portfolio‑level agility, iterative decision‑making and flexible financing arrangements. The Financial Case focuses on affordability, financial controls, fiduciary risk management and value for money.

Contingency and Financial Flexibility
A contingency of 5% of total programme value is proposed to manage inflationary pressures, foreign exchange volatility, and delivery risks. This level of contingency is consistent with advice from the EECAD Finance Business Partner and reflects experience from GGF and ISF, where operating environments have deteriorated or changed rapidly, requiring response to a markedly different context.

Flow of Funds
Funds will flow in the following manner: FCDO → P4R → Delivery Partners (CSOs/NGOs, Suppliers, Multilaterals, IFIs) → Beneficiaries. Delivery chain mapping will ensure visibility and accountability of funds throughout the supply chain.

Indicative Allocations
The Business Case value is up to £39m. For the three-year Spending Review period, beginning FY26/27, the annual allocation is expected to be £6.4m per year. Over five years, this equates to a total of £32m of planned allocations, with the remaining headroom retained to provide flexibility during implementation and ability to respond to potential rapid changes/need within the EN region.

Table 1 below sets out indicative budgets by activity. Table 2 sets out indicative country allocations, including regional scope, these are not ringfenced and will be modified depending on the changing priorities and the operating environments. MEL, Programme funded roles, L&D and contingency are required to support effective oversight, adaptive management, fiduciary assurance and learning across a complex, multi‑country portfolio.

Costs to be incurred by FCDO
FCDO costs include staff time associated with programme management, commercial oversight, governance, technical assurance and travel and L&D. The indicative level of effort required from EN programme teams and cross‑cutting functions is set out in the Management Case.

Costs to be incurred by third party organisations
These costs will include direct cost of project implementation, Partner staffing and operational costs and overhead charges by partners. Overheads will include those for respective partner headquarters, pre-agreed with FCDO and against PrOF Non-Project Attributable Costs (NPAC) guidance. The EN Programme Hub will ensure that robust controls are included for downstream partner monitoring and duty of care in insecure environments.

The adaptive nature of some programme components is expected to generate higher transaction costs than traditional delivery. This reflects more frequent review points, increased engagement with downstream partners and beneficiaries, and iterative redesign of interventions based on learning. These additional costs are considered proportionate and justified where they improve relevance, effectiveness and overall VfM.

The programme will also coordinate, where appropriate, with multilateral organisations such as the World Bank and EBRD, exploring opportunities to support existing trust funds or ongoing programmes where there is clear strategic and financial complementarity.

Sector Codes and Markers
Sector	Code	Marker
ICF	International Climate Finance	0 – not targeted
Paris Climate Agreement Marker	Climate Rio Markers	0 - not targeted
Gender Equality Markers	OECD DAC GEM Markers	GEM 1 - Significant objective

Disbursement Mechanism and Schedule
By default, payments will be made in arrears, based on verified milestones or outputs delivered. Advance payments may be considered where justified and in line with PrOF Rule 24, subject to PRO or SRO approval. Where advance payments are required (notably for NGOs, IFIs and Multilaterals), the programme team will ensure payments are not in advance of need and are clearly linked to intended outcomes. Where possible, an 80% utilisation requirement will be incorporated into agreements and MoUs.

Assessment of Financial Risk and Fraud
Overall fiduciary risk is assessed as Major, but manageable through strong controls, informed by experience under GGF and ISF, where similar risks were successfully mitigated.

Risk mitigation measures include:
- Robust due diligence and delivery chain mapping for all partners – due diligence and delivery chain mapping will be conducted for all partners (prior to receiving funding). This will build on existing central assurance assessments, due diligence and fiduciary risk assessments of partners and similar checks conducted by FCDO centrally.
- Working with partners to strengthen fiscal management systems and conduct thorough oversight of tranche requests and invoices (inc. random spot checks).
- Use of independent audits where appropriate.
- Quarterly/annual review platforms will further validate all data reported.
- Quarterly financial and narrative reporting requirements will be incorporated in all arrangements (Multilaterals and trust funds may be exemptions).
- Bi‑annual reinforcement of FCDO’s zero‑tolerance policy on fraud and corruption.
- In case of fraud being detected, programme team will work with partners to suspend payments, investigate, and recover funds where possible.

Tax Considerations
In line with the General Anti‑Abuse Rule (GAAR) and FCDO requirements on tax compliance, all partners will be required to represent and warrant that, as at the commencement date of any agreement, they have notified FCDO in writing of any Occasions of Tax Non‑Compliance, including any related litigation. Should an Occasion of Tax Non‑Compliance arise at any point during the term of an agreement, partners will be required to:
- Notify FCDO in writing within five working days of the occurrence; and
- Provide details of the actions being taken to address the issue, prevent recurrence, and identify any mitigating factors.

Where partners are liable to be taxed in the UK or pay national insurance contributions in respect
of consideration received under the agreement or contract, the partner will be bound to:
- Comply at all times with the Income Tax (Earnings and Pensions) Act 2003, the Social Security Contributions and Benefits Act 1992, and all other applicable tax legislation; and
- Indemnify FCDO against any income tax, national insurance, social security contributions or related liabilities arising from the provision of services by the partner or its personnel.
Potential tax liabilities, including VAT, income tax and relevant local taxes, will be assessed during the contracting and agreement stage and addressed through appropriate contractual provisions.

Accounting considerations arising from the programme (Asset Management)
There are no accounting considerations: the programme is not expected to create any material assets or ongoing liabilities for FCDO. However, a limited quantity of low‑value assets may be procured by delivery partners to support programme operations and delivery (for example, office equipment or operational assets in delivery locations).

All such assets will remain the responsibility of delivery partners and will be managed in accordance with FCDO asset management guidelines. Partners will be required to maintain comprehensive and up‑to‑date asset inventories, which will be subject to review through routine programme oversight and annual audits, proportionate to the scale and risk of the intervention.

At the conclusion of the programme, or upon completion or termination of individual agreements or contracts, decisions on the disposal of assets will be taken by FCDO in consultation with stakeholders. Disposal options may include transfer, sale, storage or write‑off, and will be determined in line with VfM principles, audit requirements and local legal considerations.

Monitoring, Reporting, and Accounting
Monitoring and reporting requirements will be proportionate and risk‑based, reflecting the diversity of delivery models,
- Standard programming: quarterly technical and financial reporting
- Adaptive programming: more flexible arrangements such as bi‑annual reporting supplemented by monthly or quarterly updates

Reporting frameworks will be agreed with partners in advance and reviewed regularly to ensure they support learning and adaptation while maintaining accountability.

The programme will operate under resource‑based accounting, in full compliance with FCDO standards, and will follow Procure‑to‑Pay (P2P) guidance, including three‑way matching (purchase order, goods or services received, and invoice) for all payments. This methodology will be applied to validate each payment, ensuring consistency across documentation. The approach strengthens financial controls, mitigates the risk of discrepancies, and upholds transparency and accountability throughout the implementation period.

The programme will work with a diverse range of delivery partners, including CSOs, commercial suppliers, multilaterals and IFIs. All partners will be subject to proportionate assessment of financial management capacity prior to contracting, in line with PROF requirements. This will include review of financial controls, internal policy on financial management, audit history, staffing capacity, and systems for managing funds and downstream partners.

Due Diligence Assessments will be completed for all partners, with Central Assurance Assessments (CAAs) relied upon where appropriate. The depth of assurance applied will be risk‑based and reflect funding size, delivery environment and use of sub‑grants. Primary delivery partners will remain responsible for assessing and monitoring the financial capacity and compliance of all downstream partners throughout implementation.

Audit
In with relevant legislation, all commercial delivery partners and any relevant downstream suppliers will conduct annual independent audits. Audit findings will be reviewed by the PRO and Programme Managers and followed up where required.

All non‑commercial partners delivering high‑value or high‑risk interventions must also provide an annual independent audit, consistent with standard Accountable Grant Arrangement (AGA) requirements. Where audit findings identify weaknesses, the PRO will ensure appropriate remedial actions are implemented and monitored. For low‑value and low‑risk interventions, a proportionate approach to audit and assurance will be applied, subject to decisions by the PRO and Senior Responsible Owner (SRO).

Value for Money (VfM) Summary
A blended portfolio approach (with multi‑country and regional interventions, country‑specific programming and use of responsive or adaptive management as appropriate) offers strong VfM by combining flexibility, strategic alignment, and cost-effectiveness. VfM will be monitored through 4Es, unit cost analysis, and learning. Detailed VfM governance, decision‑making and accountability arrangements are set out in the Management Case.

Following HMT Green Book guidance, VfM will be monitored using a combination of quantitative and qualitative methods:
4Es Framework:
  1. Economy: Benchmarking input costs against market rates and procurement standards.
  2. Efficiency: Tracking unit costs (e.g., cost per output or beneficiary) and comparing against planned budgets.
  3. Effectiveness: Measuring achievement of intended outcomes using KPIs and adaptive learning reviews.
  4. Equity: Assessing whether benefits reach marginalized or priority groups fairly.
If programme allows Cost-Benefit Analysis (CBA):
  1. Where feasible, comparing expected benefits to costs over the programme lifecycle. This will ensure decisions are evidence-based and resources are allocated to interventions that maximize social value
Adaptive Learning Metrics:
  1. Monitoring changes in portfolio composition and documenting decisions that improve VfM over time.
1. Regular VfM Reviews:
  1. Integrating VfM checks into quarterly reporting and decision-making processes.

MEL
Up to £0.5m per year will be allocated for MEL on programme level, with resources being set aside for MEL from external providers. Components which use an adaptive methodology are expected to build MEL into these projects to facilitate regular learning and adapting accordingly. Implementing partners/managing agents will set out their budgets for MEL activities during project design, to be agreed as part of funding agreement. Combined, expenditure on MEL will be around 5-10% of the programme budget (with a maximum of 10% in the case of highly adaptive, innovative programmes). Other MEL requirements such as for the responsive projects will utilise FCDO MEL contracts with an external MEL supplier which covers the EECAD regions.

Management Case

Programme Management Set Up

The programme will be delivered through a single HMG department, FCDO, and will fall under the EECAD remit. Portfolio fit will be overseen by the EN Strategy Board and regional portfolio SRO with delivery oversight by the Posts’ Programme Boards.

The SRO will be supported by a Senior Programme Manager as the PRO, who will lead the programme’s implementation and drive delivery of programme outcomes on a day-to-day basis. The PRO will be responsible for effective management of risk, MEL and leadership within EN programme teams, combining technical, programme management and relationship management.

The programme will take a multi-disciplinary approach, drawing on technical advisers based in the region, political teams in the region, and UK based advisors, providing a strategic view of trends and issues, while advising on project-level dynamics, and brokering further expertise from FCDO Communities of Expertise. The SRO will ensure wider coherence with the HMG Portfolio, including ISF programming and other centrally managed programmes. The EN programme Hub, which has pooled resources and expertise in programme management (including working in GGF), will support with areas such as MEL, risk, financial management and procurement. The GGF (Phase 2) Project Completion Report (PCR) identified that the blend of political, advisory and programme management experience is important for the success of the programme.
Responsive and Adaptive Management

The programme will employ two different programming approaches, responsive and adaptive management. Responsive management is defined as projects that amend goals or activities in response to changes in the context, for example as took place in response to Covid-19. Adaptive management is defined as projects with a known objective but the causal pathway to achieving these objectives is not clear, therefore testing, learning and research is required to help establish these pathways. As such, solutions to tackle specific problems are not clear, so a premium is put on innovation, iteration and evaluation to help determine this. For example, when the objective is known, women’s economic empowerment, but there is a lack of evidence on how to achieve this in a given context and/or a highly political operating environment.

The majority of programme components are expected to take a responsive approach, while a minority of projects, where the political context is particularly complex and/or outputs unknown, are expected to be adaptive, placing a greater emphasis on innovation and learning. Further, as adaptive management is a new way of operating for EN programme teams, during the first year of the programme adaptive management will be trialled across one, possibly two, projects. This will allow the team to both build their understanding of this approach, develop relevant partnerships, including with delivery partners, and better test VfM. Based on this learning, an adaptive management approach may be scaled up (or down).

Based on the Central Asia Development Programme Team implementation experience and learning from other adaptive programmes, this approach may include:

- Ensuring timely data collection from programme interventions and external environment to assess the need and for adaptation.
- Enhanced use of data and learning to inform programme decisions. This will include decisions to enter and exit from policy areas, geographical areas etc. FCDO will build formal strategy reviews with delivery partners on a regular, e.g. six-monthly basis, to discuss programme adaptations.
- Selecting delivery partners that have experience of adaptive management and designing mechanisms through which our partners are incentivised to utilise the approach.

The following systems/tools may be used in the programme to facilitate adaptive management:

Active use of the results framework (Theory of Change and Log Frame): This may involve encouraging delivery partners to actively monitor changes in the assumptions, developing log frames which incentivise learning, coordination, and exploring way to measure adaptation, which may use a range of tools. Tools like Political Economy Analysis (PEA) will be used to guide implementation.

Timely data collection and learning: delivery partners will be required to generate timely data to inform programme adaptation. Programme performance data and analysis of the context (e.g. through PEA) should be routinely interrogated to inform decisions on any necessary adaptation. FCDO will ensure that programme agreements incentivise this approach, e.g. using a flexible results framework. Implementers will be expected to use this data to monitor and react to important portfolio and external changes and inform ENSB of key developments.

Use of adaptive contracting: While each component of the programme will have budget ceilings and indicative budgets will be allocated during the start-up phase, detailed workplan and budgets will be agreed with implementing partners on a regular basis, e.g. annual. This will allow the programme to shift resources away from less effective areas and to activities that generate high VFM.

Programme Management Tools

The following tools will be used to aid programme management by the programme delivery team:

A single delivery plan will be established and regularly monitored to keep track of the main programme activities, key decision points, and financial performance. The core programme team will meet monthly to review and update the plan.

A risk matrix and delivery chain map to track programme risks and progress against mitigation measures. These tools will be updated regularly. Different programme components will be required to provide risk analysis as part of their regular quarterly reporting to FCDO.

A results framework will be developed, including to reflect adaptive programming elements, during the start-up phase and refined during the inception phase. The results framework will track progress against the theory of change (ToC) at the output, outcome and impact level and support the monitoring of assumptions underpinning the ToC. This will be monitored annually using the annual review process.

A VfM framework will be developed to allow the programme team to track programme VfM over time based on indicators.

Political economy analysis frameworks will be developed to support the understanding of political and economic contexts and how they influence the programme’s outcomes.

The FCDO annual review process will review programme performance. It will review performance against the results framework, assess VfM (making use of the VfM framework), review performance and assess risk. It will make a series of recommendations for the programme team and implementers to action.

As required, FCDO will commission independent evaluation of the programme to inform further stages of implementation. This will look at all the aspects described in FCDO’s annual review process but will also consider how effective the programme is being at achieving the target outcomes and impact.

Monitoring, Evaluation and Learning

The MEL approach will integrate principles of adaptive management, to ensure that the programme can deliver in changing and politically volatile contexts. It will adhere to the FCDO PROF and respond to PCR recommendations from the previous programme (GGF Phase 3) as well as recommendations from the independent review of the GGF Phase 3 programme.

A MEL plan will be developed for the programme. Key elements of the plan could include (but not be limited to):

- Overall programme evaluation framework
- Analysis of the programme Theory of Change, assumptions made and its relevance.
- Process/performance and or impact evaluations of specific elements of the programme where this can inform the wider evidence base.
- Assessment of implementation approach (stakeholder engagement, influencing, management, coordination, GESI)
- Assessment of programme risks
- Assessment of output, outcome, and impact performance
- Analysis and measurement of VfM
- Review of programme in the context of EN overall portfolio (linked to cross portfolio MEL) and the changing external environment (linked to EN overall theory of change).

Projects will each have their own results framework and risk register, which will be aligned with the overall programme results framework and risk register. These are reviewed and updated regularly (at a minimum quarterly).  Where projects are following an adaptive approach there will be rapid feedback loops and regular reflection sessions to assess progress and make decisions around what to scale up and what to stop funding. This will involve smaller pilots which are monitored closely to allow assessment of progress in a rapid manner. Undertaking conflict sensitive MEL will also be important.

The programme ToC should be reviewed regularly and updated as needed with input from the Governance, Economics and M&E Advisers, informed by political economy analysis, conflict and gender analysis to identify whether change processes are as expected, challenge assumptions, analyse barriers and identify new opportunities for change. This process aims to ensure a responsive and adaptive portfolio that retains relevance and avoid the risk of HMG investing in areas/projects that will not deliver desired change. Relevant stakeholders will be consulted as part of this process to test and challenge thinking, including for instance implementing partners, development partners, researchers and civil society representatives.

Proportionate country results frameworks will be developed to underpin the programme results framework, outlining country-specific contributions to the programme outcomes and outputs. Strong monitoring, evaluation and learning is central to this programme, particularly for adaptive components where implementing partners will need to make routine use of data and evidence to continually assess progress and ensure the programme remains relevant to the context. Delivery partners will be responsible for developing data collection tools agreed with FCDO, collating data across the portfolio of interventions, analysing and interpreting data, and presenting to FCDO.

Indicative indicators are set out below and will be further developed during inception. Where possible, indicators will be disaggregated by gender, age, location, disability (using the Washington Group Questions). The results framework will also aim to capture the wider development impacts of programme interventions.

A results framework will be developed with implementing partners during as part of inception, but some indicative indicators could include the following;

Outcome:
- Number of partner public institutions demonstrating changes in policy‑making, budgeting or service delivery practices influenced by P4R support
- Examples of strengthened electoral, oversight or accountability functions in supported contexts
- Evidence of improved regulatory quality, competition policy, State Owned Enterprise governance or market oversight in supported sectors
- Private sector or stakeholder feedback indicating improved predictability, transparency or inclusiveness of economic rules

Output:
- Number and type of public institutions receiving sustained technical assistance
- Evidence products (PEAs, diagnostics, policy notes) produced and actively used by P4R-supported institutions
- Number and diversity of CSOs, media outlets or local leaders supported, disaggregated where possible (e.g. gender, youth, disability, minority groups)
- Partnerships established with IFIs, multilaterals or private sector actors to advance reform

Evaluation

A evidence and learning strategy will be developed prior to the start of the new programme, further assessing the evidence gaps. This strategy will inform the type of evaluation that may be undertaken (e.g. process, performance) and respond to common challenges in evaluating technical assistance programmes which include time lag (outcomes not transpiring until long after projects have ended) and attribution, influencing factors, and the complexity of reform processes, as well as integrate learning from evaluation during GGF phase 3. Any evaluative work commissioned by HMG will be done in line with FCDO’s evaluation policy, ethics principles and will be submitted to FCDO’s independent quality assurance service (EQUALS).

In case of relevant commonalities across country-led projects (e.g. in terms of themes), evaluation may take a multi-country thematic perspective. Evaluation at this level will be led the external MEL provider and implemented by the PRO and EECAD MEL Adviser.  Programme evaluation will be used to assess the extent to which outputs are leading to outcomes and impact, and to test the assumptions in the Theory of Change.

Learning

Learning involves the integration of evidence - from GGF, HMG and the wider evidence base - to inform decision-making or programming. In addition to specific learning activities planned by implementing partners as part of their project MEL plan, learning is supported through the following mechanisms/activities:

- Commissioning of evidence synthesis products through available helpdesks to inform programming (e.g. on thematic areas of intervention, gender equality, disability inclusion).
- Governance and economic networks used for the exchange of experiences, lessons, ideas and to highlight latest evidence
- Learning sessions on specific topics (e.g. MEL, GEDSI, VfM)
- Annual workshop to bring together those working across EN programmes
- Production of user-friendly evidence products and thematic learning pieces (based on MEL, network meetings, wider evidence base)

Working with the delivery partners and the EECAD MEL adviser, the programme team (lead by the PRO) will look to disseminate programme learnings. This could take the form of:
- Generation of learning products such as case studies, policy briefs, and research papers – tailored to the target audiences (led by implementers).
- Packaging monitoring data, results and VfM performance for ENSB, national governments and other relevant stakeholders to guide strategic decision making.
- Dissemination of research and evidence through workshops, conferences, and global learning events.
- Learning from similar programmes globally and providing periodic insights and advice to shape programme interventions.

M&E Governance

Four groups of stakeholders are involved in the collection, analysis and reporting of MEL information to support the SRO and PRO in performing their MEL-related responsibilities:

- Implementing partners – undertake their own MEL to support results management and ensure that evidence and learning guide project decision making, in line with guidance established by the GGF and based on PROF requirements)
- Staff at Post (where relevant supported by political teams) - monitor the implementation of projects on the ground, sharing learnings and reflections across the region, lead on relevant KPIs and report against relevant indicators in the results framework.
- Programme Advisory and Results Group in HQ, including Monitoring and Evaluation Advisory capacity – support the SRO and PRO by advising on the overall MEL approach, the ToC and programme results framework, as well as MEL arrangements with implementing partners.
- Regional MEL provider for EECAD – will, once in place, support selected MEL functions focussing on the assessment/verification of outcome level change, generation of (evaluative) evidence, and the capturing of key lessons around implementation, bringing in innovative M&E approaches.

Risk Management

The overall risk rating of the programme is Eager, reflecting risk ratings for Strategy and context, reputational and policy and programme delivery.

The programme has an Eager risk appetite for both Strategy and Context and Policy and Programme Delivery Risks, considered to be major to severe. The appetite for Financial & Fiduciary, Safeguarding and People is cautious due to the FCDO’s zero tolerance risk approach to Fraud and Corruption and Sexual Exploitation and Abuse and Sexual Harassment (SEAH) and robust policies and systems in place to ensure the safety of their staff and any third parties involved in the programme. Given the programme will work with children, young vulnerable and marginalised groups, specific attention will be paid to safeguarding risks to ensure the programme does no harm. Any risk falling outside of appetite will be escalated though agreed routes to the Regional Development Director and beyond.

Risks will be managed through the programme’s risks register. An initial overview of key risks and mitigation is provided below. The programme team will mitigate these risks by ensuring the programme is adequately resourced and appropriate governance structures are in place to support the design, planning and implementation stages. Risk analysis and the risk register will be refined further during the programme’s inception phase and will then be reviewed and updated regularly during implementation. Quarterly progress meetings with the implementing partners will have a standing agenda item on risks to discuss and update the understanding of risks and effectiveness of mitigating measures.

What are the risks and how will these be managed?

Overall, we assess the programme risk to be Eager taking into consideration the scale, complexity and geographical coverage of the programme.

Our risk appetite by category is set out in annex A, this will be regularly reviewed and revised as needed. The key risks are set out in annex B; these will be closely tracked by the PRO who will hold ownership and report to the SRO routinely on risk. Individual country risk registers for the programme will be held and maintained by post, with support from the EN hub as required.