Concept Note for Approval
Programme Title: Eastern Neighbourhood - Partnerships for Resilience Programme (EN-P4P)
Programme Value: Up to £39m					Directorate: EECAD
Threshold for Approval:					Minister of State (Europe, North America, and Overseas Territories)
Programme duration: / 5 years			Start Date: / April 2026			End Date: / March 2031
Overall programme risk rating:			Major
Novel and Contentious:		No	Reputational risks and UK political handling issues:				Given the high level of geo-political competition in the EN region programming will face disinformation challenges.
Programme ID:		Tbc
PORTFOLIO / FIT		Supporting European security by building resilience are key drivers for UK interest in Moldova, Georgia, Armenia and Azerbaijan collectively the Eastern Neighbourhood (EN). The stability and resilience of countries in EN is critical to UK national security. This programme will support the EECAD Directorate Plan goal of: Support the sovereignty, resilience and inclusive development of the Central Asia & EN region and deliver on UK security, economic growth and climate and energy priorities. The programme will also support the objectives of Country plans across the EN region. / The programme will complement the high-risk Integrated Security Fund’s (ISF) work, countering direct state threats and hybrid warfare. This ODA programme will work at the intersection of security and resilience, focusing on reducing longer-term vulnerabilities including through systems strengthening. / We are also bidding separately for modest non-ODA resources which will be used to scope and facilitate strategic economic partnerships for UK firms on the connectivity and infrastructure as part of the Azerbaijan-Armenia peace process (including the US led TRIPP programme).
PROGRAMME / NARRATIVE		The ability of EN states to protect their independence and choose their own development pathways is undermined by weak state and non-state institutions, weak accountability and rule of law, and chronic multidimensional fragility. States are unable or unwilling to tackle vulnerabilities, including ongoing internal and external conflict, and economic shocks, energy insecurity, foreign influence over critical infrastructure, poverty, and limited ability to mitigate the impact of climate change. Shocks are often triggered by external factors and malign actors. / The region is politically volatile, with emerging opportunities presented by the Armenia/Azerbaijan peace process, to Moldova’s continued trajectory towards EU accession following recent elections. A flexible approach which allows the programme to pivot to changing contexts will be critical, informed by analysis, evidence and lessons learning. The programme will provide targeted support to drive systematic change, putting a premium on investment in knowledge and relationships, the ability to spot opportunities and respond at pace, and use of different modalities. Working in partnership with receptive governments and a broad range of actors, including the IFIs, this programme aims to support the building of EN countries’ resilience through; / Democratic and societal resilience: strong and inclusive public institutions and systems, effective public service provision and democratic accountability are a pivotal part of supporting EN countries to build their resilience to withstand malign influence and shocks. Partnering with receptive governments and a range of actors to strengthen national and district institutions will support countries in building systems which respond to local needs, but also to achieve their own democratic development pathways and geo-political positioning. Gender equality and broader inclusion of marginalised groups will be a critical part of building this inclusive democratic and societal resilience. This pillar of the programme will also address the challenges of societal polarisations and exclusion, including political economy and conflict sensitivity analysis. / Local leadership and civil space: local leadership and civil society are critical in ensuring that the voices of citizens, particularly women and LGBT+, are heard and that sustainable development process meet local needs. An active civil society, independent media and freedom of expression are an important part of building a thriving democracy, providing citizens with a range of perspectives. Local leaders, independent media and Civil Society Organisations (CSOs) also support increased civic participation and engagement, and improve political accountability and transparency. This is particularly important when it comes to elections and referendums, which are often trigger points for malign action such as dis- and mis-information campaigns.
		Economic resilience: Limited or slow economic growth, compounded by external shocks, such as conflict and energy price volatility, present significant challenge in the region, both in terms of household-level deprivation, and macro-level system vulnerabilities. In order to improve the lives of their citizens and to secure long-term resilience, inclusive economic growth and reform is critical. Strengthening economic regulation and private sector institutions are a central part of this and will reduce vulnerability to external influence and support the economic stability and reliability required for increased trade and investment. Where governments are receptive, this programme will develop smart and targeted coalitions and partnerships with IFIs, multilateral agencies, and the private sector to support the building of economic resilience, without displacing local capability. / Across these three pillars, gender and wider equalities will be mainstreamed, with this being an explicit objective of the programme. The inception phase will consider themes of women's leadership, and of gender-based violence, for example. This work will be critical in addressing inequalities that are instrumentalised and promoted to undermine democracy and stability across EN.
	STRATEGIC	The region’s geographic and geo-political positioning at the intersection of Europe and Russia/Asia mean local developments impact European, and in turn, UK security. This disparate group of countries, require increased resilience to withstand malign influence and shocks. Whilst the ISF tackles direct security challenges in the region, this programme is needed to tackle fragility and support long-term resilience. / This need has deepened with the other donors having recently withdrawn or reducing their ODA spend in the region, with notable gaps in international support for democratic and economic reform. The programme will make targeted investments where the UK can have greatest impact, coordinating with and leveraging investment from others, such as the IFIs and EU. / UK comparative advantage / Established extensive networks in the region, across governments, the private sector, and civil society, at the intersection of democratic and economic resilience, alongside security and defence. / Strong reputation in the region for democratic institutions, technical and regulatory expertise, market economy, development diplomacy and higher education and cultural links, which we can draw on to support locally owned systems change. / Delivering the Good Governance Fund programme in the region for 10 years has enhanced the UK’s reputation as a valued partner and has enabled broader discussions and relationship building with governments and multilaterals.
	ECONOMIC	We have considered the following options: / Multiple Regional Programmes on specific priority themes: Focusing on a few narrowly defined priority themes (e.g. rule of law, gender, economic growth), providing thematic clarity. / Programme via IFIs: Work with regional IFIs and IMF/WB, who have significant leveraging capability. This would require minimal HMG project management resources and can be executed with a limited budget, however our work would be constrained by the thematic focus of the IFIs and we would not be able to respond to the shifting context in such an agile way. / Continuation of the current EN Good Governance Fund: Continue to deliver demand led support, covering a broad scope of work. / Country specific programmes: A standalone programme for Moldova, and a South Caucasus programme. Alternatively, Azerbaijan could be considered as part of Central Asia programming, with a regional programme covering Moldova, Georgia and Armenia only. / Adaptive Democratic, Social and Economic Resilience Programme (recommended): Incorporating country-specific and multi-country projects aligned with an integrated programming and policy portfolio theory of change for the region and Country Plans. This would offer flexibility to respond to emerging opportunities through adaptive management, harnessing learning from previous engagements. This approach supports regional efficiencies and navigates sensitivities by scaling interventions across countries based on VfM. It also allows for a diversified portfolio of delivery partners. / Recommended Approach / Options one and two lack the flexibility needed in the changing EN environment. Option three covers a wide scope of activity, which in the current resource constrained environment is too broad, it is also not as flexible as required, having not been designed for today’s geopolitical context. Option four could provide flexibility within the standalone country programmes. However, option five allows for multi-country projects, addressing common EN challenges, and provides additional flexibility, with resource and expertise redeployed with ease across the region responding to changing country contexts.
	COMMERCIAL	To ensure appropriate portfolio diversity and to demonstrate the best value for money, future programming will consider a range of routes to markets including: / Engaging with multilateral organisations – opportunity of influencing existing programming of multilaterals/IFIs by leveraging UK expertise, analysis, and diplomatic influence. / Consultations and calls for bids from international and local NGOs and academic institutions, including those that focus on gender, equalities and women’s rights, providing opportunity for building civil society capability and local leadership opportunities / Commercial contracts/call-down contracts –through competitive tenders with expert implementing partners. / A commercially procured fund or component manager to bring in external expertise and reduce demands on in-house resourcing. / We envisage the programme will combine a mixture of modalities, to allow for a more tailored and flexible programme that can be used like a toolbox, with the appropriate component selected for each context and desired outcomes, drawing on both in house and external expertise.
	FINANCIAL	The programme will cost up to £39m over five years, this will allow for medium term development programme in line with best practice, while appropriate break clauses will be built into relevant agreements in line with Government Spending reviews. A proportion of the programme is expected to focus on multi-country programming, technical expertise and support, including programme funded roles, as well as country-specific programming based on contextual analysis.
	MANAGEMENT	Portfolio fit will be overseen by the EN Strategy Board and regional portfolio SRO (HMA Tbilisi), with delivery oversight by the Post Programme Boards and the EN Development Director. / The EN Development Director (G6, based in the region) acts as the SRO, supported by a Senior Programme Manager (SEO, based in the region) as the PRO. The programme will take a multi-disciplinary approach, drawing on regional advisers based in Armenia, Georgia and Moldova, political teams in the region, and UK based advisors, providing a strategic view of trends and issues, while advising on project-level dynamics, and brokering further expertise from FCDO Centres of Expertise, HMG and beyond. The EN programme Hub, which has pooled resources and expertise in programme management, will support with areas such as risk and financial management. / The programme will be managed in an adaptable way and results will be reviewed regularly. Governance arrangements will be finalised in the business case, aligning with FCDO best practices. This will clarify decision-making processes and balance FCDO HQ oversight with empowered Posts and decentralised decision-making.
	RISK	Contextual: Malign influence and democratic backsliding in EN countries are significant risks. Combined with increasing authoritarian behaviour by some of EN governments, this could further reduce the space within which the programme can effectively operate and underscores the need for an adaptive approach. There is a significant risk of conflict in the region which may materialise, influenced by local dynamics, geopolitics and the future outcome of Russia’s war on Ukraine. / Reputational/Delivery: Further reductions of ODA funding and cooperation from likeminded partners would impact the implementing partners landscape and the UK's potential alliances and position, potentially leading to more public criticism, reinforcing anti-Western disinformation narratives. Democratic backsliding in some EN countries may also reduce our ability to work with local actors and civil society and/or pose significant risks to people working for these organisations. / Delivery: An adaptive programme requires significant staffing resources, expertise, and experience. Staffing gaps and resource pressures could negatively impact our ability to manage the programme adaptively.
	RECOMMENDA-TION	We recommend you approve this concept note. The concept note is the product of collaborative work across EN country teams, HQ policy and advisory teams and received strategic input from the Politics, Governance and Rights Centre of Expertise. / The next stage Business Case design will develop the themes identified in this note as well as setting out how the programme fits within the wider regional portfolio.
	Outcome:			[[Approved/ Approved with Conditions/ Rejected]]
	Conditions (if applicable):
	Notes:			[[Feedback to accompany any full approval or rejection]]

Annex A: Assurances Table
Legislation: Development Act, Gender Equality, / Public Sector Equality Duty, Counter-Terrorism	In accordance with The International Development (Gender Equality) Act 2014, the programme will support the reduction of the gender equalities, informed by Gender Equality, Disability and Social Inclusion analysis. This is expected to cover assessing the role of gender, equalities, and rights in delivering the outcomes, preventing harm, and as desirable outcomes in and of themselves. / In line with the Public Sector Equality Duty (PSED), the business case will assess the equalities impacts of the programmes. This will be used to inform decision making across the lifetime of the programme, as well informing the development of success indicators that contribute to closing equality gaps. The business case will also consider how to best reach the EECAD commitment to 80% of ODA programming achieving a Significant or Principal Gender Equality, Disability and Social Inclusion marker by 2030.
Safeguarding Considerations:	The Social Development Adviser, Risk Advisor, and EN Regional Safeguarding Champion will support the design of programme and interventions to do no harm. The design and mobilisation process will also utilise country-based staff inputs to consider the local cultural, economic, political, and social context across the region, and will include robust, meaningful community engagement early in the process. This will enable identification of key safeguarding risks and with appropriate mitigations.
Climate and Environment: / Paris Alignment / Environmental Protection / International Climate Finance (ICF)	Some activities are expected to ICF eligible. Exact proportions of programme spend for ICF will be scoped during business case design. / There are no specific climate-related or environmental risks in this concept note, and the proposed programme would not be considered as climate or environment sensitive. / Programme activities are not anticipated to directly contribute to climate change or carry environmental risk. We do not expect any activities to have nature benefits. A climate and environment risk assessment will be conducted as part of the business case. / The programme will align with the Paris Agreement and comply with the UK fossil fuels policy and Prof Rule 5 requirements. / PARG’s accredited Climate and Environment Adviser will quality assure the programme’s business case and input on programme and mobilisation implementation.
Nutrition:	No direct or indirect interventions to improve nutrition are considered in this concept note.